## TIP as of 2025_12_03
Agency | Section | MAG ID | Location | Federal Functional Classification | MAG Mode | Estimated Date for Completion/Open to Traffic | AQ Area | In Program | Miles | Lanes Before | Lanes After | PM1 - Safety | PM2T - Transit Asset Condition | PM2N - Pavement Condition | PM2B - Bridge Condition | PM3F - Travel Reliability | PM3S - Non SOV Travel | PM3E - CMAQ Emissions | On NHS | TIP ID | Local ID | STIP ID | Federal ID / Grant ID | TRACS / ALI | Work | Work Year | Funding | Apportionment Year | Federal | Regional | Local | Total | Note
ADOT | Highway | 60858 | 10 (Maricopa): SR202L Santan - Riggs Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 6 | 4 | 8 | Yes | No | Yes | Yes | Yes | Yes | No | Yes | DOT09-698 |  | 5723 | 010-C(222)S | F0252 | Construct freeway widening | 2026 | RARF | 2026 | 0 | 191802857 | 0 | 191802857
ADOT | Highway | 39146 | 85: Broadway Road and Baseline Road | Principal Arterial - Other | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 2 | 4 | 4 | No | No | No | No | Yes | No | No | Yes | DOT20-866 |  | 44811 | ----- | H8006 | Design interchange improvements | 2026 | RARF | 2026 | 0 | 2024000 | 0 | 2024000
ADOT | Highway | 56320 | 10 (Maricopa): Koli Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 1 | 0 | 4 | No | No | No | No | Yes | No | No | Yes | DOT22-820 |  | 7787 | ----- | ----- | Construct new interchange | 2026 | RARF | 2026 | 0 | 82570827 | 0 | 82570827
ADOT | Highway | 60858 | 10 (Maricopa): SR202L Santan - Riggs Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 6 | 4 | 8 | Yes | No | Yes | Yes | Yes | Yes | No | Yes | DOT22-835R |  | 5723 | 010-C(222)S | F0252 | Acquisition of right of way for freeway widening | 2026 | RARF | 2026 | 0 | 29419351 | 0 | 29419351
ADOT | Highway | 39931 | 202 (Santan): McClintock Dr - 48th St | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2026 | Maricopa | 5-year | 6 | 9 | 9 | Yes | No | No | No | No | No | No | Yes | DOT24-219C |  | 104496 | 202-C(212)T | F0743 | Convert HPS Lighting to LED Lighting (Const) | 2026 | Carbon-AZ | 2026 | 1838850 | 0 | 111150 | 1950000
ADOT | Highway | 42572 | 60 (Grand Ave): 35th Ave/Indian School Rd Intersection | Principal Arterial - Other | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 0 | 0 | 0 | Yes | No | No | No | Yes | No | No | Yes | DOT25-012 |  | 8893 | 060-B(227)T | F0272 | Construct intersection improvements | 2026 | RARF | 2026 | 0 | 73737875 | 5000000 | 78737875
ADOT | Highway | 31299 | 101 (Agua Fria): Northern Ave TI | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2028 | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT25-014 |  | 101559 | ----- | ----- | Construction for Interchange Improvements | 2026 | RARF | 2026 | 0 | 15000000 | 0 | 15000000
ADOT | Highway | 10216 | 101 (Pima): Princess Dr - Shea Blvd Capital Pavement Improvements | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2025 | Maricopa | FLCP | 4 | 8 | 10 | No | No | Yes | No | Yes | No | No | Yes | DOT25-038 |  | 7789 | ----- | F0770 | Construct freeway pavement surface | 2026 | RARF | 2026 | 0 | 25000000 | 0 | 25000000
ADOT | Highway | 15580 | 10 (Papago): SR 85 - Citrus Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 11.7 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT25-200 |  | 103441 | ----- | F0660 | Construction of HOV lanes | 2026 | RARF | 2026 | 0 | 9700000 | 3000000 | 12700000
ADOT | Highway | 56320 | 10 (Maricopa): Koli Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 1 | 0 | 4 | No | No | No | No | Yes | No | No | Yes | DOT25-253 |  | 7787 | ----- | ----- | Right of way acquisition for new interchange | 2026 | RARF | 2026 | 0 | 30445586 | 0 | 30445586
ADOT | Highway | 15426 | 10 (Papago): Jackrabbit Trail TI | Principal Arterial - Interstate | Freeway Interchange | OCT-DEC 2028 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT25-256P |  | 102988 | ----- | F0486 | Procurement for traffic interchange | 2026 | RARF | 2026 | 0 | 2000000 | 0 | 2000000
ADOT | Highway | 6186 | 24 (Williams Gateway): Meridian Rd - Ironwood Rd, Phase 2 | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2028 | Pinal | FLCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | DOT25-257 |  | 104374 |  | F0719 | Right of way and utilities for freeway widening | 2026 | NHPP | 2026 | 108445 | 6555 | 0 | 115000
ADOT | Highway | 21089 | 24 (Williams Gateway): SR 202L - Meridian Rd, Phase 2 | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2028 | Maricopa | FLCP | 3.1 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | DOT25-258 |  | 104373 |  | F0719 | Right of way and utilities for freeway mainline widening | 2026 | NHPP | 2026 | 363055 | 21945 | 0 | 385000
ADOT | Highway | 33219 | 10: Burnt Well Rest Area | Principal Arterial - Other | Freeway | OCT-DEC 2026 | Maricopa | 5-year | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT25-510C |  | 104935 | 010-A(242)T | F0779 | Truck Parking Expansion (Construction) | 2026 | NHFP | 2026 | 7245312 | 0 | 434688 | 7680000
ADOT | Highway | 33219 | 10: Burnt Well Rest Area | Principal Arterial - Other | Freeway | OCT-DEC 2026 | Maricopa | 5-year | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT25-510D2 |  | 104935 | 010-A(242)T | F0779 | Truck Parking Expansion (Design) | 2026 | NHFP | 2026 | 471700 | 0 | 28300 | 500000
ADOT | Highway | 33219 | 10: Burnt Well Rest Area | Principal Arterial - Other | Freeway | OCT-DEC 2026 | Maricopa | 5-year | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT25-510R |  | 104935 | 010-A(242)T | F0779 | Truck Parking Expansion (Right of Way) | 2026 | NHFP | 2026 | 290567 | 0 | 17433 | 308000
ADOT | Highway | 38280 | 10 (Papago): I-10 Tunnel to I-17 Split | Principal Arterial - Interstate | Freeway | OCT-DEC 2034 | Maricopa | 479-FLCP | 7 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT25-515D |  | 105493 | ----- | F0840 | Predesign of freeway corridor improvements | 2026 | RARF | 2026 | 0 | 8000000 | 0 | 8000000
ADOT | Highway | 14950 | MAG regionwide | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-010 |  | 101548 | ----- | ----- | Minor Improvements | 2026 | RARF | 2026 | 0 | 10000000 | 0 | 10000000
ADOT | Highway | 22227 | 10 (Maricopa): Knox Road Pedestrian Bridge | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-010D |  | 102456 |  | F0829 | Design pedestrian bridge | 2026 | NHPP | 2026 | 1232034 | 80193 | 0 | 1312227
ADOT | Highway | 3730 | MAG regionwide | Local | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-015 |  | 3662 | ----- | M5194 | R/W Property Management | 2026 | RARF | 2026 | 0 | 400000 | 0 | 400000
ADOT | Highway | 19798 | MAG regionwide | Local | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-018 |  | 3661 | ----- | M6972 | R/W Plans & Titles | 2026 | RARF | 2026 | 0 | 450000 | 0 | 450000
ADOT | Highway | 19798 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-0181 |  | 3661 | ----- | M6972 | R/W Plans & Titles | 2026 | RARF | 2026 | 0 | 450000 | 0 | 450000
ADOT | Highway | 30130 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-020 |  | 4272 | ----- | F0272 | Design Change Orders | 2026 | RARF | 2026 | 0 | 2250000 | 0 | 2250000
ADOT | Highway | 30130 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-0201 |  | 4272 | ----- | F0272 | Design Change Orders | 2026 | RARF | 2026 | 0 | 1250000 | 0 | 1250000
ADOT | Highway | 46386 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-022 |  | 4271 | ----- | M6987 | Preliminary Engineering (ADOT Staff) | 2026 | RARF | 2026 | 0 | 800000 | 0 | 800000
ADOT | Highway | 46386 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-0221 |  | 4271 | ----- | M6987 | Preliminary Engineering (ADOT Staff) | 2026 | RARF | 2026 | 0 | 800000 | 0 | 800000
ADOT | Highway | 46842 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-023 |  | 3663 | ----- | M7141 | Risk Management Indemnification | 2026 | RARF | 2026 | 0 | 2300000 | 0 | 2300000
ADOT | Highway | 49223 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-024 |  | 3659 | ----- | M6987 | Preliminary Engineering (Mgmt. Cons. 30% Plans) | 2026 | RARF | 2026 | 0 | 1200000 | 0 | 1200000
ADOT | Highway | 49223 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-0241 |  | 3659 | ----- | M6987 | Preliminary Engineering (Mgmt. Cons. 30% Plans) | 2026 | RARF | 2026 | 0 | 1200000 | 0 | 1200000
ADOT | Highway | 2827 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-025 |  | 3654 | ----- | F0496 | FMS Preservation | 2026 | State | 2026 | 0 | 0 | 720000 | 720000
ADOT | Highway | 16909 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-026 |  | 3655 | ----- | M7157 | Freeway Service Patrols | 2026 | State | 2026 | 0 | 0 | 1000000 | 1000000
ADOT | Highway | 30990 | MAG regionwide | Local | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-028 |  | 3660 | ----- | F0272 | R/W Advance Acquisition | 2026 | RARF | 2026 | 0 | 1000000 | 0 | 1000000
ADOT | Highway | 30990 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-0281 |  | 3660 | ----- | F0272 | R/W Advance Acquisition | 2026 | RARF | 2026 | 0 | 750000 | 0 | 750000
ADOT | Highway | 19989 | 202 (South Mountain): Litter, Landscape, Sweep | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | FLCP | 22 | 8 | 8 | No | No | No | No | Yes | No | No | Yes | DOT26-029 |  | 101911 | ----- | M8827 | Landscape, Litter, and Sweeping | 2026 | RARF | 2026 | 0 | 785000 | 0 | 785000
ADOT | Highway | 19989 | 202 (South Mountain): Litter, Landscape, Sweep | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | FLCP | 22 | 8 | 8 | No | No | No | No | Yes | No | No | Yes | DOT26-029X |  | 101911 | ----- | M8827 | P3 Maintenance | 2026 | RARF | 2026 | 0 | 3215146 | 0 | 3215146
ADOT | Highway | 20725 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-031 |  | 5697 | ----- | M5183 | Risk Analysis Process FY 2026 | 2026 | RARF | 2026 | 0 | 425000 | 0 | 425000
ADOT | Highway | 9967 | MAG regionwide | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-040 |  | 4243 | ----- | F0526 | Dynamic Message Signs (DMS), Travel Times | 2026 | State | 2026 | 0 | 0 | 170000 | 170000
ADOT | Highway | 24066 | SR 79: MP 140 - MP 148 | Principal Arterial - Other | Safety | OCT-DEC 2026 | Pinal | 5-year | 8 | 2 | 2 | Yes | No | No | No | No | No | No | No | DOT26-202 |  | 103644 | 079-A(214)T | F0707 | Construct passing lanes | 2026 | HSIP-AZ | 2026 | 7424596 | 0 | 448783 | 7873379
ADOT | Highway | 15426 | 10 (Papago): Jackrabbit Trail TI | Principal Arterial - Interstate | Freeway Interchange | OCT-DEC 2028 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-256R |  | 102988 | ----- | F0486 | Right of way and utilities for traffic interchange | 2026 | NHPP | 2026 | 19000000 | 23500000 | 0 | 42500000
ADOT | Highway | 42572 | 60 (Grand Ave): 35th Ave/Indian School Rd Intersection | Principal Arterial - Other | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 0 | 0 | 0 | Yes | No | No | No | Yes | No | No | Yes | DOT26-501C1 |  | 8893 | 060-B(227)T | F0272 | Construct intersection improvements | 2026 | MEGA | 2025 | 6369883 | 0 | 0 | 6369883
ADOT | Highway | 42572 | 60 (Grand Ave): 35th Ave/Indian School Rd Intersection | Principal Arterial - Other | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 0 | 0 | 0 | Yes | No | No | No | Yes | No | No | Yes | DOT26-501C2 |  | 8893 | 060-B(227)T | F0272 | Construct intersection improvements | 2026 | INFRA | 2025 | 133888089 | 0 | 0 | 133888089
ADOT | Highway | 42572 | 60 (Grand Ave): 35th Ave/Indian School Rd Intersection | Principal Arterial - Other | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 0 | 0 | 0 | Yes | No | No | No | Yes | No | No | Yes | DOT26-501C3 |  | 8893 | 060-B(227)T | F0272 | Construct intersection improvements | 2026 | MEGA | 2026 | 6369882 | 0 | 0 | 6369882
ADOT | Highway | 13489 | 10 (Maricopa): Gila River - Gas Line | Principal Arterial - Interstate | Freeway | JAN-MAR 2027 | Maricopa/Pinal | 5-year | 3.3 | 4 | 6 | Yes | No | Yes | Yes | Yes | Yes | No | Yes | DOT26-502C |  | 104187 | 010-C(222)T | F0734 | Construct freeway widening and crossroad | 2026 | Leg Approp | 2024 | 0 | 0 | 112555862 | 112555862
ADOT | Highway | 13489 | 10 (Maricopa): Gila River - Gas Line | Principal Arterial - Interstate | Freeway | JAN-MAR 2027 | Maricopa/Pinal | 5-year | 3.3 | 4 | 6 | Yes | No | Yes | Yes | Yes | Yes | No | Yes | DOT26-502C4 |  | 104187 | 010-C(222)T | F0734 | Construct freeway widening and crossroad | 2026 | NHPP | 2024 | 10083269 | 0 | 604954 | 10688223
ADOT | Highway | 3395 | I-10: L303 to L101, Ramp Meters | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | 5-year | 8 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-503D |  | 105020 | ----- | ----- | Design Ramp Meters | 2026 | NHPP | 2026 | 283020 | 0 | 16980 | 300000
ADOT | Highway | 40237 | 101 (Agua Fria): 59th Avenue Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JUL-SEP 2030 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-504D |  | 105494 | ----- | ----- | Design of interchange improvements | 2026 | 479 RARF FLCP | 2026 | 0 | 456374 | 0 | 456374
ADOT | Highway | 47970 | 101 (Agua Fria): 67th Ave Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | OCT-DEC 2033 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-505D |  | 104992 | ----- | ----- | Design of interchange improvements | 2026 | 479 RARF FLCP | 2026 | 0 | 985726 | 0 | 985726
ADOT | Highway | 22448 | 101 (Price): Frye Road Northbound Ramp | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | APR-JUN 2029 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-506D |  | 105483 | ----- | ----- | Design ramp improvements | 2026 | RARF | 2026 | 0 | 1137851 | 0 | 1137851
ADOT | Highway | 39473 | 202 (Santan): SR-101 to I-10 | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2029 | Maricopa | 479-FLCP | 4.5 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT26-507D |  | 101557 | ----- | F0847 | Design of freeway widening | 2026 | RARF | 2026 | 0 | 5626278 | 0 | 5626278
ADOT | Highway | 39473 | 202 (Santan): SR-101 to I-10 | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2029 | Maricopa | 479-FLCP | 4.5 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT26-507R |  | 101557 | ----- | F0847 | Right of way and utilities for freeway widening | 2026 | RARF | 2026 | 0 | 911472 | 0 | 911472
ADOT | Highway | 79116 | 30 (Tres Rios): 97th Ave - 71st Ave | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | 479-FLCP | 4.5 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-508R |  | 103174 | ----- | F0504 | Right of way and utilities for new freeway | 2026 | 479 RARF FLCP | 2026 | 0 | 8063256 | 0 | 8063256
ADOT | Highway | 34045 | 30 (Tres Rios): 71st Ave - SR202L South Mountain | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | 479-FLCP | 0.75 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-509R |  | 103175 | ----- | F0501 | Right of way and utilities for new freeway | 2026 | 479 RARF FLCP | 2026 | 0 | 17039333 | 0 | 17039333
ADOT | Highway | 94455 | 30 (Tres Rios): Dysart Rd - 97th Ave | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2031 | Maricopa | 479-FLCP | 4.1 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-510D |  | 104995 | ----- | F0862 | Design of new freeway | 2026 | HURF FLCP | 2026 | 0 | 30485177.65 | 0 | 30485177.65
ADOT | Highway | 94455 | 30 (Tres Rios): Dysart Rd - 97th Ave | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2031 | Maricopa | 479-FLCP | 4.1 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-510R |  | 104995 | ----- | F0862 | Right of way and utilities for new freeway | 2026 | 479 RARF FLCP | 2026 | 0 | 892851.48 | 0 | 892851.48
ADOT | Highway | 28516 | 347: Riggs Road Overpass | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | Other | 0.5 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-511C |  | 102768 | ----- | F0476 | Construct new overpass | 2026 | Leg Approp | 2026 | 0 | 0 | 41400000 | 41400000
ADOT | Highway | 7661 | 30 (Tres Rios): Estrella Pkwy - Dysart Rd | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2033 | Maricopa | 479-FLCP | 3.3 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-512D |  | 104984 | ----- | F0861 | Design new freeway | 2026 | NHPP | 2026 | 16352844 | 19678933 | 0 | 36031777
ADOT | Highway | 7661 | 30 (Tres Rios): Estrella Pkwy - Dysart Rd | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2033 | Maricopa | 479-FLCP | 3.3 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-512R |  | 104984 | ----- | F0861 | Right of way and utilities for new freeway | 2026 | RARF | 2026 | 0 | 7507414 | 0 | 7507414
ADOT | Highway | 1063 | 30 (Tres Rios): SR303L/SR30 System TI - Estrella Pkwy | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2035 | Maricopa | 479-FLCP | 8.8 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-513D |  | 104980 | ----- | F0860 | Design of new freeway | 2026 | NHPP | 2026 | 24479670 | 14869917 | 0 | 39349587
ADOT | Highway | 1063 | 30 (Tres Rios): SR303L/SR30 System TI - Estrella Pkwy | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2035 | Maricopa | 479-FLCP | 8.8 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-513R |  | 104980 | ----- | F0860 | Right of way and utilities for new freeway | 2026 | NHPP | 2026 | 68776045 | 19694011 | 0 | 88470056
ADOT | Highway | 11749 | 303 (Estrella): 155th Avenue Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JUL-SEP 2030 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-514D |  | 105479 | ----- | F0859 | Design interchange improvements | 2026 | RARF | 2026 | 0 | 3631528 | 0 | 3631528
ADOT | Highway | 11749 | 303 (Estrella): 155th Avenue Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JUL-SEP 2030 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-514D1 |  | 105479 | ----- | F0859 | Design interchange improvements | 2026 | Leg Approp | 2025 | 0 | 0 | 3500000 | 3500000
ADOT | Highway | 33075 | 60 (Superstition): Ellsworth Road to Meridian Road GPL | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2032 | Maricopa | 479-FLCP | 4 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT26-515D |  | 105490 | ----- | ----- | Predesign of freeway widening | 2026 | 479 RARF FLCP | 2026 | 0 | 2167300 | 0 | 2167300
ADOT | Highway | 49988 | 60 (Superstition): Ellsworth Road to Meridian Road HOV | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2041 | Maricopa | 479-FLCP | 4 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT26-516D |  | 105500 | ----- | ----- | Predesign of HOV lanes | 2026 | RARF | 2026 | 0 | 1333486 | 0 | 1333486
ADOT | Highway | 37881 | 51: I-10 to Shea Boulevard Pavement Rehab | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 9.4 | 10 | 10 | No | No | Yes | No | Yes | No | No | Yes | DOT26-517C |  | 105492 | ----- | F0858 | Pavement Capital Rehabilitation | 2026 | RARF | 2026 | 0 | 3757436 | 0 | 3757436
ADOT | Highway | 37881 | 51: I-10 to Shea Boulevard Pavement Rehab | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 9.4 | 10 | 10 | No | No | Yes | No | Yes | No | No | Yes | DOT26-517C1 |  | 105492 | ----- | F0858 | Pavement Capital Rehabilitation | 2026 | RARF | 2026 | 0 | 51967950 | 0 | 51967950
ADOT | Highway | 46658 | 101 (Agua Fria): 75th Ave - I-17 | Principal Arterial - Other Freeway or Expressway | Freeway | JAN-MAR 2027 | Maricopa | FLCP | 6 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT26-518C |  | 8894 | 101-A(214)T | F0316 | Construct freeway widening | 2026 | RARF | 2026 | 0 | 5500000 | 0 | 5500000
ADOT | Highway | 10389 | 30 (Tres Rios): SR303L - SR202L South Mountain, Phase 1 | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 13.8 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-519R |  | 8892 | ----- | H6876 | Right of way and utilities for new freeway | 2026 | NHPP | 2026 | 68402145 | 155597855 | 0 | 224000000
ADOT | Highway | 10389 | 30 (Tres Rios): SR303L - SR202L South Mountain, Phase 1 | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 13.8 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT26-519R1 |  | 8892 | ----- | H6876 | Right of way and utilities for new freeway | 2026 | NHPP | 2026 | 15000000 | 52020030 | 0 | 67020030
ADOT | Highway | 42572 | 60 (Grand Ave): 35th Ave/Indian School Rd Intersection | Principal Arterial - Other | Freeway | OCT-DEC 2029 | Maricopa | FLCP | 0 | 0 | 0 | Yes | No | No | No | Yes | No | No | Yes | DOT26-520R |  | 8893 | 060-B(227)T | F0272 | Right of way and utilities for intersection improvements | 2026 | RARF | 2026 | 0 | 23300136 | 0 | 23300136
ADOT | Highway | 24288 | 303 (Estrella): Grand Ave Ultimate Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JAN-MAR 2036 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-521R |  | 105485 | ----- | F0854 | Right of way and utilities for interchange improvements | 2026 | RARF | 2026 | 0 | 10000000 | 0 | 10000000
ADOT | Highway | 31696 | 347: Casa Blanca Road and Mammoth Way (Cement Plant Access) | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | Other | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-522C |  | 105086 | ----- | F0682 | Construct intersection improvements | 2026 | Leg Approp | 2026 | 0 | 0 | 10839000 | 10839000
ADOT | Highway | 31696 | 347: Casa Blanca Road and Mammoth Way (Cement Plant Access) | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | Other | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-522C2 |  | 105086 | ----- | F0682 | Construct intersection improvements | 2026 | Leg Approp | 2024 | 0 | 0 | 18000000 | 18000000
ADOT | Highway | 20133 | 347: I-10 to City of Maricopa | Principal Arterial - Other | Freeway | OCT-DEC 2027 | Pinal | 5-year | 13.4 | 4 | 6 | No | No | No | No | No | No | No | Yes | DOT26-522D |  | 103478 | 347-A(214)T | F0581 | Design road widening | 2026 | Leg Approp | 2025 | 0 | 0 | 1500000 | 1500000
ADOT | Highway | 15580 | 10 (Papago): SR 85 - Citrus Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 11.7 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT26-523C |  | 103441 |  | F0660 | Construction of HOV lanes | 2026 | Leg Approp | 2025 | 0 | 0 | 27000000 | 27000000
ADOT | Highway | 9470 | US 60/Grand Ave ITS |  | Freeway | OCT-DEC 2030 | Maricopa | 5-year | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-524D |  | 105024 | ----- | ----- | Design Intelligent Technology System | 2026 | NHPP | 2026 | 235750 | 0 | 14250 | 250000
ADOT | Highway | 30465 | Fiber Pull Box and Fiber Inventory |  | ITS | OCT-DEC 2026 | Maricopa | 5-year | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT26-560 |  | 104478 | 888-A(238)T | F0750 | Study to collect existing fiber optic infrastructure features | 2026 | STBGP-AZ | 2026 | 188600 | 0 | 11400 | 200000
ADOT | Highway | 17135 | MAG Regionwide |  | Street | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-582C |  | 104985 | ----- | ----- | Local roadway turnbacks | 2026 | RARF | 2026 | 0 | 2745960 | 0 | 2745960
ADOT | Highway | 28859 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-584C |  | 104986 | ----- | ----- | System supporting infrastructure | 2026 | RARF | 2026 | 0 | 10000000 | 0 | 10000000
ADOT | Highway | 19443 | MAG regionwide | Major Collector | Freeway | OCT-DEC 2032 | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-585 |  | 101891 | ----- | M6915 | Maintenance (Landscape, litter & sweep) | 2026 | RARF | 2026 | 0 | 7922686 | 0 | 7922686
ADOT | Highway | 19443 | MAG regionwide | Major Collector | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-5851 |  | 101891 | ----- | M6914 | Maintenance (Landscape, litter & sweep) | 2026 | RARF | 2026 | 0 | 7922686 | 0 | 7922686
ADOT | Highway | 39741 | 60 (Grand Ave): 85th Ave to I-17 | Principal Arterial - Other | Freeway | OCT-DEC 2027 | Maricopa | 5-year | 10.8 | 6 | 6 | No | No | Yes | No | No | No | No | Yes | DOT27-202 |  | 103682 | 060-B(230)T | F0675 | Construct pavement rehabilitation | 2026 | NHPP | 2026 | 30960361 | 0 | 1871412 | 32831773
ADOT | Highway | 9060 | I-10/I-17 Traffic Interchange West Connection | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2030 | Maricopa | 479-FLCP | 1.4 | 0 | 2 | No | No | No | No | Yes | Yes | No | Yes | DOT27-501D |  | 105478 | ----- | ----- | Design of ramp | 2026 | NHPP | 2026 | 1637855 | 1637855 | 0 | 3275710
ADOT | Highway | 9060 | I-10/I-17 Traffic Interchange West Connection | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2030 | Maricopa | 479-FLCP | 1.4 | 0 | 2 | No | No | No | No | Yes | Yes | No | Yes | DOT27-501R |  | 105478 | ----- | ----- | Right of way and utilities for ramp | 2026 | RARF | 2026 | 0 | 2567293 | 0 | 2567293
ADOT | Highway | 6186 | 24 (Williams Gateway): Meridian Rd - Ironwood Rd, Phase 2 | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2028 | Pinal | 479-FLCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | DOT28-515C1 |  | 104374 |  | F0719 | Construct interchange improvements at Ironwood Drive | 2026 | Leg Approp | 2023 | 0 | 0 | 59800000 | 59800000
ADOT | Highway | 15426 | 10 (Papago): Jackrabbit Trail TI | Principal Arterial - Interstate | Freeway Interchange | OCT-DEC 2028 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-505C |  | 102988 | ----- | F0486 | Construct traffic interchange improvements | 2026 | NHPP | 2026 | 39615093 | 41153773 | 0 | 80768866
ADOT | Highway | 6186 | 24 (Williams Gateway): Meridian Rd - Ironwood Rd, Phase 2 | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2028 | Pinal | 479-FLCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | DOT30-514C |  | 104374 |  | F0719 | Widen freeway and construct grade-separated interchanges | 2026 | NHPP | 2026 | 76277710 | 4610636 | 0 | 80888346
ADOT | Highway | 21089 | 24 (Williams Gateway): SR 202L - Meridian Rd, Phase 2 | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2028 | Maricopa | 479-FLCP | 3.1 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | DOT30-514C1 |  | 104373 | ----- | F0829 | Widen freeway and construct grade-separated interchanges | 2026 | NHPP | 2026 | 216640090 | 54160023 | 0 | 270800113
ADOT | Highway | 27723 | 303 (Estrella): Lake Pleasant Parkway - 51st Avenue | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2028 | Maricopa | 479-FLCP | 7 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | DOT30-515C |  | 103444 | ----- | F0561 | Freeway widening | 2026 | NHPP | 2026 | 51008760 | 20252190 | 0 | 71260950
ADOT | Highway | 15580 | 10 (Papago): SR 85 - Citrus Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 11.7 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT25-201 |  | 103441 | ----- | F0660 | Construction of HOV lanes | 2027 | Leg Approp | 2026 | 0 | 0 | 30000000 | 30000000
ADOT | Highway | 11749 | 303 (Estrella): 155th Avenue Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JUL-SEP 2030 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT26-514R |  | 105479 | ----- | F0859 | Right of way and utilities for interchange improvements | 2027 | 479 RARF FLCP | 2027 | 0 | 5070250 | 0 | 5070250
ADOT | Highway | 3730 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-015 |  | 3662 | ----- | M5194 | R/W Property Management | 2027 | 479 RARF FLCP | 2027 | 0 | 439354 | 0 | 439354
ADOT | Highway | 19798 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-018 |  | 3661 | ----- | M6972 | R/W Plans & Titles | 2027 | RARF | 2027 | 0 | 988545 | 0 | 988545
ADOT | Highway | 30130 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-020 |  | 4272 | ----- | F0272 | Design Change Orders | 2027 | RARF | 2027 | 0 | 2745959.56 | 0 | 2745959.56
ADOT | Highway | 46386 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-022 |  | 4271 | ----- | M6987 | Preliminary Engineering (ADOT Staff) | 2027 | RARF | 2027 | 0 | 1757414.12 | 0 | 1757414.12
ADOT | Highway | 46842 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-023 |  | 3663 | ----- | M7141 | Risk Management Indemnification | 2027 | RARF | 2027 | 0 | 2526283 | 0 | 2526283
ADOT | Highway | 49223 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-024 |  | 3659 | ----- | M6987 | Preliminary Engineering (Mgmt. Cons. 30% Plans) | 2027 | RARF | 2027 | 0 | 2636121.18 | 0 | 2636121.18
ADOT | Highway | 2827 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-025 |  | 3654 | ----- | F0496 | FMS Preservation | 2027 | HURF | 2027 | 0 | 0 | 720000 | 720000
ADOT | Highway | 16909 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-026 |  | 3655 | ----- | M7157 | Freeway Service Patrols | 2027 | HURF | 2027 | 0 | 0 | 1000000 | 1000000
ADOT | Highway | 30990 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-028 |  | 3660 | ----- | F0272 | R/W Advance Acquisition | 2027 | RARF | 2027 | 0 | 1647575.74 | 0 | 1647575.74
ADOT | Highway | 19989 | 202 (South Mountain): Litter, Landscape, Sweep | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 22 | 8 | 8 | No | No | No | No | Yes | No | No | Yes | DOT27-029 |  | 101911 | ----- | M8827 | Landscape, Litter, and Sweeping | 2027 | RARF | 2027 | 0 | 800818.24 | 0 | 800818.24
ADOT | Highway | 20725 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-031 |  | 5697 | ----- | M5183 | Risk Analysis Process FY 2027 | 2027 | RARF | 2027 | 0 | 82379 | 0 | 82379
ADOT | Highway | 9967 | MAG regionwide | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT27-040 |  | 4243 | ----- | F0526 | Dynamic Message Signs (DMS), Travel Times | 2027 | State | 2027 | 0 | 0 | 170000 | 170000
ADOT | Highway | 37270 | SR 347: N. of Lakeview Dr to I-10 | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2027 | Pinal | 5-year | 13.3 | 4 | 4 | No | No | Yes | No | No | No | No | Yes | DOT27-201 |  | 103680 | 347-S(215)T | F0673 | Construct pavement preservation | 2027 | STBGP-AZ | 2027 | 29347575 | 0 | 1773925 | 31121500
ADOT | Highway | 15580 | 10 (Papago): SR 85 - Citrus Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 11.7 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT27-203D |  | 103441 | ----- | F0660 | Design of HOV lanes | 2027 | Leg Approp | 2027 | 0 | 0 | 4802100 | 4802100
ADOT | Highway | 46032 | I-10/SR 202L/SR 51Mini Stack to SR 51 at Thomas Road | Principal Arterial - Interstate | Freeway Interchange | OCT-DEC 2031 | Maricopa | 479-FLCP | 8 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT27-502D |  | 105498 | ----- | ----- | Design of freeway corridor improvements | 2027 | RARF | 2027 | 0 | 21278441 | 0 | 21278441
ADOT | Highway | 17827 | 17: 19th Avenue to McDowell Road | Principal Arterial - Interstate | Freeway | JUL-SEP 2038 | Maricopa | 479-FLCP | 2.9 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT27-504D |  | 105481 | ----- | ----- | Predesign of freeway corridor improvements | 2027 | RARF | 2027 | 0 | 11760286 | 0 | 11760286
ADOT | Highway | 36077 | 17: I-10 Split - 19th Avenue | Principal Arterial - Interstate | Freeway | JUL-SEP 2039 | Maricopa | 479-FLCP | 3.5 | 6 | 8 | Yes | No | Yes | No | Yes | No | No | Yes | DOT27-505D |  | 8890 | ----- | H7563 | Predesign of freeway improvements | 2027 | 479 RARF FLCP | 2027 | 0 | 18267002 | 0 | 18267002
ADOT | Highway | 47419 | SR 101 (Pima): Pima Rd Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | APR-JUN 2033 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-506D |  | 104991 | ----- | ----- | Predesign of interchange improvements | 2027 | RARF | 2027 | 0 | 1648564 | 0 | 1648564
ADOT | Highway | 42362 | 74: Lake Pleasant Parkway Intersection | Principal Arterial - Other | Freeway Interchange | OCT-DEC 2033 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-507D |  | 105496 | ----- | ----- | Predesign of intersection improvements | 2027 | RARF | 2027 | 0 | 295905 | 0 | 295905
ADOT | Highway | 33075 | 60 (Superstition): Ellsworth Road to Meridian Road GPL | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2032 | Maricopa | 479-FLCP | 4 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT27-512D |  | 105490 | ----- | ----- | Design of freeway widening | 2027 | NHPP | 2027 | 2146626 | 2146626 | 0 | 4293252
ADOT | Highway | 33075 | 60 (Superstition): Ellsworth Road to Meridian Road GPL | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2032 | Maricopa | 479-FLCP | 4 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT27-512R |  | 105490 | ----- | ----- | Right of way and utilities for freeway widening | 2027 | 479 RARF FLCP | 2027 | 0 | 674847 | 0 | 674847
ADOT | Highway | 26171 | Loop 202 (Red Mountain Freeway): SR 51 to Priest Drive Pavement Rehab | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 5 | 10 | 10 | No | No | Yes | No | Yes | No | No | Yes | DOT27-513C |  | 105768 | ----- | ----- | Pavement Capital Rehabilitation | 2027 | RARF | 2027 | 0 | 23695819 | 0 | 23695819
ADOT | Highway | 22448 | 101 (Price): Frye Road Northbound Ramp | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | APR-JUN 2029 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-514C |  | 105483 | ----- | ----- | Construct ramp improvements | 2027 | 479 RARF FLCP | 2027 | 0 | 21906167 | 0 | 21906167
ADOT | Highway | 17135 | MAG Regionwide |  | Street | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-582C |  | 104985 | ----- | ----- | Local roadway turnbacks | 2027 | RARF | 2027 | 0 | 5491919 | 0 | 5491919
ADOT | Highway | 7092 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-583C |  | 104983 | ----- | ----- | Minor Improvements | 2027 | RARF | 2027 | 0 | 10983838 | 0 | 10983838
ADOT | Highway | 28859 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-584C |  | 104986 | ----- | ----- | System supporting infrastructure | 2027 | RARF | 2027 | 0 | 21967677 | 0 | 21967677
ADOT | Highway | 19443 | MAG regionwide | Major Collector | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-585 |  | 101891 | ----- | M6914 | Maintenance (Landscape, litter & sweep) | 2027 | RARF | 2027 | 0 | 18420899 | 0 | 18420899
ADOT | Highway | 39473 | 202 (Santan): SR-101 to I-10 | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2029 | Maricopa | 479-FLCP | 4.5 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT30-501C |  | 101557 | ----- | F0847 | Construction of general purpose lanes | 2027 | RARF | 2027 | 0 | 112309526 | 0 | 112309526
ADOT | Highway | 93281 | 30 (Tres Rios): SR85 - SR303L | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2050 | Maricopa | 479-FLCP | 12.4 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT30-503 |  | 104994 | ----- | ----- | Predesign of new freeway | 2027 | RARF | 2027 | 0 | 27459596 | 0 | 27459596
ADOT | Highway | 79116 | 30 (Tres Rios): 97th Ave - 71st Ave | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | 479-FLCP | 4.5 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT30-510C |  | 103174 | ----- | F0504 | Construct new freeway | 2027 | NHPP | 2027 | 192750000 | 211202953 | 0 | 403952953
ADOT | Highway | 34045 | 30 (Tres Rios): 71st Ave - SR202L South Mountain | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | 479-FLCP | 0.75 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT30-510C1 |  | 103175 | ----- | F0501 | Construct new freeway | 2027 | NHPP | 2027 | 297853374 | 560546652 | 0 | 858400026
ADOT | Highway | 1709 | 101 (Pima): Pima Rd Extension (JPA) | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2028 | Maricopa | FLCP | 3 | 4 | 4 | No | No | No | No | Yes | No | No | Yes | DOT98-111 |  | 81198 | ----- | H3875 | Design roadway improvements | 2027 | RARF | 2027 | 0 | 297000 | 0 | 297000
ADOT | Highway | 39146 | 85: Broadway Road and Baseline Road | Principal Arterial - Other | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 2 | 4 | 4 | No | No | No | No | Yes | No | No | Yes | DOT11-105 |  | 44811 | ----- | H8006 | Construct interchange improvements | 2028 | RARF | 2028 | 0 | 25300000 | 0 | 25300000
ADOT | Highway | 28516 | 347: Riggs Road Overpass | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | Other | 0.5 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT22-011C |  | 102768 | ----- | F0476 | Construct new overpass | 2028 | Leg Approp | 2028 | 0 | 0 | 25000000 | 25000000
ADOT | Highway | 28516 | 347: Riggs Road Overpass | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2030 | Maricopa | Other | 0.5 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT22-011C1 |  | 102768 | ----- | F0476 | Construct new overpass | 2028 | Leg Approp | 2028 | 0 | 0 | 24000000 | 24000000
ADOT | Highway | 13143 | 8: Paloma Rd to Jct SR-85 | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2029 | Maricopa | 5-year | 12.11 | 4 | 4 | No | No | Yes | No | No | No | No | Yes | DOT25-519C |  | 105119 | ----- | F0837 | Design pavement rehabilitation | 2028 | NHPP | 2028 | 36518957 | 0 | 2190983 | 38709940
ADOT | Highway | 22227 | 10 (Maricopa): Knox Road Pedestrian Bridge | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT27-010C |  | 102456 |  | F0829 | Construct pedestrian bridge | 2028 | NHPP | 2028 | 12899721 | 925262 | 0 | 13824983
ADOT | Highway | 3730 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-015 |  | 3662 | ----- | M5194 | R/W Property Management | 2028 | 479 RARF FLCP | 2028 | 0 | 452534 | 0 | 452534
ADOT | Highway | 19798 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-018 |  | 3661 | ----- | M6972 | R/W Plans & Titles | 2028 | RARF | 2028 | 0 | 1018202 | 0 | 1018202
ADOT | Highway | 30130 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-020 |  | 4272 | ----- | F0272 | Design Change Orders | 2028 | RARF | 2028 | 0 | 2828338.35 | 0 | 2828338.35
ADOT | Highway | 46386 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-022 |  | 4271 | ----- | M6987 | Preliminary Engineering (ADOT Staff) | 2028 | RARF | 2028 | 0 | 1810136.54 | 0 | 1810136.54
ADOT | Highway | 46842 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-023 |  | 3663 | ----- | M7141 | Risk Management Indemnification | 2028 | RARF | 2028 | 0 | 2602071 | 0 | 2602071
ADOT | Highway | 49223 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-024 |  | 3659 | ----- | M6987 | Preliminary Engineering (Mgmt. Cons. 30% Plans) | 2028 | RARF | 2028 | 0 | 2715204.82 | 0 | 2715204.82
ADOT | Highway | 2827 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-025 |  | 3654 | ----- | F0496 | FMS Preservation | 2028 | HURF | 2028 | 0 | 0 | 720000 | 720000
ADOT | Highway | 16909 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-026 |  | 3655 | ----- | M7157 | Freeway Service Patrols | 2028 | HURF | 2028 | 0 | 0 | 1000000 | 1000000
ADOT | Highway | 30990 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-028 |  | 3660 | ----- | F0272 | R/W Advance Acquisition | 2028 | RARF | 2028 | 0 | 1697003.01 | 0 | 1697003.01
ADOT | Highway | 19989 | 202 (South Mountain): Litter, Landscape, Sweep | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 22 | 8 | 8 | No | No | No | No | Yes | No | No | Yes | DOT28-029 |  | 101911 | ----- | M8827 | Landscape, Litter, and Sweeping | 2028 | RARF | 2028 | 0 | 816834.6 | 0 | 816834.6
ADOT | Highway | 20725 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-031 |  | 5697 | ----- | M5183 | Risk Analysis Process FY 2028 | 2028 | RARF | 2028 | 0 | 84850 | 0 | 84850
ADOT | Highway | 9967 | MAG regionwide | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT28-040 |  | 4243 | ----- | F0526 | Dynamic Message Signs (DMS), Travel Times | 2028 | State | 2028 | 0 | 0 | 170000 | 170000
ADOT | Highway | 15580 | 10 (Papago): SR 85 - Citrus Rd | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | FLCP | 11.7 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT28-201C |  | 103441 | ----- | F0660 | Construction of HOV lanes | 2028 | Leg Approp | 2027 | 0 | 0 | 76000000 | 76000000
ADOT | Highway | 9060 | I-10/I-17 Traffic Interchange West Connection | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2030 | Maricopa | 479-FLCP | 1.4 | 0 | 2 | No | No | No | No | Yes | Yes | No | Yes | DOT28-501C |  | 105478 | ----- | ----- | Construction of ramp | 2028 | NHPP | 2028 | 64162019 | 3878298 | 0 | 68040317
ADOT | Highway | 38280 | 10 (Papago): I-10 Tunnel to I-17 Split | Principal Arterial - Interstate | Freeway | OCT-DEC 2034 | Maricopa | 479-FLCP | 7 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT28-502D |  | 105493 | ----- | F0840 | Design of freeway corridor improvements | 2028 | RARF | 2028 | 0 | 15225964 | 0 | 15225964
ADOT | Highway | 12898 | 101 (Agua Fria): I-10 to US 60 (Grand Avenue) | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2034 | Maricopa | 479-FLCP | 10 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT28-503D |  | 105480 | ----- | ----- | Predesign of freeway widening | 2028 | RARF | 2028 | 0 | 8439649 | 0 | 8439649
ADOT | Highway | 45442 | 101 (Agua Fria): US-60 Grand Ave - 75th Ave | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2042 | Maricopa | 479-FLCP | 5 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT28-504D |  | 101558 | ----- | ----- | Predesign of freeway widening | 2028 | 479 RARF FLCP | 2028 | 0 | 4909543 | 0 | 4909543
ADOT | Highway | 47419 | SR 101 (Pima): Pima Rd Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | APR-JUN 2033 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-505D |  | 104991 | ----- | ----- | Design of interchange improvements | 2028 | RARF | 2028 | 0 | 3396156 | 0 | 3396156
ADOT | Highway | 24288 | 303 (Estrella): Grand Ave Ultimate Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JAN-MAR 2036 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-509D |  | 105485 | ----- | F0854 | Predesign interchange improvements | 2028 | RARF | 2028 | 0 | 5641743 | 0 | 5641743
ADOT | Highway | 31402 | 347: I-10 to Riggs Road | Principal Arterial - Other | Freeway | JAN-MAR 2033 | Maricopa | 479-FLCP | 4 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | DOT28-510R |  | 105487 | ----- | ----- | Right of way and utilities for roadway widening | 2028 | RARF | 2028 | 0 | 1489845 | 0 | 1489845
ADOT | Highway | 29620 | 60 (Grand Ave): 51st Avenue/Bethany Home Road | Principal Arterial - Other | Freeway Interchange | JAN-MAR 2037 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-512D |  | 105486 | ----- | ----- | Predesign of interchange improvements | 2028 | RARF | 2028 | 0 | 2148180 | 0 | 2148180
ADOT | Highway | 34574 | 60 (Grand Ave): I-17 DHOV | Principal Arterial - Other | Freeway Interchange | JAN-MAR 2049 | Maricopa | 479-FLCP | 1 | 0 | 2 | No | No | No | No | Yes | No | No | Yes | DOT28-513D |  | 105491 | ----- | ----- | Predesign of interchange improvements | 2028 | RARF | 2028 | 0 | 3094315 | 0 | 3094315
ADOT | Highway | 4597 | 60 (Grand Ave): 303 to I-10 Corridor Optimization | Principal Arterial - Other | Freeway | OCT-DEC 2039 | Maricopa | 479-FLCP | 33 | 6 | 6 | No | No | No | No | Yes | No | No | Yes | DOT28-514D |  | 105477 | ----- | ----- | Predesign of corridor improvements | 2028 | RARF | 2028 | 0 | 6148694 | 0 | 6148694
ADOT | Highway | 11749 | 303 (Estrella): 155th Avenue Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JUL-SEP 2030 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-515C |  | 105479 | ----- | F0859 | Construct interchange improvements | 2028 | 479 RARF FLCP | 2028 | 0 | 89997047 | 0 | 89997047
ADOT | Highway | 17135 | MAG Regionwide |  | Street | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-582C |  | 104985 | ----- | ----- | Local roadway turnbacks | 2028 | RARF | 2028 | 0 | 5656677 | 0 | 5656677
ADOT | Highway | 7092 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-583C |  | 104983 | ----- | ----- | Minor Improvements | 2028 | RARF | 2028 | 0 | 11313353 | 0 | 11313353
ADOT | Highway | 28859 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-584C |  | 104986 | ----- | ----- | System supporting infrastructure | 2028 | RARF | 2028 | 0 | 22626707 | 0 | 22626707
ADOT | Highway | 19443 | MAG regionwide | Major Collector | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-585 |  | 101891 | ----- | M6914 | Maintenance (Landscape, litter & sweep) | 2028 | RARF | 2028 | 0 | 18981534 | 0 | 18981534
ADOT | Highway | 40237 | 101 (Agua Fria): 59th Avenue Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JUL-SEP 2030 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-533C |  | 105494 | ----- | ----- | Construct interchange improvements | 2028 | 479 RARF FLCP | 2028 | 0 | 10030306 | 0 | 10030306
ADOT | Highway | 1709 | 101 (Pima): Pima Rd Extension (JPA) | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2028 | Maricopa | FLCP | 3 | 4 | 4 | No | No | No | No | Yes | No | No | Yes | DOT99-124 |  | 81198 | ----- | H3875 | Construct roadway extension | 2028 | RARF | 2028 | 0 | 3634000 | 0 | 3634000
ADOT | Highway | 42362 | 74: Lake Pleasant Parkway Intersection | Principal Arterial - Other | Freeway Interchange | OCT-DEC 2033 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT28-511D |  | 105496 | ----- | ----- | Design of intersection improvements | 2029 | RARF | 2029 | 0 | 617412 | 0 | 617412
ADOT | Highway | 3730 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-015 |  | 3662 | ----- | M5194 | R/W Property Management | 2029 | 479 RARF FLCP | 2029 | 0 | 458191 | 0 | 458191
ADOT | Highway | 19798 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-018 |  | 3661 | ----- | M6972 | R/W Plans & Titles | 2029 | RARF | 2029 | 0 | 1030929 | 0 | 1030929
ADOT | Highway | 30130 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-020 |  | 4272 | ----- | F0272 | Design Change Orders | 2029 | RARF | 2029 | 0 | 2863692.58 | 0 | 2863692.58
ADOT | Highway | 46386 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-022 |  | 4271 | ----- | M6987 | Preliminary Engineering (ADOT Staff) | 2029 | RARF | 2029 | 0 | 1832763.25 | 0 | 1832763.25
ADOT | Highway | 46842 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-023 |  | 3663 | ----- | M7141 | Risk Management Indemnification | 2029 | RARF | 2029 | 0 | 2634597 | 0 | 2634597
ADOT | Highway | 49223 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-024 |  | 3659 | ----- | M6987 | Preliminary Engineering (Mgmt. Cons. 30% Plans) | 2029 | RARF | 2029 | 0 | 2749144.88 | 0 | 2749144.88
ADOT | Highway | 2827 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-025 |  | 3654 | ----- | F0496 | FMS Preservation | 2029 | HURF | 2029 | 0 | 0 | 720000 | 720000
ADOT | Highway | 16909 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-026 |  | 3655 | ----- | M7157 | Freeway Service Patrols | 2029 | HURF | 2029 | 0 | 0 | 1000000 | 1000000
ADOT | Highway | 30990 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-028 |  | 3660 | ----- | F0272 | R/W Advance Acquisition | 2029 | RARF | 2029 | 0 | 1718215.55 | 0 | 1718215.55
ADOT | Highway | 19989 | 202 (South Mountain): Litter, Landscape, Sweep | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 22 | 8 | 8 | No | No | No | No | Yes | No | No | Yes | DOT29-029 |  | 101911 | ----- | M8827 | Landscape, Litter, and Sweeping | 2029 | RARF | 2029 | 0 | 833171.3 | 0 | 833171.3
ADOT | Highway | 19989 | 202 (South Mountain): Litter, Landscape, Sweep | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 22 | 8 | 8 | No | No | No | No | Yes | No | No | Yes | DOT29-029X |  | 101911 | ----- | M8827 | P3 Maintenance | 2029 | RARF | 2029 | 0 | 26353379 | 0 | 26353379
ADOT | Highway | 20725 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-031 |  | 5697 | ----- | M5183 | Risk Analysis Process FY 2029 | 2029 | RARF | 2029 | 0 | 85911 | 0 | 85911
ADOT | Highway | 9967 | MAG regionwide | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT29-040 |  | 4243 | ----- | F0526 | Dynamic Message Signs (DMS), Travel Times | 2029 | State | 2029 | 0 | 0 | 170000 | 170000
ADOT | Highway | 12785 | 8: Gillespie Canal Bridge EB #489 & WB #568 | Principal Arterial - Interstate | Bridge | OCT-DEC 2029 | Maricopa | 5-year | 0 | 0 | 0 | No | No | No | Yes | No | No | No | Yes | DOT29-220 |  | 104378 | ----- | ----- | Bridge replacement (Construction) | 2029 | Bridge | 2029 | 18868000 | 0 | 1132000 | 20000000
ADOT | Highway | 9470 | US 60/Grand Ave ITS |  | Freeway | OCT-DEC 2030 | Maricopa | 5-year | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-500C |  | 105024 | ----- | ----- | Construct Intelligent Technology System | 2029 | NHPP | 2029 | 1697400 | 0 | 102600 | 1800000
ADOT | Highway | 3395 | I-10: L303 to L101, Ramp Meters | Principal Arterial - Interstate | Freeway | OCT-DEC 2030 | Maricopa | 5-year | 8 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-503C |  | 105020 | ----- | ----- | Construct Ramp Meters | 2029 | NHPP | 2029 | 1981140 | 0 | 118860 | 2100000
ADOT | Highway | 17135 | MAG Regionwide |  | Street | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-582C |  | 104985 | ----- | ----- | Local roadway turnbacks | 2029 | RARF | 2029 | 0 | 5727385 | 0 | 5727385
ADOT | Highway | 7092 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-583C |  | 104983 | ----- | ----- | Minor Improvements | 2029 | RARF | 2029 | 0 | 11454770 | 0 | 11454770
ADOT | Highway | 28859 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-584C |  | 104986 | ----- | ----- | System supporting infrastructure | 2029 | RARF | 2029 | 0 | 22909541 | 0 | 22909541
ADOT | Highway | 19443 | MAG regionwide | Major Collector | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT29-585 |  | 101891 | ----- | M6914 | Maintenance (Landscape, litter & sweep) | 2029 | RARF | 2029 | 0 | 19212677 | 0 | 19212677
ADOT | Highway | 94455 | 30 (Tres Rios): Dysart Rd - 97th Ave | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2031 | Maricopa | 479-FLCP | 4.1 | 0 | 6 | No | No | No | No | Yes | No | No | Yes | DOT30-509C |  | 104995 | ----- | F0862 | Construct new freeway | 2029 | NHPP | 2029 | 455422484 | 179202834 | 0 | 634625318
ADOT | Highway | 36077 | 17: I-10 Split - 19th Avenue | Principal Arterial - Interstate | Freeway | JUL-SEP 2039 | Maricopa | 479-FLCP | 3.5 | 6 | 8 | Yes | No | Yes | No | Yes | No | No | Yes | DOT22-802 |  | 8890 | ----- | H7563 | Right of way for freeway improvements | 2030 | NHPP | 2030 | 92235010 | 23058752 | 0 | 115293762
ADOT | Highway | 3730 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-015 |  | 3662 | ----- | M5194 | R/W Property Management | 2030 | 479 RARF FLCP | 2030 | 0 | 463918 | 0 | 463918
ADOT | Highway | 19798 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-018 |  | 3661 | ----- | M6972 | R/W Plans & Titles | 2030 | RARF | 2030 | 0 | 1043816 | 0 | 1043816
ADOT | Highway | 30130 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-020 |  | 4272 | ----- | F0272 | Design Change Orders | 2030 | RARF | 2030 | 0 | 2899488.74 | 0 | 2899488.74
ADOT | Highway | 46386 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-022 |  | 4271 | ----- | M6987 | Preliminary Engineering (ADOT Staff) | 2030 | RARF | 2030 | 0 | 1855672.79 | 0 | 1855672.79
ADOT | Highway | 46842 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-023 |  | 3663 | ----- | M7141 | Risk Management Indemnification | 2030 | RARF | 2030 | 0 | 2667530 | 0 | 2667530
ADOT | Highway | 49223 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-024 |  | 3659 | ----- | M6987 | Preliminary Engineering (Mgmt. Cons. 30% Plans) | 2030 | RARF | 2030 | 0 | 2783509.19 | 0 | 2783509.19
ADOT | Highway | 2827 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-025 |  | 3654 | ----- | F0496 | FMS Preservation | 2030 | HURF | 2030 | 0 | 0 | 720000 | 720000
ADOT | Highway | 16909 | I-10, I-17, SR-51, US-60, SR-101L, SR-202L, SR-303L | Principal Arterial - Other Freeway or Expressway | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-026 |  | 3655 | ----- | M7157 | Freeway Service Patrols | 2030 | HURF | 2030 | 0 | 0 | 1000000 | 1000000
ADOT | Highway | 30990 | MAG regionwide | Local | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-028 |  | 3660 | ----- | F0272 | R/W Advance Acquisition | 2030 | RARF | 2030 | 0 | 1739693.24 | 0 | 1739693.24
ADOT | Highway | 19989 | 202 (South Mountain): Litter, Landscape, Sweep | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 22 | 8 | 8 | No | No | No | No | Yes | No | No | Yes | DOT30-029 |  | 101911 | ----- | M8827 | Landscape, Litter, and Sweeping | 2030 | RARF | 2030 | 0 | 849834.72 | 0 | 849834.72
ADOT | Highway | 20725 | MAG regionwide | Principal Arterial - Other Freeway or Expressway | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-031 |  | 5697 | ----- | M5183 | Risk Analysis Process FY 2030 | 2030 | RARF | 2030 | 0 | 86985 | 0 | 86985
ADOT | Highway | 9967 | MAG regionwide | Principal Arterial - Interstate | Freeway | N/A | Maricopa | FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | DOT30-040 |  | 4243 | ----- | F0526 | Dynamic Message Signs (DMS), Travel Times | 2030 | State | 2030 | 0 | 0 | 170000 | 170000
ADOT | Highway | 47419 | SR 101 (Pima): Pima Rd Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | APR-JUN 2033 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-512C |  | 104991 | ----- | ----- | Construct interchange improvements | 2030 | RARF | 2030 | 0 | 70210076 | 0 | 70210076
ADOT | Highway | 46041 | 10 (Papago): 27th Avenue Interchange | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2039 | Maricopa | 479-FLCP | 0.4 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-520D |  | 105499 | ----- | ----- | Predesign of interchange improvements | 2030 | RARF | 2030 | 0 | 440490 | 0 | 440490
ADOT | Highway | 42541 | 10 (Papago): 35th Avenue Interchange | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2039 | Maricopa | 479-FLCP | 0.35 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-521D |  | 105497 | ----- | ----- | Predesign of interchange improvements | 2030 | RARF | 2030 | 0 | 706431 | 0 | 706431
ADOT | Highway | 32820 | 10 (Papago): 43rd Avenue Interchange | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2039 | Maricopa | 479-FLCP | 0.3 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-522D |  | 105489 | ----- | ----- | Predesign of interchange improvements | 2030 | RARF | 2030 | 0 | 847231 | 0 | 847231
ADOT | Highway | 377 | 10 (Papago): 51st Avenue Interchange | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2039 | Maricopa | 479-FLCP | 0.3 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-523D |  | 105476 | ----- | ----- | Predesign of interchange improvements | 2030 | RARF | 2030 | 0 | 867295 | 0 | 867295
ADOT | Highway | 31786 | 10 (Papago): 67th Avenue Interchange | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2039 | Maricopa | 479-FLCP | 0.3 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-524D |  | 105488 | ----- | ----- | Predesign of interchange improvements | 2030 | RARF | 2030 | 0 | 630813 | 0 | 630813
ADOT | Highway | 40662 | 10 (Papago): 75th Avenue Interchange | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2039 | Maricopa | 479-FLCP | 0.4 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-525D |  | 105495 | ----- | ----- | Predesign of interchange improvements | 2030 | RARF | 2030 | 0 | 776135 | 0 | 776135
ADOT | Highway | 22839 | 10 (Papago): 99th Avenue Interchange | Principal Arterial - Interstate | Freeway Interchange | JAN-MAR 2039 | Maricopa | 479-FLCP | 0.2 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-526D |  | 105484 | ----- | ----- | Predesign of interchange improvements | 2030 | RARF | 2030 | 0 | 290297 | 0 | 290297
ADOT | Highway | 64461 | 10 (Papago): SR101L - I-17 | Principal Arterial - Interstate | Freeway | JAN-MAR 2039 | Maricopa | 479-FLCP | 9 | 10 | 12 | No | No | No | No | Yes | No | No | Yes | DOT30-527D |  | 104993 | ----- | ----- | Predesign of freeway widening | 2030 | RARF | 2030 | 0 | 3001319 | 0 | 3001319
ADOT | Highway | 17827 | 17: 19th Avenue to McDowell Road | Principal Arterial - Interstate | Freeway | JUL-SEP 2038 | Maricopa | 479-FLCP | 2.9 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT30-528D |  | 105481 | ----- | ----- | Design of freeway corridor improvements | 2030 | NHPP | 2030 | 19868410 | 4967103 | 0 | 24835513
ADOT | Highway | 17827 | 17: 19th Avenue to McDowell Road | Principal Arterial - Interstate | Freeway | JUL-SEP 2038 | Maricopa | 479-FLCP | 2.9 | 6 | 8 | No | No | No | No | Yes | No | No | Yes | DOT30-528R |  | 105481 | ----- | ----- | Right of way and utilities for freeway corridor improvements | 2030 | NHPP | 2030 | 184503700 | 46125925 | 0 | 230629625
ADOT | Highway | 36077 | 17: I-10 Split - 19th Avenue | Principal Arterial - Interstate | Freeway | JUL-SEP 2039 | Maricopa | 479-FLCP | 3.5 | 6 | 8 | Yes | No | Yes | No | Yes | No | No | Yes | DOT30-529D |  | 8890 | ----- | H7563 | Design of freeway improvements | 2030 | NHPP | 2030 | 30861323 | 7715331 | 0 | 38576654
ADOT | Highway | 12898 | 101 (Agua Fria): I-10 to US 60 (Grand Avenue) | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2034 | Maricopa | 479-FLCP | 10 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT30-530D |  | 105480 | ----- | ----- | Design of freeway widening | 2030 | RARF | 2030 | 0 | 17303801 | 0 | 17303801
ADOT | Highway | 12898 | 101 (Agua Fria): I-10 to US 60 (Grand Avenue) | Principal Arterial - Other Freeway or Expressway | Freeway | JUL-SEP 2034 | Maricopa | 479-FLCP | 10 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT30-530R |  | 105480 | ----- | ----- | Right of way and utilities for freeway widening | 2030 | RARF | 2030 | 0 | 731831 | 0 | 731831
ADOT | Highway | 20169 | 101 (Price): SR 202 to US 60 Superstition Bottleneck Improvements | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | APR-JUN 2036 | Maricopa | 479-FLCP | 4.4 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-531D |  | 105482 | ----- | ----- | Predesign of corridor improvements | 2030 | RARF | 2030 | 0 | 18312591 | 0 | 18312591
ADOT | Highway | 24288 | 303 (Estrella): Grand Ave Ultimate Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JAN-MAR 2036 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-532D |  | 105485 | ----- | F0854 | Design interchange improvements | 2030 | NHPP | 2030 | 9099755 | 2274939 | 0 | 11374694
ADOT | Highway | 24288 | 303 (Estrella): Grand Ave Ultimate Interchange | Principal Arterial - Other Freeway or Expressway | Freeway Interchange | JAN-MAR 2036 | Maricopa | 479-FLCP | 1 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-532R |  | 105485 | ----- | F0854 | Right of way and utilities for interchange improvements | 2030 | NHPP | 2030 | 23983182 | 5995795 | 0 | 29978977
ADOT | Highway | 33075 | 60 (Superstition): Ellsworth Road to Meridian Road GPL | Principal Arterial - Other Freeway or Expressway | Freeway | APR-JUN 2032 | Maricopa | 479-FLCP | 4 | 8 | 10 | No | No | No | No | Yes | No | No | Yes | DOT30-534C |  | 105490 | ----- | ----- | Construct freeway widening | 2030 | NHPP | 2030 | 62114555 | 25528639 | 0 | 87643194
ADOT | Highway | 31986 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | Yes | No | Yes | No | No | Yes | DOT30-581C |  | 104987 | ----- | ----- | Capital rehabilitation for regional freeways | 2030 | RARF | 2030 | 0 | 51492020 | 0 | 51492020
ADOT | Highway | 17135 | MAG Regionwide |  | Street | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-582C |  | 104985 | ----- | ----- | Local roadway turnbacks | 2030 | RARF | 2030 | 0 | 5798977 | 0 | 5798977
ADOT | Highway | 7092 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-583C |  | 104983 | ----- | ----- | Minor Improvements | 2030 | RARF | 2030 | 0 | 11597955 | 0 | 11597955
ADOT | Highway | 28859 | MAG Regionwide |  | Freeway | N/A | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-584C |  | 104986 | ----- | ----- | System supporting infrastructure | 2030 | RARF | 2030 | 0 | 23195910 | 0 | 23195910
ADOT | Highway | 19443 | MAG regionwide | Major Collector | Freeway | OCT-DEC 2032 | Maricopa | 479-FLCP | 0 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | DOT30-585 |  | 101891 | ----- | M6914 | Maintenance (Landscape, litter & sweep) | 2030 | RARF | 2030 | 0 | 19446586 | 0 | 19446586
Apache Junction | Highway | 43674 | Tomahawk Road: US60 to Southern Avenue | Minor Arterial | Street | OCT-DEC 2026 | Pinal | Other | 0.7 | 2 | 4 | No | No | No | No | Yes | No | No | No | APJ25-220C |  | 103061 | APJ-0(222)T | T0411 | Construct Expansion Capacity of Roadway | 2026 | STBGP >200 PHX-MESA | 2026 | 1413667 | 0 | 664459 | 2078126
Apache Junction | Highway | 3685 | Tomahawk Road: Southern Avenue to Old West Highway | Minor Arterial | Street | OCT-DEC 2028 | Pinal | Other | 0.65 | 2 | 3 | No | No | No | No | Yes | No | No | No | APJ27-530C |  | 105747 | ----- | ----- | Construct Expansion Capacity of Roadway | 2027 | Local | 2027 | 0 | 0 | 4250000 | 4250000
Avondale | Highway | 45845 | 99th Ave: Osborn Rd to Thomas (W 1/2) (0.5 miles) | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | AVN10-813 |  | 105104 | ----- | ----- | Add 1 SB & 1NB | 2026 | Private | 2026 | 0 | 0 | 2000000 | 2000000
Avondale | Highway | 29304 | Van Buren: 111th Avenue to 107th Avenue | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.5 | 2 | 6 | No | No | No | No | Yes | No | No | No | AVN15-408 |  | 105084 | ----- | ----- | Construct roadway widening and improvements | 2026 | Local | 2026 | 0 | 0 | 2000000 | 2000000
Avondale | Highway | 28760 | McDowell Road: 117th Avenue to Avondale Blvd | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.3 | 4 | 5 | No | No | No | No | Yes | No | No | No | AVN16-404 |  | 100856 | ----- | ----- | Add 1 EB Lane Construct roadway widening and improvements | 2026 | Private | 2026 | 0 | 0 | 2000000 | 2000000
Avondale | Highway | 19545 | Van Buren: .25 mi east of Avondale to 111th Avenue ( S 1/2, .25 mi) | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.25 | 2 | 6 | No | No | No | No | Yes | No | No | No | AVN16-413 |  | 105072 | ----- | ----- | Add 4 lanes, curb, gutter, sidewalks | 2026 | Private | 2026 | 0 | 0 | 2000000 | 2000000
Avondale | Highway | 44693 | El Mirage: Camelback to Indian School Road | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN20-703 |  | 100861 | ----- | ----- | Construct roadway widening | 2026 | Private | 2026 | 0 | 0 | 1000000 | 1000000
Avondale | Highway | 23477 | Dysart Road: Whyman to Lower Buckeye | Local | Street | OCT-DEC 2026 | Maricopa | Other | 0.5 | 0 | 4 | No | No | No | No | Yes | No | No | No | AVN21-701 |  | 100854 | ----- | ----- | Construct new roadway | 2026 | Private | 2026 | 0 | 0 | 6000000 | 6000000
Avondale | Highway | 19282 | Dysart Road: WOLF to Buckeye Canal ( W 1/2, .25 miles) | Major Collector | Street | OCT-DEC 2026 | Maricopa | Other | 0.25 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN26-230 |  | 105071 | ----- | ----- | Add through lanes | 2026 | Private | 2026 | 0 | 0 | 1000000 | 1000000
Avondale | Highway | 23832 | Lower Buckeye Road: 125th Avenue to El Mirage ( N & S 1/2, .25 miles) Roadway Improvements | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.25 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN26-231 |  | 105080 | ----- | ----- | Add 2 lanes, curb, gutter, sidewalk | 2026 | Local | 2026 | 0 | 0 | 1000000 | 1000000
Avondale | Highway | 6576 | Dysart Road: Lower Buckeye to west-side of Aqua Fria (MOSC) | Local | Street | OCT-DEC 2026 | Maricopa | Other | 1 | 0 | 4 | No | No | No | No | Yes | No | No | No | AVN26-232 |  | 105059 | ----- | ----- | New Roadway | 2026 | Private | 2026 | 0 | 0 | 1000000 | 1000000
Avondale | Highway | 46069 | Lower Buckeye Rd: Litchfield Rd to 107th Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN26-520D |  | 105789 | ----- | ----- | Roadway widening (ADOT Fee) | 2026 | STBGP >200 PHX-WEST | 2026 | 21000 | 0 | 9000 | 30000
Avondale | Highway | 46069 | Lower Buckeye Rd: Litchfield Rd to 107th Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN26-520D1 |  | 105789 | ----- | ----- | Roadway widening (Design) | 2026 | STBGP >200 PHX-WEST | 2026 | 1967000 | 0 | 843000 | 2810000
Avondale | Highway | 1564 | Agua Fria Channel to Friendship Park (Phase 2) - north connection |  | Bike/Ped | OCT-DEC 2027 | Maricopa | Other | 0.15 | 0 | 0 | No | No | No | No | No | Yes | No | No | AVN26-540C | P0012 | 105052 | ----- | T0695 | Construct connection to Friendship Park | 2026 | CDS | 2024 | 500000 | 0 | 250000 | 750000
Avondale | Highway | 1564 | Agua Fria Channel to Friendship Park (Phase 2) - north connection |  | Bike/Ped | OCT-DEC 2027 | Maricopa | Other | 0.15 | 0 | 0 | No | No | No | No | No | Yes | No | No | AVN26-540D | P0012 | 105052 | ----- | T0695 | ADOT Design Review Fees | 2026 | Local | 2024 | 0 | 0 | 30000 | 30000
Avondale | Highway | 9283 | Dysart Road at McDowell Road | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | Yes | Yes | No | No | AVN20-472 |  | 100846 |  | SH636 | Construct Transit and Pedestrian improvements | 2027 | Local | 2027 | 0 | 0 | 2900000 | 2900000
Avondale | Highway | 46069 | Lower Buckeye Rd: Litchfield Rd to 107th Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN26-520R |  | 105789 | ----- | ----- | Roadway widening (Right of Way) | 2027 | STBGP >200 PHX-WEST | 2027 | 3010000 | 0 | 1290000 | 4300000
Avondale | Highway | 46069 | Lower Buckeye Rd: Litchfield Rd to 107th Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN26-520U |  | 105789 | ----- | ----- | Roadway widening (Utilities) | 2027 | STBGP >200 PHX-WEST | 2027 | 770000 | 0 | 330000 | 1100000
Avondale | Highway | 1177 | Dysart Road: Southern to Indian Springs | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 1 | 0 | 4 | No | No | No | Yes | Yes | No | No | No | AVN27-230 |  | 105050 | ----- | ----- | Add 4 lanes and 4-lane bridge | 2027 | Private | 2027 | 0 | 0 | 35000000 | 35000000
Avondale | Highway | 15516 | Vermeersch: Lower Buckeye to Dysart | Principal Arterial - Other | Street | OCT-DEC 2027 | Maricopa | Other | 1 | 2 | 2 | No | No | No | No | Yes | No | No | No | AVN27-231 |  | 105066 | ----- | ----- | Add Center Turn Lane, curb, gutter, sidewalks | 2027 | Local | 2027 | 0 | 0 | 4000000 | 4000000
Avondale | Highway | 46069 | Lower Buckeye Rd: Litchfield Rd to 107th Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN26-520C |  | 105789 | ----- | ----- | Roadway widening (Construction) | 2028 | STBGP >200 PHX-WEST | 2028 | 19317725 | 0 | 8279025 | 27596750
Avondale | Highway | 16700 | Agua Fria Channel to Friendship Park (Phase 2) - bridge section |  | Bike/Ped | OCT-DEC 2029 | Maricopa | Other | 0.15 | 0 | 0 | No | No | No | Yes | No | Yes | No | No | AVN28-540C |  | 105068 | ----- | ----- | Construct bridge to Friendship Park | 2028 | Local | 2028 | 0 | 0 | 6000000 | 6000000
Avondale | Highway | 7096 | Lower Buckeye Road: Central to the MOSC ( N & S 1/2, .30 miles) Roadway Improvements | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | Other | 0.3 | 2 | 4 | No | No | No | No | Yes | No | No | No | AVN30-530 |  | 105061 | ----- | ----- | Add 2 lanes, curb, gutter, sidewalk | 2030 | Local | 2030 | 0 | 0 | 2000000 | 2000000
Buckeye | Highway | 46845 | McDowell Rd: Dean Rd (alignment) to Verrado Way | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | BKY12-107 |  | 100891 | ----- | ----- | Construct two through lanes | 2026 | Private | 2026 | 0 | 0 | 2000000 | 2000000
Buckeye | Highway | 41057 | Jackrabbit Trl: Indian School to 750 feet north of Thomas Rd | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | BKY12-112 |  | 102039 | ----- | ----- | Construct two through lanes | 2026 | Private | 2026 | 0 | 0 | 200000 | 200000
Buckeye | Highway | 31916 | Canyon Springs Blvd (267th Ave): Deer Valley Rd (alignment) to Pinnacle Peak Rd (alignment) | Local | Street | OCT-DEC 2027 | Maricopa | Other | 1 | 0 | 4 | No | No | No | No | Yes | No | No | No | BKY13-103 |  | 102055 | ----- | ----- | Construct new four lane roadway and bridge over the CAP | 2026 | Private | 2026 | 0 | 0 | 5200000 | 5200000
Buckeye | Highway | 47900 | Broadway Rd: Apache Rd to Watson Rd | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | BKY13-106 |  | 102049 | ----- | ----- | Construct two through lanes | 2026 | Private | 2026 | 0 | 0 | 7756320 | 7756320
Buckeye | Highway | 14078 | Turner Rd: Baseline Rd to 0.5 miles north | Major Collector | Street | APR-JUN 2027 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | BKY13-109 |  | 100881 | ----- | ----- | Construct two through lanes, for intersection realignment at Baseline Road | 2026 | Private | 2026 | 0 | 0 | 1750000 | 1750000
Buckeye | Highway | 6425 | Pinnacle Peak Rd: 259th Ave (alignment) to 271st Ave | Local | Street | OCT-DEC 2027 | Maricopa | Other | 1.5 | 0 | 4 | No | No | No | No | Yes | No | No | No | BKY13-120 |  | 100875 | ----- | ----- | Construct new six lane roadway. Stripe only 2 lanes in each direction. | 2026 | Private | 2026 | 0 | 0 | 3000000 | 3000000
Buckeye | Highway | 45080 | Durango Street:Yuma Road to 247th Avenue (102980) | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0.5 | 0 | 2 | No | No | No | No | No | No | No | No | BKY21-006 | 102980 | 102964 | ----- | ----- | Construct two lane roadway. Includes ROW acquisition and all utility relocations to support installation of a Collector Roadway. | 2026 | Local | 2026 | 0 | 0 | 1642000 | 1642000
Buckeye | Highway | 39408 | Interstate 10 Fiber: SR85 to Watson Road | Principal Arterial - Interstate | ITS | JUL-SEP 2027 | Maricopa | Other | 4 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | BKY23-002 |  | 103220 | ----- | ----- | Conduit will be installed by the ADOT I-10 widening Project from Perryville Road to SR-85 in 2021. This project is to fund the installation of Fiber through the City's conduit ITS communications in accordance with City 2018 ITS Strategic Plan. There are 4 miles of fiber, and 0 miles of conduit and is one of 6 projects to complete Fiber Communications Ring #1. Cost: $161,000 | 2026 | Local | 2026 | 0 | 0 | 161000 | 161000
Buckeye | Highway | 42710 | Interstate 10 ITS: Johnson Road to SR-85 | Principal Arterial - Interstate | ITS | JUL-SEP 2028 | Maricopa | Other | 3 | 0 | 0 | No | No | No | No | Yes | No | No | Yes | BKY23-003 |  | 105101 | ----- | ----- | Install conduit and fiber for citywide ITS system. Includes 3 miles of fiber and 3 miles of conduit | 2026 | Local | 2026 | 0 | 0 | 120000 | 120000
Buckeye | Highway | 46791 | Jackrabbit Tr: Thomas Rd to McDowell Rd | Minor Arterial | Freeway | OCT-DEC 2027 | Maricopa | 5-year | 1 | 2 | 4 | No | No | No | No | No | No | No | No | BKY23-200 |  | 103477 | ----- | HB2858 | Roadway widening | 2026 | Leg Approp | 2023 | 0 | 0 | 20080000 | 20080000
Buckeye | Highway | 46791 | Jackrabbit Tr: Thomas Rd to McDowell Rd | Minor Arterial | Freeway | OCT-DEC 2027 | Maricopa | 5-year | 1 | 2 | 4 | No | No | No | No | No | No | No | No | BKY23-201 |  | 103477 | ----- | HB2858 | Roadway widening | 2026 | Local | 2023 | 0 | 0 | 5020000 | 5020000
Buckeye | Highway | 37489 | Buckeye Fiber Optic Backbone (MC 85/Miller Rd) | Minor Arterial | ITS | OCT-DEC 2026 | Maricopa | SM+O | 4.4 | 2 | 2 | No | No | No | No | Yes | No | Yes | No | BKY24-262C |  | 104421 | BKY-0(216)T | T0630 | Conduit, fiber, pull boxes, vaults and splices along MC 85/Miller Rd (Construction) | 2026 | CMAQ | 2026 | 1365512 | 0 | 82538 | 1448050
Buckeye | Highway | 7266 | Indian School Road: Jackrabbit Trail to Loop 303 | Principal Arterial - Other | Street | JUL-SEP 2028 | Maricopa | Other | 3.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | BKY25-002 |  | 103029 | ----- | ----- | Roadway widening from 2 to 4 lanes, including 5 traffic signals | 2026 | Local | 2026 | 0 | 0 | 4150000 | 4150000
Buckeye | Highway | 6826 | Miller Rd: Broadway Rd to Lower Buckeye Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | BKY26-520D |  | 105791 | ----- | ----- | Roadway widening (ADOT Fee) | 2026 | STBGP >200 PHX-WEST | 2026 | 21000 | 0 | 9000 | 30000
Buckeye | Highway | 47852 | Citywide in the PM-10 nonattainment area |  | Air Quality | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | BKY26-580 |  |  | ----- | ----- | Purchase PM-10 certified street sweepers | 2026 | CMAQ | 2026 | 212611 | 0 | 251982 | 464593
Buckeye | Highway | 6826 | Miller Rd: Broadway Rd to Lower Buckeye Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | BKY26-520C |  | 105791 | ----- | ----- | Roadway widening (Construction) | 2028 | STBGP >200 PHX-WEST | 2028 | 6618234 | 0 | 2836386 | 9454620
Carefree | Highway | 12176 | Pima Rd: Stagecoach Pass to Cave Creek Rd | Principal Arterial - Other | Street | OCT-DEC 2030 | Maricopa | ALCP | 0.25 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | CFR26-101CRB |  | 103034 | ----- | ----- | Construct Roadway Widening | 2026 | RARF | 2026 | 0 | 5250855.4 | -5250855.4 | 0
Carefree | Highway | 12176 | Pima Rd: Stagecoach Pass to Cave Creek Rd | Principal Arterial - Other | Street | OCT-DEC 2030 | Maricopa | ALCP | 0.25 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | CFR27-500CZ |  | 103034 | ----- | ----- | Construct Roadway Widening | 2027 | RARF | 2027 | 0 | 307281.73 | -307281.73 | 0
Cave Creek | Highway | 212 | Morning Star Rd. from Old Stage Rd. to Spur Cross Rd., 54th St. from Morning Star Rd. to 2,000 feet south, Spur Cross Rd. from near Honda Bow Rd. to entrance to Spur Cross Conservation Area | Minor Collector | Air Quality | OCT-DEC 2026 | Maricopa | Other | 2.5 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | CVK26-530C |  | 105114 | ----- | ----- | Paving Unpaved Alleys (Construction) | 2026 | CMAQ | 2026 | 1324448 | 0 | 80057 | 1404505
Cave Creek | Highway | 212 | Morning Star Rd. from Old Stage Rd. to Spur Cross Rd., 54th St. from Morning Star Rd. to 2,000 feet south, Spur Cross Rd. from near Honda Bow Rd. to entrance to Spur Cross Conservation Area | Minor Collector | Air Quality | OCT-DEC 2026 | Maricopa | Other | 2.5 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | CVK26-530D |  | 105114 | ----- | ----- | Paving Unpaved Roads (Design) | 2026 | Local | 2026 | 0 | 0 | 126168 | 126168
Cave Creek | Highway | 212 | Morning Star Rd. from Old Stage Rd. to Spur Cross Rd., 54th St. from Morning Star Rd. to 2,000 feet south, Spur Cross Rd. from near Honda Bow Rd. to entrance to Spur Cross Conservation Area | Minor Collector | Air Quality | OCT-DEC 2026 | Maricopa | Other | 2.5 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | CVK26-530D1 |  | 105114 | ----- | ----- | ADOT Review Fee | 2026 | Local | 2026 | 0 | 0 | 30000 | 30000
Cave Creek | Highway | 212 | Morning Star Rd. from Old Stage Rd. to Spur Cross Rd., 54th St. from Morning Star Rd. to 2,000 feet south, Spur Cross Rd. from near Honda Bow Rd. to entrance to Spur Cross Conservation Area | Minor Collector | Air Quality | OCT-DEC 2026 | Maricopa | Other | 2.5 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | CVK26-530R |  | 105114 | ----- | ----- | Paving Unpaved Roads (Right of Way) | 2026 | Local | 2026 | 0 | 0 | 1000 | 1000
Chandler | Highway | 38402 | Alma School Road, Willis Road to Pecos Road | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | Other | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | CHN11-105 |  | 100947 | ----- | ----- | Construct Roadway widening | 2026 | Private | 2026 | 0 | 0 | 1000000 | 1000000
Chandler | Highway | 4237 | Kyrene Road: North of Chandler Blvd. to Loop 202 | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-060D |  |  | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 2084854.9 | 2084854.9
Chandler | Highway | 4237 | Kyrene Road: North of Chandler Blvd. to Loop 202 | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-060DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2026 | 479 RARF ALCP | 2026 | 0 | 1381633.8 | -1381633.8 | 0
Chandler | Highway | 13236 | Alma School Road: Germann Road to Ocotillo Road | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | 479-ALCP | 2.1 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-061C |  |  | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 13493790.6 | 13493790.6
Chandler | Highway | 33403 | Various alleys in Chandler | Local | Air Quality | OCT-DEC 2026 | Maricopa | Other | 0 | 2 | 2 | No | No | No | No | No | No | Yes | No | CHN24-030C |  | 102460 | CHN-0(256)D | T0555 | Construct Road Paving | 2026 | CMAQ | 2026 | 2629089 | 0 | 158917 | 2788006
Chandler | Highway | 46012 | Alma School Road: Germann Rd to Queen Creek Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | CHN24-125CZ | 6ST747 | 102058 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 6805000 | 6805000
Chandler | Highway | 37397 | Kyrene Branch Canal and Highline Canal Shared Use Paths |  | Bike/Ped | APR-JUN 2027 | Maricopa | Other | 1.9 | 0 | 0 | No | No | No | No | Yes | Yes | Yes | No | CHN25-250C |  | 103119 | CHN-0(252)D | T0387 | Construct Bicycle Lane (4' min. w/o curb/gutter), Shared-use path (10' min.), and Signalized Crossing | 2026 | CMAQ | 2026 | 3399118.37 | 0 | 205461.03 | 3604579.4
Chandler | Highway | 8396 | Ray Rd at Dobson Rd | Minor Arterial | Safety | OCT-DEC 2027 | Maricopa | 5-year | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | CHN26-270C |  | 103602 | CHN-0(255)D | T0527 | Install dual left-turn lanes on all four approaches to intersection (Construction) | 2026 | HSIP-AZ | 2026 | 3368473 | 0 | 203608 | 3572081
Chandler | Highway | 8396 | Ray Rd at Dobson Rd | Minor Arterial | Safety | OCT-DEC 2027 | Maricopa | 5-year | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | CHN26-271C |  | 103602 | CHN-0(255)D | T0527 | Install dual left-turn lanes on all four approaches to intersection (Construction) | 2026 | Local | 2026 | 0 | 0 | 7012165 | 7012165
Chandler | Highway | 38477 | Chandler Blvd: Price Rd to Dobson Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 1 | 6 | 6 | Yes | No | Yes | No | No | Yes | No | No | CHN26-520D |  | 105779 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 7000 | 0 | 3000 | 10000
Chandler | Highway | 38477 | Chandler Blvd: Price Rd to Dobson Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 1 | 6 | 6 | Yes | No | Yes | No | No | Yes | No | No | CHN26-520D1 |  | 105779 | ----- | ----- | Roadway rehabilitation (Design) | 2026 | STBGP >200 PHX-MESA | 2026 | 175000 | 0 | 1053000 | 1228000
Chandler | Highway | 41611 | Chandler Citywide: Roadway Safety Action Plan |  | Safety | JUL-SEP 2027 | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | CHN26-570 |  | 105552 | ----- | ----- | Roadway Safety Action Plan | 2026 | SS4A | 2024 | 560000 | 0 | 140000 | 700000
Chandler | Highway | 4237 | Kyrene Road: North of Chandler Blvd. to Loop 202 | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-060RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 6254564.7 | 6254564.7
Chandler | Highway | 4237 | Kyrene Road: North of Chandler Blvd. to Loop 202 | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-060RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 4144901.4 | -4144901.4 | 0
Chandler | Highway | 4237 | Kyrene Road: North of Chandler Blvd. to Loop 202 | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-060C |  |  | ----- | ----- | Construct roadway widening | 2028 | Local | 2028 | 0 | 0 | 12509129.4 | 12509129.4
Chandler | Highway | 4237 | Kyrene Road: North of Chandler Blvd. to Loop 202 | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-060CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 8289802.8 | -8289802.8 | 0
Chandler | Highway | 14944 | McQueen Road: North of Warner Road to Pecos Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-064D |  |  | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 4244543.9 | 4244543.9
Chandler | Highway | 14944 | McQueen Road: North of Warner Road to Pecos Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-064DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 1760104 | -1760104 | 0
Chandler | Highway | 38477 | Chandler Blvd: Price Rd to Dobson Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 1 | 6 | 6 | Yes | No | Yes | No | No | Yes | No | No | CHN26-520C |  | 105779 | ----- | ----- | Roadway rehabilitation (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 4246060 | 0 | 10819740 | 15065800
Chandler | Highway | 14944 | McQueen Road: North of Warner Road to Pecos Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-064RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2029 | Local | 2029 | 0 | 0 | 12733631.7 | 12733631.7
Chandler | Highway | 14944 | McQueen Road: North of Warner Road to Pecos Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-064RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 8438580.6 | -8438580.6 | 0
Chandler | Highway | 14944 | McQueen Road: North of Warner Road to Pecos Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-064C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 25467263.4 | 25467263.4
Chandler | Highway | 14944 | McQueen Road: North of Warner Road to Pecos Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3 | 4 | 6 | No | No | No | No | No | No | No | No | CHN20-064CRW |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 16877161.2 | -16877161.2 | 0
Chandler | Transit | 45942 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | CHN26-500T |  | 105761 | ----- | 30.09.01 | City of Chandler Chandler Flex | 2026 | 5310-PMS | 2025 | 90000 | 0 | 90000 | 180000
El Mirage | Highway | 18023 | 121st Avenue: WWTP to Ramirez Road | Minor Collector | Air Quality | OCT-DEC 2026 | Maricopa | Other | 0.4 | 2 | 2 | No | No | No | No | No | No | Yes | No | ELM26-233C |  | 18023 | ----- | T0400 | Paving Unpaved Roads (Construction) | 2026 | CMAQ | 2026 | 835297 | 0 | 50490 | 885787
Florence | Highway | 15256 | Felix Rd: Hunt Hwy to Merrill Ranch Pkwy | Major Collector | Street | JAN-MAR 2026 | Pinal | Other | 1.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | FLO23-202 |  | 103168 | ----- | ----- | Widen Roadway | 2026 | Private | 2026 | 0 | 0 | 7500000 | 7500000
Florence | Highway | 16009 | Felix Rd: Heritage Rd to 1/2 mile north | Major Collector | Street | JAN-MAR 2026 | Pinal | Other | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | FLO26-201 |  | 105067 | ----- | ----- | Construct Roadway Widening | 2026 | Private | 2026 | 0 | 0 | 1000000 | 1000000
Florence | Highway | 21667 | Florence-Kelvin Hwy: SR 79 to Quail Run Rd | Major Collector | Street | OCT-DEC 2030 | Pinal | Other | 2 | 2 | 4 | No | No | No | No | Yes | No | No | No | FLO16-401 |  | 105074 | ----- | ----- | Construct Roadway Widening | 2030 | Private | 2030 | 0 | 0 | 1714000 | 1714000
Florence | Highway | 27013 | Felix Rd: Arizona Farms Rd to 1/2 mile south | Major Collector | Street | OCT-DEC 2030 | Pinal | Other | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | FLO24-201 |  | 103187 | ----- | ----- | Construct Roadway Widening | 2030 | Private | 2030 | 0 | 0 | 1000000 | 1000000
Fountain Hills | Highway | 27512 | Shea Blvd: Palisades Blvd. to Technology Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 2.2 | 4 | 6 | No | No | No | No | Yes | No | No | No | FTH19-102RRB |  | 100900 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 134709.15 | -134709.15 | 0
Fountain Hills | Highway | 27512 | Shea Blvd: Palisades Blvd. to Technology Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 2.2 | 4 | 6 | No | No | No | No | Yes | No | No | No | FTH22-102CRB |  | 100900 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 1795001.3 | -1795001.3 | 0
Fountain Hills | Highway | 27512 | Shea Blvd: Palisades Blvd. to Technology Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 2.2 | 4 | 6 | No | No | No | No | Yes | No | No | No | FTH26-102DRB |  | 100900 | ----- | ----- | Design Roadway Widening | 2026 | RARF | 2026 | 0 | 351106.76 | -351106.76 | 0
Fountain Hills | Highway | 37235 | Fountain Hills: Comprehensive Safety Action Plan and Demonstration Plan |  | Safety | N/A | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | FTH26-570 |  | 105805 | ----- | ----- | Planning and Demonstration | 2026 | SS4A | 2024 | 240000 | 0 | 60000 | 300000
Fountain Hills | Highway | 27512 | Shea Blvd: Palisades Blvd. to Technology Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 2.2 | 4 | 6 | No | No | No | No | Yes | No | No | No | FTH27-500CZ |  | 100900 | ----- | ----- | Construct roadway widening | 2027 | RARF | 2027 | 0 | 339177.45 | -339177.45 | 0
Gila Bend | Highway | 30814 | Various segments in Gila Bend | Local | Bike/Ped | JUL-SEP 2028 | Maricopa | Other | 1.3 | 2 | 2 | No | No | No | No | No | Yes | Yes | No | GBD21-802D1 |  | 100897 | GBD-0(205)T | T0702 | ADOT Design Review Fee | 2026 | STBGP-MAG | 2026 | 28290 | 0 | 1710 | 30000
Gila Bend | Highway | 30814 | Various segments in Gila Bend | Local | Bike/Ped | JUL-SEP 2028 | Maricopa | Other | 1.3 | 2 | 2 | No | No | No | No | No | Yes | Yes | No | GBD21-802D2 |  | 100897 | GBD-0(205)T | T0702 | Design sidewalks and bike lanes with shade trees | 2026 | STBGP-MAG | 2026 | 228206 | 0 | 13794 | 242000
Gila Bend | Highway | 30814 | Various segments in Gila Bend | Local | Bike/Ped | JUL-SEP 2028 | Maricopa | Other | 1.3 | 2 | 2 | No | No | No | No | No | Yes | Yes | No | GBD21-802C |  | 100897 | GBD-0(205)T | T0702 | Construct sidewalks and bike lanes with shade trees | 2027 | CMAQ | 2027 | 1110967 | 0 | 97153 | 1208120
Gilbert | Highway | 36605 | McQueen Rd at Elliot Rd | Minor Arterial | Street | OCT-DEC 2025 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB22-126CRB | ST1870 | 102063 | ----- | ----- | Construct intersection improvements | 2026 | RARF | 2026 | 0 | 5917150.79 | -5917150.79 | 0
Gilbert | Highway | 36605 | McQueen Rd at Elliot Rd | Minor Arterial | Street | OCT-DEC 2025 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB22-126RRB | ST1870 | 102063 | ----- | ----- | Acquisition of right-of-way for intersection improvements | 2026 | RARF | 2026 | 0 | 407182.37 | -407182.37 | 0
Gilbert | Highway | 8305 | Elliot Rd at Cooper Dr | Minor Arterial | Street | OCT-DEC 2024 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB23-108DRB | ST1380 | 100904 | ----- | ----- | Design intersection improvement (Reimb.) | 2026 | RARF | 2026 | 0 | 901949.23 | -901949.23 | 0
Gilbert | Highway | 36684 | Warner Rd: Recker Rd to Power Rd | Minor Arterial | Street | JAN-MAR 2026 | Maricopa | ALCP | 1 | 2 | 6 | No | No | No | No | Yes | No | No | No | GLB23-129RRB | ST1180 | 102826 | GIL-0(219)T | T0335 | Acquisition of right-of-way for roadway widening | 2026 | STBGP >200 PHX-MESA | 2026 | 2450000 | 0 | -2450000 | 0
Gilbert | Highway | 36684 | Warner Rd: Recker Rd to Power Rd | Minor Arterial | Street | JAN-MAR 2026 | Maricopa | ALCP | 1 | 2 | 6 | No | No | No | No | Yes | No | No | No | GLB23-129RWZ | ST1180 | 102826 | GIL-0(219)T | T0335 | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 3500000 | 3500000
Gilbert | Highway | 36684 | Warner Rd: Recker Rd to Power Rd | Minor Arterial | Street | JAN-MAR 2026 | Maricopa | ALCP | 1 | 2 | 6 | No | No | No | No | Yes | No | No | No | GLB24-129CRB | ST1180 | 102826 | GIL-0(219)T | T0335 | Construct roadway widening | 2026 | STBGP >200 PHX-MESA | 2026 | 7966851.61 | 0 | -7966851.61 | 0
Gilbert | Highway | 36525 | Baseline Rd: Greenfield Rd to Power Rd | Minor Arterial | Street | JUL-SEP 2027 | Maricopa | ALCP | 3 | 5 | 6 | No | No | No | No | Yes | No | No | No | GLB24-130CZ |  | 103005 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 17550000 | 17550000
Gilbert | Highway | 8305 | Elliot Rd at Cooper Dr | Minor Arterial | Street | OCT-DEC 2024 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB25-108CRB | ST1380 | 100904 | ----- | ----- | Construct intersection improvement (Reimb.) | 2026 | RARF | 2026 | 0 | 2692399.54 | -2692399.54 | 0
Gilbert | Highway | 8305 | Elliot Rd at Cooper Dr | Minor Arterial | Street | OCT-DEC 2024 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB25-108RRB | ST1380 | 100904 | ----- | ----- | Acquisition of right-of-way for intersection improvement | 2026 | RARF | 2026 | 0 | 734454.44 | -734454.44 | 0
Gilbert | Highway | 25046 | Stacey Rd: Higley Rd. east to 172nd St. | Local | Air Quality | OCT-DEC 2027 | Maricopa | Other | 0.5 | 2 | 2 | No | No | No | No | No | No | Yes | No | GLB25-230C | ST2126 | 103064 | GIL-0(223)T | T0423 | Construct Pave Unpaved Road | 2026 | CMAQ | 2026 | 2860984 | 0 | 347084 | 3208068
Gilbert | Highway | 14332 | McQueen Rd at Guadalupe Rd | Minor Arterial | Street | JAN-MAR 2025 | Maricopa | ALCP | 0.1 | 6 | 6 | No | No | No | No | Yes | No | No | No | GLB26-123CRB | ST1910 | 103038 | ----- | ----- | Construct roadway widening (Reimb.) | 2026 | RARF | 2026 | 0 | 2515542.97 | -2515542.97 | 0
Gilbert | Highway | 37011 | Recker Rd: Ocotillo to Chandler Heights Rd | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | GLB26-230 | ST080 | 105092 | ----- | ----- | Add 1 lane in each direction | 2026 | Local | 2026 | 0 | 0 | 5389000 | 5389000
Gilbert | Highway | 5360 | Higley Rd: Warner Rd to Amber Ln | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 0.6 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB26-520D |  | 105788 | ----- | ----- | Roadway widening (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 21000 | 0 | 9000 | 30000
Gilbert | Highway | 5360 | Higley Rd: Warner Rd to Amber Ln | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 0.6 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB26-520D1 |  | 105788 | ----- | ----- | Roadway widening (Design) | 2026 | STBGP >200 PHX-MESA | 2026 | 750134 | 0 | 321486 | 1071620
Gilbert | Highway | 46003 | Townwide | Minor Arterial | Safety | JAN-MAR 2028 | Maricopa | Other | 10.5 | 0 | 0 | Yes | No | No | No | No | No | No | No | GLB26-570 |  |  | ----- | ----- | Planning Level Study to evaluate safety and efficiency of fourteen (14) At-Grade railroad crossings within Gilbert, prioritizing the crossings for elimination and completing 15% Design Plans for up three (3) At-Grade Crossings | 2026 | RCE | 2026 | 2448000 | 0 | 612000 | 3060000
Gilbert | Highway | 44489 | Ocotillo Road: Greenfield Road to Higley Road | Major Collector | Street | OCT-DEC 2024 | Maricopa | 479-ALCP | 0.73 | 0 | 4 | No | No | No | No | No | No | No | No | GLB20-002DRB |  |  | ----- | ----- | Design new roadway (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 5794509.5 | -5794509.5 | 0
Gilbert | Highway | 15517 | Power Road at Pecos Road Grade Separation | Principal Arterial - Other | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.45 | 5 | 6 | No | No | No | No | No | No | No | No | GLB20-006D |  |  | ----- | ----- | Design rail crossing | 2027 | Local | 2027 | 0 | 0 | 14994412.5 | 14994412.5
Gilbert | Highway | 5360 | Higley Rd: Warner Rd to Amber Ln | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 0.6 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB26-520R |  | 105788 | ----- | ----- | Roadway widening (Right of Way) | 2027 | STBGP >200 PHX-MESA | 2027 | 262500 | 0 | 112500 | 375000
Gilbert | Highway | 5360 | Higley Rd: Warner Rd to Amber Ln | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 0.6 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB26-520U |  | 105788 | ----- | ----- | Roadway widening (Utilities) | 2027 | STBGP >200 PHX-MESA | 2027 | 1144570 | 0 | 490530 | 1635100
Gilbert | Highway | 36605 | McQueen Rd at Elliot Rd | Minor Arterial | Street | OCT-DEC 2025 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB27-500CZ | ST1870 | 102063 | ----- | ----- | Construct intersection improvements | 2027 | RARF | 2027 | 0 | 1813703.81 | -1813703.81 | 0
Gilbert | Highway | 44489 | Ocotillo Road: Greenfield Road to Higley Road | Major Collector | Street | OCT-DEC 2024 | Maricopa | 479-ALCP | 0.73 | 0 | 4 | No | No | No | No | No | No | No | No | GLB20-002RWRB |  |  | ----- | ----- | Acquisition of right-of-way for new roadway (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 17383528.5 | -17383528.5 | 0
Gilbert | Highway | 29373 | Recker Road: Ocotillo Road to Chandler Heights | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 2 | No | No | No | No | No | No | No | No | GLB20-044D |  |  | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 1348328.7 | 1348328.7
Gilbert | Highway | 35163 | Hunt Highway: Higley Road to Recker Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1.04 | 2 | 6 | No | No | No | No | No | No | No | No | GLB20-047D |  |  | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 1617469.2 | 1617469.2
Gilbert | Highway | 26466 | Val Vista Drive: Riggs Road to Hunt Highway | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | GLB20-049D |  |  | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 1353580.2 | 1353580.2
Gilbert | Highway | 43119 | Val Vista Road at Union Pacific Railroad Grade Separation | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0 | 6 | 6 | No | No | No | No | No | No | No | No | GLB20-102D |  |  | ----- | ----- | Design rail crossing | 2028 | Local | 2028 | 0 | 0 | 3242815.8 | 3242815.8
Gilbert | Highway | 49446 | Higley Rd, Greenfield Rd, Ray Rd, Warner Rd, and Elliot Rd. | Minor Arterial | ITS | OCT-DEC 2029 | Maricopa | Other | 17 | 6 | 6 | No | No | No | No | Yes | No | No | No | GLB22-801 | TS1330 | 100922 | ----- | ----- | Gilbert ATMS Fiber East Ring Project Phase I | 2028 | Local | 2028 | 0 | 0 | 7838000 | 7838000
Gilbert | Highway | 5360 | Higley Rd: Warner Rd to Amber Ln | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 0.6 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLB26-520C |  | 105788 | ----- | ----- | Roadway widening (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 6633773.3 | 0 | 2843045.7 | 9476819
Gilbert | Highway | 42229 | Guadalupe Rd at Power Rd | Principal Arterial - Other | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | GLB28-500DZ | ST1340 | 102065 | ----- | ----- | Design intersection improvement | 2028 | Local | 2028 | 0 | 0 | 960000 | 960000
Gilbert | Highway | 42229 | Guadalupe Rd at Power Rd | Principal Arterial - Other | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | GLB28-501RWZ | ST1340 | 102065 | ----- | ----- | Acquisition of right-of-way for intersection improvement | 2028 | Local | 2028 | 0 | 0 | 227000 | 227000
Gilbert | Highway | 42229 | Guadalupe Rd at Power Rd | Principal Arterial - Other | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | GLB28-502CZ | ST1340 | 102065 | ----- | ----- | Construct intersection improvement | 2028 | Local | 2028 | 0 | 0 | 7398000 | 7398000
Gilbert | Highway | 44489 | Ocotillo Road: Greenfield Road to Higley Road | Major Collector | Street | OCT-DEC 2024 | Maricopa | 479-ALCP | 0.73 | 0 | 4 | No | No | No | No | No | No | No | No | GLB20-002CRB |  |  | ----- | ----- | Construct new roadway (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 34767057 | -34767057 | 0
Gilbert | Highway | 15517 | Power Road at Pecos Road Grade Separation | Principal Arterial - Other | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.45 | 5 | 6 | No | No | No | No | No | No | No | No | GLB20-006RW |  |  | ----- | ----- | Acquisition of right-of-way for rail crossing | 2029 | Local | 2029 | 0 | 0 | 44983237.5 | 44983237.5
Gilbert | Highway | 29373 | Recker Road: Ocotillo Road to Chandler Heights | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 2 | No | No | No | No | No | No | No | No | GLB20-044RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2029 | Local | 2029 | 0 | 0 | 4044986.1 | 4044986.1
Gilbert | Highway | 35163 | Hunt Highway: Higley Road to Recker Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1.04 | 2 | 6 | No | No | No | No | No | No | No | No | GLB20-047RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2029 | Local | 2029 | 0 | 0 | 4852407.6 | 4852407.6
Gilbert | Highway | 26466 | Val Vista Drive: Riggs Road to Hunt Highway | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | GLB20-049RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2029 | Local | 2029 | 0 | 0 | 4060740.6 | 4060740.6
Gilbert | Highway | 43119 | Val Vista Road at Union Pacific Railroad Grade Separation | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0 | 6 | 6 | No | No | No | No | No | No | No | No | GLB20-102RW |  |  | ----- | ----- | Acquisition of right-of-way for rail crossing | 2029 | Local | 2029 | 0 | 0 | 9728447.4 | 9728447.4
Gilbert | Highway | 18918 | McQueen Road at Union Pacific Railroad Grade Separation | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 0 | 6 | 6 | No | No | No | No | No | No | No | No | GLB20-103D |  |  | ----- | ----- | Design rail crossing | 2029 | Local | 2029 | 0 | 0 | 3183736.2 | 3183736.2
Gilbert | Highway | 15517 | Power Road at Pecos Road Grade Separation | Principal Arterial - Other | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.45 | 5 | 6 | No | No | No | No | No | No | No | No | GLB20-006C |  |  | ----- | ----- | Construct rail crossing | 2030 | Local | 2030 | 0 | 0 | 89966475 | 89966475
Gilbert | Highway | 29373 | Recker Road: Ocotillo Road to Chandler Heights | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 2 | No | No | No | No | No | No | No | No | GLB20-044C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 8089972.2 | 8089972.2
Gilbert | Highway | 35163 | Hunt Highway: Higley Road to Recker Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-FLCP | 1.04 | 2 | 6 | No | No | No | No | No | No | No | No | GLB20-047C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 9704815.2 | 9704815.2
Gilbert | Highway | 26466 | Val Vista Drive: Riggs Road to Hunt Highway | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | GLB20-049C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 8121481.2 | 8121481.2
Gilbert | Highway | 43119 | Val Vista Road at Union Pacific Railroad Grade Separation | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0 | 6 | 6 | No | No | No | No | No | No | No | No | GLB20-102C |  |  | ----- | ----- | Construct rail crossing | 2030 | Local | 2030 | 0 | 0 | 19456894.8 | 19456894.8
Gilbert | Highway | 18918 | McQueen Road at Union Pacific Railroad Grade Separation | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 0 | 6 | 6 | No | No | No | No | No | No | No | No | GLB20-103RW |  |  | ----- | ----- | Acquisition of right-of-way for rail crossing | 2030 | Local | 2030 | 0 | 0 | 9551208.6 | 9551208.6
Glendale | Highway | 34440 | Reems Rd, Northern to Orangewood | Major Collector | Street | OCT-DEC 2027 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | GLN23-204 |  | 103207 | ----- | ----- | Widen Roadway | 2026 | Private | 2026 | 0 | 0 | 2100000 | 2100000
Glendale | Highway | 19777 | Maryland Ave to the north, 43rd Ave on the east, Bethany Home Rd to south and 59th Ave to the west | Major Collector | Bike/Ped | OCT-DEC 2027 | Maricopa | Other | 1.83 | 2 | 2 | No | No | No | No | No | Yes | Yes | No | GLN24-251R |  | 103069 | GLN-0(269)T | T0373 | Right of Way Bicycle Lane (4' min. w/o curb/gutter), Bicycle Lane (5' min. with curb/gutter), Buffered Bike Lane, Improvement to an existing bicycle and pedestrian facility | 2026 | Local | 2026 | 0 | 0 | 143220 | 143220
Glendale | Highway | 19777 | Maryland Ave to the north, 43rd Ave on the east, Bethany Home Rd to south and 59th Ave to the west | Major Collector | Bike/Ped | OCT-DEC 2027 | Maricopa | Other | 1.83 | 2 | 2 | No | No | No | No | No | Yes | Yes | No | GLN25-251C |  | 103069 | GLN-0(269)T | T0373 | Construct Bicycle Lane (4' min. w/o curb/gutter), Bicycle Lane (5' min. with curb/gutter), Buffered Bike Lane, Improvement to an existing bicycle and pedestrian facility | 2026 | CMAQ | 2026 | 1501761.2 | 0 | 3726839.54 | 5228600.74
Glendale | Highway | 4710 | Bethany Home Road: Loop 101 to 47th Avenue | Minor Arterial | ITS | OCT-DEC 2027 | Maricopa | SM+O | 6 | 4 | 4 | No | No | No | No | Yes | No | Yes | No | GLN25-260C |  | 103934 | GLN-0(271)T | T0550 | Advanced Detection & Stop Bars (Procure & Install) | 2026 | CMAQ | 2026 | 513746 | 0 | 31054 | 544800
Glendale | Highway | 33870 | Glendale Avenue: 83rd Avenue to 45th Avenue | Minor Arterial | ITS | OCT-DEC 2027 | Maricopa | SM+O | 5 | 5 | 5 | No | No | No | No | Yes | No | Yes | No | GLN25-261C |  | 103935 | GLN-0(270)T | T0546 | Radar Detection & Adaptive Control (Procure and Construct) | 2026 | CMAQ | 2026 | 397192 | 0 | 24008 | 421200
Glendale | Highway | 10828 | 67th Ave: Deer Valley Rd to Pinnacle Peak Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLN26-520D |  | 105786 | ----- | ----- | Roadway widening (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 21000 | 0 | 9000 | 30000
Glendale | Highway | 10828 | 67th Ave: Deer Valley Rd to Pinnacle Peak Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLN26-520D1 |  | 105786 | ----- | ----- | Roadway widening (Design) | 2026 | STBGP >200 PHX-MESA | 2026 | 784000 | 0 | 336000 | 1120000
Glendale | Highway | 21070 | Litchfield Rd: Missouri Ave to Northern Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.5 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-521D |  | 105781 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 21000 | 0 | 9000 | 30000
Glendale | Highway | 21070 | Litchfield Rd: Missouri Ave to Northern Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.5 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-521D1 |  | 105781 | ----- | ----- | Roadway rehabilitation (Design) | 2026 | STBGP >200 PHX-MESA | 2026 | 1337000 | 0 | 573000 | 1910000
Glendale | Highway | 43039 | Glendale Ave: El Mirage Rd to Litchfield Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-522D |  | 105780 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 21000 | 0 | 9000 | 30000
Glendale | Highway | 43039 | Glendale Ave: El Mirage Rd to Litchfield Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-522D1 |  | 105780 | ----- | ----- | Roadway rehabilitation (Design) | 2026 | STBGP >200 PHX-MESA | 2026 | 1337000 | 0 | 573000 | 1910000
Glendale | Highway | 25453 | Camelback Rd: 59th Ave to 83rd Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-523D |  | 105778 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 21000 | 0 | 9000 | 30000
Glendale | Highway | 25453 | Camelback Rd: 59th Ave to 83rd Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-523D1 |  | 105778 | ----- | ----- | Roadway rehabilitation (Design) | 2026 | STBGP >200 PHX-MESA | 2026 | 980000 | 0 | 420000 | 1400000
Glendale | Highway | 49216 | 75th Avenue Reconstruction | Major Collector | Street | OCT-DEC 2030 | Maricopa | Other | 1 | 0 | 0 | No | No | Yes | No | Yes | No | No | No | GLN26-530 |  |  | ----- | ----- | Pavement reconstruction | 2026 | Leg Approp | 2026 | 0 | 0 | 3000000 | 3000000
Glendale | Highway | 19890 | Glendale: Comprehensive Safety Action Plan and Demonstration Plan |  | Safety | N/A | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | GLN26-570 |  | 105800 | CRE4N8H1X6J5 | ----- | Active Transportation & ADA Transition Plan | 2026 | SS4A | 2024 | 799992 | 0 | 199998 | 999990
Glendale | Highway | 48643 | 59th Avenue: Camelback Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 11 | 4 | 6 | No | No | No | No | No | No | No | No | GLN20-001D |  |  | ----- | ----- | Design roadway widening | 2027 | Local | 2027 | 0 | 0 | 3237564.2 | 3237564.2
Glendale | Highway | 48643 | 59th Avenue: Camelback Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 11 | 4 | 6 | No | No | No | No | No | No | No | No | GLN20-001DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 2145534.6 | -2145534.6 | 0
Glendale | Highway | 10828 | 67th Ave: Deer Valley Rd to Pinnacle Peak Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLN26-520R |  | 105786 | ----- | ----- | Roadway widening (Right of Way) | 2027 | STBGP >200 PHX-MESA | 2027 | 980000 | 0 | 420000 | 1400000
Glendale | Highway | 10828 | 67th Ave: Deer Valley Rd to Pinnacle Peak Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLN26-520U |  | 105786 | ----- | ----- | Roadway widening (Utilities) | 2027 | STBGP >200 PHX-MESA | 2027 | 350000 | 0 | 150000 | 500000
Glendale | Highway | 21070 | Litchfield Rd: Missouri Ave to Northern Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.5 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-521R |  | 105781 | ----- | ----- | Roadway rehabilitation (Right of Way) | 2027 | STBGP >200 PHX-MESA | 2027 | 2240000 | 0 | 960000 | 3200000
Glendale | Highway | 21070 | Litchfield Rd: Missouri Ave to Northern Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.5 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-521U |  | 105781 | ----- | ----- | Roadway rehabilitation (Utilities) | 2027 | STBGP >200 PHX-MESA | 2027 | 350000 | 0 | 150000 | 500000
Glendale | Highway | 43039 | Glendale Ave: El Mirage Rd to Litchfield Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-522R |  | 105780 | ----- | ----- | Roadway rehabilitation (Right of Way) | 2027 | STBGP >200 PHX-MESA | 2027 | 315000 | 0 | 135000 | 450000
Glendale | Highway | 43039 | Glendale Ave: El Mirage Rd to Litchfield Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-522U |  | 105780 | ----- | ----- | Roadway rehabilitation (Utilities) | 2027 | STBGP >200 PHX-MESA | 2027 | 280000 | 0 | 120000 | 400000
Glendale | Highway | 25453 | Camelback Rd: 59th Ave to 83rd Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-523U |  | 105778 | ----- | ----- | Roadway rehabilitation (Utilities) | 2027 | STBGP >200 PHX-MESA | 2027 | 350000 | 0 | 150000 | 500000
Glendale | Highway | 48643 | 59th Avenue: Camelback Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 11 | 4 | 6 | No | No | No | No | No | No | No | No | GLN20-001RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2028 | Local | 2028 | 0 | 0 | 9712692.6 | 9712692.6
Glendale | Highway | 48643 | 59th Avenue: Camelback Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 11 | 4 | 6 | No | No | No | No | No | No | No | No | GLN20-001RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 6436603.8 | -6436603.8 | 0
Glendale | Highway | 10828 | 67th Ave: Deer Valley Rd to Pinnacle Peak Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | GLN26-520C |  | 105786 | ----- | ----- | Roadway widening (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 6751500 | 0 | 2893500 | 9645000
Glendale | Highway | 21070 | Litchfield Rd: Missouri Ave to Northern Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.5 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-521C |  | 105781 | ----- | ----- | Roadway rehabilitation (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 11958100 | 0 | 5124900 | 17083000
Glendale | Highway | 43039 | Glendale Ave: El Mirage Rd to Litchfield Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-522C |  | 105780 | ----- | ----- | Roadway rehabilitation (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 8554000 | 0 | 3666000 | 12220000
Glendale | Highway | 25453 | Camelback Rd: 59th Ave to 83rd Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 3 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | GLN26-523C |  | 105778 | ----- | ----- | Roadway rehabilitation (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 12540500 | 0 | 5374500 | 17915000
Glendale | Highway | 48643 | 59th Avenue: Camelback Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 11 | 4 | 6 | No | No | No | No | No | No | No | No | GLN20-001C |  |  | ----- | ----- | Construct roadway widening | 2029 | Local | 2029 | 0 | 0 | 19425385.2 | 19425385.2
Glendale | Highway | 48643 | 59th Avenue: Camelback Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 11 | 4 | 6 | No | No | No | No | No | No | No | No | GLN20-001CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 12873207.6 | -12873207.6 | 0
Glendale | Highway | 42786 | Glendale Ave, Cotton Ln to 303L Estrella | Major Collector | Street | OCT-DEC 2030 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | GLN23-206A |  | 103227 | ----- | ----- | Widen Roadway | 2029 | Local | 2029 | 0 | 0 | 1380625 | 1380625
Glendale | Highway | 42786 | Glendale Ave, Cotton Ln to 303L Estrella | Major Collector | Street | OCT-DEC 2030 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | GLN23-206B |  | 103227 | ----- | ----- | Widen Roadway | 2029 | Private | 2029 | 0 | 0 | 4141875 | 4141875
Glendale | Transit | 14161 | Regionwide: Glendale |  | Transit Bus | OCT-DEC 2026 | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | GLN23-010T |  | 102982 | AZ-2022-003 | 11.12.04 | Purchase bus: < 30 foot - 1 replace (GUS) | 2026 | 5307 | 2021 | 123250 | 21750 | 0 | 145000
Glendale | Transit | 7246 | Regionwide: Glendale |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | GLN26-210T |  |  | ----- | 11.12.04 | Purchase bus: < 30 foot - 5 replace (GUS) | 2026 | 5339-PMS | 2025 | 909861 | 160564 | 0 | 1070425
Glendale | Transit | 7246 | Regionwide: Glendale |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | GLN26-211T |  |  | ----- | 11.12.04 | Purchase bus: < 30 foot - 6 replace (dial-a-ride) | 2026 | 5339-PMS | 2025 | 877756 | 154898 | 0 | 1032654
Glendale | Transit | 7246 | Regionwide: Glendale |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | GLN26-211T2 |  |  | ----- | 11.12.04 | Purchase bus: < 30 foot - 5 replace (dial-a-ride) | 2026 | 5339-PMS | 2024 | 731463 | 129082 | 0 | 860545
Glendale | Transit | 47559 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | GLN26-500T |  | 103172 | ----- | 30.09.01 | City of Glendale GUS - Glendale Urban Shuttle | 2026 | 5310-PMS | 2025 | 36405 | 0 | 36405 | 72810
Glendale | Transit | 47559 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | GLN26-501T |  | 103172 | ----- | 30.09.01 | City of Glendale Taxi Vouchers | 2026 | 5310-PMS | 2025 | 53196 | 0 | 53196 | 106392
Glendale | Transit | 38297 | Regionwide: Glendale |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | GLN26-510T |  |  | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PMS | 2025 | 119020 | 0 | 29755 | 148775
Goodyear | Highway | 42310 | Yuma Road: Estrella Parkway to Litchfield Road | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | GDY20-020D |  | 105100 | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 3421367.5 | 3421367.5
Goodyear | Highway | 18761 | Yuma Road Bridge at Bullard Wash | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 0.22 | 0 | 6 | No | No | No | No | No | No | No | No | GDY20-022D |  |  | ----- | ----- | Design new bridge | 2026 | Local | 2026 | 0 | 0 | 1226230.8 | 1226230.8
Goodyear | Highway | 27110 | Camelback Rd: Perryville Rd to 181st Ave | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.75 | 2 | 6 | No | No | No | No | Yes | No | No | No | GDY21-207 |  |  | ----- | ----- | Widen Roadway | 2026 | Private | 2026 | 0 | 0 | 5500000 | 5500000
Goodyear | Highway | 44428 | Goodyear (Citywide) | Minor Arterial | ITS | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | GDY25-271C |  | 104863 | GDY-0(220)T | T0700 | Intelligent Transportation System (ITS) and Dilemma Zone Advance Detection Technology Upgrades | 2026 | CDS | 2024 | 471710 | 0 | 28513 | 500223
Goodyear | Highway | 44428 | Goodyear (Citywide) | Minor Arterial | ITS | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | GDY25-271D |  | 104863 | GDY-0(220)T | T0700 | ADOT Design Review Fees | 2026 | CDS | 2024 | 28290 | 0 | 1710 | 30000
Goodyear | Highway | 40395 | Bullard Ave.: Celebrate Life Way to Roosevelt | Minor Arterial | Street | JAN-MAR 2026 | Maricopa | Other | 0.5 | 5 | 6 | No | No | No | No | Yes | No | No | No | GDY26-530 | 42052 | 105766 | ----- | ----- | Widen Roadway - Add one SB lane | 2026 | Local | 2026 | 0 | 0 | 5230400 | 5230400
Goodyear | Highway | 19328 | Camelback Rd: SR303 to Village Blvd | Minor Arterial | Street | APR-JUN 2027 | Maricopa | Other | 2 | 2 | 4 | No | No | No | No | Yes | No | No | No | GDY26-531 | 42038 | 105756 | ----- | ----- | Widen Roadway | 2026 | Local | 2026 | 0 | 0 | 31228500 | 31228500
Goodyear | Highway | 19260 | Cotton Lane: Estrella Parkway to Cotton Lane Bridge | Minor Arterial | Street | JUL-SEP 2026 | Maricopa | Other | 2 | 2 | 4 | No | No | No | No | Yes | No | No | No | GDY26-532 | 42046 | 105755 | ----- | ----- | Widen Roadway | 2026 | Local | 2026 | 0 | 0 | 7000000 | 7000000
Goodyear | Highway | 17433 | Yuma Road: Canyon Trails to Sarival | Minor Arterial | Street | JAN-MAR 2027 | Maricopa | Other | 0.5 | 3 | 6 | No | No | No | No | Yes | No | No | No | GDY26-534 | 42037 | 105754 | ----- | ----- | Widen Roadway | 2026 | Local | 2026 | 0 | 0 | 10278000 | 10278000
Goodyear | Highway | 28279 | Goodyear: Road Safety Plan & Demonstration Project |  | Safety | JUL-SEP 2027 | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | GDY26-570 |  | 105555 | 693JJ32540130 | ----- | Development of Road Safety Action Plan with Demonstration Activities | 2026 | SS4A | 2024 | 624000 | 0 | 156000 | 780000
Goodyear | Highway | 28611 | Estrella Pkwy: MC-85 to Vineyard Ave | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | Yes | No | No | GDY10-712 |  | 100937 | ----- | ----- | Reconstruct and widen roadway at Gila River and on-road bike lane | 2027 | Local | 2027 | 0 | 0 | 95337000 | 95337000
Goodyear | Highway | 29252 | Rainbow Valley Road and Riggs Road to State Route 238 | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 20 | 0 | 2 | No | No | No | No | Yes | No | No | No | GDY11-103 |  | 102084 | ----- | ----- | Design Sonoran Valley Parkway | 2027 | Local | 2027 | 0 | 0 | 8000000 | 8000000
Goodyear | Highway | 42310 | Yuma Road: Estrella Parkway to Litchfield Road | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | GDY20-020RW |  | 105100 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 10264102.5 | 10264102.5
Goodyear | Highway | 18761 | Yuma Road Bridge at Bullard Wash | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 0.22 | 0 | 6 | No | No | No | No | No | No | No | No | GDY20-022RW |  |  | ----- | ----- | Acquisition of right-of-way for new bridge | 2027 | Local | 2027 | 0 | 0 | 3678692.4 | 3678692.4
Goodyear | Highway | 27449 | Cotton Lane: Union Pacific Railroad to Huhtamaki Driveway | Minor Arterial | Street | APR-JUN 2029 | Maricopa | Other | 0.5 | 5 | 6 | No | No | No | No | Yes | No | No | No | GDY27-530 | 42084 | 105764 | ----- | ----- | Widen Roadway - Eliminate Scallop St | 2027 | Local | 2027 | 0 | 0 | 7000000 | 7000000
Goodyear | Highway | 3745 | Estrella Parkway - Yuma Road | Minor Arterial | Street | APR-JUN 2030 | Maricopa | Other | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | GDY27-531 | 42-23-300 | 105748 | ----- | ----- | Widen Roadway - Eliminate Scallop St | 2027 | Local | 2027 | 0 | 0 | 24236000 | 24236000
Goodyear | Highway | 29252 | Rainbow Valley Road and Riggs Road to State Route 238 | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 20 | 0 | 2 | No | No | No | No | Yes | No | No | No | GDY11-102 |  | 102084 | ----- | ----- | Acquire/protect ROW Sonoran Valley Parkway | 2028 | Local | 2028 | 0 | 0 | 27000000 | 27000000
Goodyear | Highway | 42310 | Yuma Road: Estrella Parkway to Litchfield Road | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | GDY20-020C |  | 105100 | ----- | ----- | Construct roadway widening | 2028 | Local | 2028 | 0 | 0 | 20528205 | 20528205
Goodyear | Highway | 18761 | Yuma Road Bridge at Bullard Wash | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 0.22 | 0 | 6 | No | No | No | No | No | No | No | No | GDY20-022C |  |  | ----- | ----- | Construct new bridge | 2028 | Local | 2028 | 0 | 0 | 7357384.8 | 7357384.8
Goodyear | Highway | 28526 | Cotton Lane: Estrella Parkway to Cotton Lane Bridge | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 3 | 2 | 4 | No | No | No | No | Yes | No | No | No | GDY25-210 |  | 103194 | ----- | ----- | Widen Roadway | 2028 | Local | 2028 | 0 | 0 | 4300000 | 4300000
Goodyear | Highway | 24059 | Indian School Road: Perryville to Citrus | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 2 | 6 | No | No | No | No | Yes | No | No | No | GDY28-530 | 42089 | 105758 | ----- | ----- | Widen Roadway | 2028 | Local | 2028 | 0 | 0 | 43724800 | 43724800
Goodyear | Highway | 25587 | Yuma Road: Cotton Lane to Canyon Trails | Minor Arterial | Street | APR-JUN 2029 | Maricopa | Other | 0.5 | 3 | 6 | No | No | No | No | Yes | No | No | No | GDY28-531 | 42-23-314 | 105759 | ----- | ----- | Widen Roadway | 2028 | Local | 2028 | 0 | 0 | 13060000 | 13060000
Goodyear | Highway | 29252 | Rainbow Valley Road and Riggs Road to State Route 238 | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 20 | 0 | 2 | No | No | No | No | Yes | No | No | No | GDY13-107 |  | 102084 | ----- | ----- | Construct Sonoran Valley Parkway | 2029 | Local | 2029 | 0 | 0 | 75000000 | 75000000
Goodyear | Transit | 25347 | Citywide: Goodyear |  | Transit Other | OCT-DEC 2025 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | Yes | No | No | GDY23-210T |  | 103307 | AZ-2023-026-01 | 30.09.01 | Operating: Microtransit Pilot Program | 2026 | 5307-AVN UZA | 2022 | 500000 | 0 | 500000 | 1000000
Guadalupe | Highway | 5121 | Guadalupe Road: I-10 to Parkside Drive | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 0.7 | 2 | 2 | No | No | No | No | No | No | No | No | GDL20-001D |  |  | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 388612.8 | 388612.8
Guadalupe | Highway | 5121 | Guadalupe Road: I-10 to Parkside Drive | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 0.7 | 2 | 2 | No | No | No | No | No | No | No | No | GDL20-001RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 1165838.4 | 1165838.4
Guadalupe | Highway | 37383 | Calle Guadalupe: I-10 to Highline Canal | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0.7 | 2 | 2 | No | No | Yes | No | No | No | No | No | GDL25-271D |  | 104862 | GUA-0(207)T | T0701 | ADOT Design Review Fees | 2026 | CDS | 2024 | 28290 | 0 | 1710 | 30000
Guadalupe | Highway | 37383 | Calle Guadalupe: I-10 to Highline Canal | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0.7 | 2 | 2 | No | No | Yes | No | No | No | No | No | GDL25-271D1 |  | 104862 | GUA-0(207)T | T0701 | Roadway reconstruction (Design) | 2026 | CDS | 2024 | 187808 | 0 | 11352 | 199160
Guadalupe | Highway | 5121 | Guadalupe Road: I-10 to Parkside Drive | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 0.7 | 2 | 2 | No | No | No | No | No | No | No | No | GDL20-001C |  |  | ----- | ----- | Construct roadway widening | 2027 | Local | 2027 | 0 | 0 | 2331676.8 | 2331676.8
Guadalupe | Highway | 37383 | Calle Guadalupe: I-10 to Highline Canal | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0.7 | 2 | 2 | No | No | Yes | No | No | No | No | No | GDL25-271C |  | 104862 | GUA-0(207)T | T0701 | Roadway reconstruction (construction) | 2027 | CDS | 2024 | 1400181 | 0 | 84634 | 1484815
MAG | Highway | 12571 | Regionwide: Transportation and Air Quality planning and Support |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG26-280 |  | 102985 | MAG-T(026)D | PMG2603P | Transportation and Air Quality planning and support | 2026 | STBGP-MAG | 2025 | 9000000 | 0 | 544008 | 9544008
MAG | Highway | 15214 | Regionwide: Trip Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG26-282 |  | 103151 | MAG-Q(026)D | PMG2606P | Trip Reduction Program | 2026 | CMAQ | 2025 | 962347 | 0 | 0 | 962347
MAG | Highway | 20244 | Regionwide: Regional Rideshare and Telework Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG26-283 |  | 103481 | MAG-Q(026)D | PMG2606P | Regional Rideshare and Telework Program | 2026 | CMAQ | 2025 | 650000 | 0 | 0 | 650000
MAG | Highway | 28220 | Regionwide: Travel Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG26-284 |  | 103482 | MAG-Q(026)D | PMG2606P | Travel Reduction Program | 2026 | CMAQ | 2025 | 135000 | 0 | 0 | 135000
MAG | Highway | 37918 | Regionwide |  | Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-285 |  | 104370 | ----- | ----- | FHWA Funding: Flex to Transit. CAPEX Repayment. Funding transfers from FHWA to FTA. | 2026 | CMAQ | 2026 | 6857225 | 0 | 0 | 6857225
MAG | Highway | 274 | Regionwide: Active Transportation Plan Update |  | Bike/Ped | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | Yes | Yes | No | No | MAG26-540 |  | 105112 | ----- | ----- | Active Transportation Plan Update | 2026 | TA-MAG | 2025 | 900000 | 0 | 0 | 900000
MAG | Highway | 5339 | Regionwide |  | Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-580 |  | 101138 | ----- | ----- | FHWA Funding: Flex to Transit. Annual Amount Placeholder. See Program of Projects for Detail when developed. | 2026 | CMAQ | 2025 | 8764845 | 0 | 0 | 8764845
MAG | Highway | 12571 | Regionwide: Transportation and Air Quality planning and Support |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG27-280 |  | 102985 | MAG-T(026)D | PMG2603P | Transportation and Air Quality planning and support | 2027 | STBGP-MAG | 2026 | 9225000 | 0 | 557609 | 9782609
MAG | Highway | 15214 | Regionwide: Trip Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG27-282 |  | 103151 | MAG-Q(026)D | PMG2606P | Trip Reduction Program | 2027 | CMAQ | 2026 | 962347 | 0 | 0 | 962347
MAG | Highway | 20244 | Regionwide: Regional Rideshare and Telework Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG27-283 |  | 103481 | MAG-Q(026)D | PMG2606P | Regional Rideshare and Telework Program | 2027 | CMAQ | 2026 | 650000 | 0 | 0 | 650000
MAG | Highway | 28220 | Regionwide: Travel Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG27-284 |  | 103482 | MAG-Q(026)D | PMG2606P | Travel Reduction Program | 2027 | CMAQ | 2026 | 135000 | 0 | 0 | 135000
MAG | Highway | 17552 | Regionwide: PM-10 Certified Street Sweepers |  | Air Quality | N/A | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG27-285P |  | 101825 | ----- | T0561 | PM-10 Certified Street Sweepers | 2027 | CMAQ | 2027 | 1400000 | 0 | 84624 | 1484624
MAG | Highway | 12571 | Regionwide: Transportation and Air Quality planning and Support |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG28-280 |  | 102985 | ----- | ----- | Transportation and Air Quality planning and support | 2028 | STBGP-MAG | 2028 | 6582479 | 0 | 397880 | 6980359
MAG | Highway | 15214 | Regionwide: Trip Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG28-282 |  | 103151 | ----- | ----- | Trip Reduction Program | 2028 | CMAQ | 2028 | 962347 | 0 | 0 | 962347
MAG | Highway | 20244 | Regionwide: Regional Rideshare and Telework Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG28-283 |  | 103481 | ----- | ----- | Regional Rideshare and Telework Program | 2028 | CMAQ | 2028 | 650000 | 0 | 0 | 650000
MAG | Highway | 28220 | Regionwide: Travel Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG28-284 |  | 103482 | ----- | ----- | Travel Reduction Program | 2028 | CMAQ | 2028 | 135000 | 0 | 0 | 135000
MAG | Highway | 17552 | Regionwide: PM-10 Certified Street Sweepers |  | Air Quality | N/A | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG28-285P |  | 101825 | ----- | T0561 | PM-10 Certified Street Sweepers | 2028 | CMAQ | 2028 | 1400000 | 0 | 84624 | 1484624
MAG | Highway | 12571 | Regionwide: Transportation and Air Quality planning and Support |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG29-280 |  | 102985 | ----- | ----- | Transportation and Air Quality planning and support | 2029 | STBGP-MAG | 2029 | 6582479 | 0 | 397880 | 6980359
MAG | Highway | 15214 | Regionwide: Trip Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG29-282 |  | 103151 | ----- | ----- | Trip Reduction Program | 2029 | CMAQ | 2029 | 962347 | 0 | 0 | 962347
MAG | Highway | 20244 | Regionwide: Regional Rideshare and Telework Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG29-283 |  | 103481 | ----- | ----- | Regional Rideshare and Telework Program | 2029 | CMAQ | 2029 | 650000 | 0 | 0 | 650000
MAG | Highway | 28220 | Regionwide: Travel Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG29-284 |  | 103482 | ----- | ----- | Travel Reduction Program | 2029 | CMAQ | 2029 | 135000 | 0 | 0 | 135000
MAG | Highway | 17552 | Regionwide: PM-10 Certified Street Sweepers |  | Air Quality | N/A | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG29-285P |  | 101825 | ----- | T0561 | PM-10 Certified Street Sweepers | 2029 | CMAQ | 2029 | 1400000 | 0 | 84624 | 1484624
MAG | Highway | 12571 | Regionwide: Transportation and Air Quality planning and Support |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG30-280 |  | 102985 | ----- | ----- | Transportation and Air Quality planning and support | 2030 | STBGP-MAG | 2030 | 6582479 | 0 | 397880 | 6980359
MAG | Highway | 15214 | Regionwide: Trip Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG30-282 |  | 103151 | ----- | ----- | Trip Reduction Program | 2030 | CMAQ | 2030 | 962347 | 0 | 0 | 962347
MAG | Highway | 20244 | Regionwide: Regional Rideshare and Telework Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG30-283 |  | 103481 | ----- | ----- | Regional Rideshare and Telework Program | 2030 | CMAQ | 2030 | 650000 | 0 | 0 | 650000
MAG | Highway | 28220 | Regionwide: Travel Reduction Program |  | Air Quality | N/A | Maricopa | UPWP | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG30-284 |  | 103482 | ----- | ----- | Travel Reduction Program | 2030 | CMAQ | 2030 | 135000 | 0 | 0 | 135000
MAG | Highway | 17552 | Regionwide: PM-10 Certified Street Sweepers |  | Air Quality | N/A | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | MAG30-285P |  | 101825 | ----- | T0561 | PM-10 Certified Street Sweepers | 2030 | CMAQ | 2030 | 1400000 | 0 | 84624 | 1484624
MAG | Transit | 37637 | Regionwide: MAG |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | MAG26-212T |  | 101271 | ----- | ----- | §5307. Partial Apportionment Placeholder | 2026 | 5307-PMS | 2025 | 34962908 | 0 | 8740727 | 43703635
MAG | Transit | 5800 | Regionwide |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | MAG26-213T |  | 101139 | ----- | ----- | Partial FY2026 CMAQ Flex Placeholder (Bus Purchases) | 2026 | CMAQ-Flex | 2025 | 8764845 | 1546737 | 0 | 10311582
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-500T |  | 105107 | ----- | ----- | §5307. Estimated Annual Apportionment Placeholder. | 2026 | 5307-MAR | 2025 | 1809301 | 0 | 452325 | 2261626
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-501T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2026 | 5307-PGA | 2025 | 1584161 | 0 | 396040 | 1980201
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-504T |  | 105107 | ----- | ----- | §5337. Partial Apportionment Placeholder | 2026 | 5337-HI PGA | 2025 | 704271 | 0 | 176068 | 880339
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-507T |  | 105107 | ----- | ----- | §5339. Annual Apportionment Placeholder | 2026 | 5339-PGA | 2025 | 613637 | 0 | 153409 | 767046
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-509T |  | 105107 | ----- | ----- | Placeholder for PMS remaining Program Admin FY2025 5310 | 2026 | 5310-PMS | 2025 | 93425 | 0 | 23356 | 116781
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG26-510T |  | 105107 | ----- | ----- | Placeholder for PMS remaining apportionment FY 2025 5310 | 2026 | 5310-PMS | 2025 | 395259 | 0 | 98815 | 494074
MAG | Transit | 5800 | Regionwide |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | MAG26-511T |  | 101139 | ----- | ----- | Section 5339 PGA Partial Apportionment Placeholder- Detail will conclude after annual or multiyear programming | 2026 | 5339-PGA | 2024 | 473576 | 0 | 118394 | 591970
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-500T |  | 105760 | ----- | 11.7L.00 | STARS Mobility Management Position | 2026 | 5310-PMS | 2025 | 40000 | 0 | 10000 | 50000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-501T |  | 105760 | ----- | 11.7A.00 | STARS Preventative Maintenance | 2026 | 5310-PMS | 2025 | 34000 | 0 | 8500 | 42500
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-502T |  | 105760 | ----- | 11.13.04 | STARS 1 Raised Roof with Lift - E | 2026 | 5310-PMS | 2025 | 108800 | 0 | 19200 | 128000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-503T |  | 105760 | ----- | 11.7L.00 | Chandler Gilbert Arc Mobility Management Position | 2026 | 5310-PMS | 2025 | 40000 | 0 | 10000 | 50000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-504T |  | 105760 | ----- | 11.7A.00 | The Centers for Habilitation Preventative Maintenance | 2026 | 5310-PMS | 2025 | 60000 | 0 | 15000 | 75000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-505T |  | 105760 | ----- | 30.09.01 | Valley of the Sun YMCA (YOPAS) Volunteer Driver Program | 2026 | 5310-PMS | 2025 | 92152 | 0 | 92152 | 184304
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-506T |  | 105760 | ----- | 11.7L.00 | The Centers for Habilitation Mobility Management Position | 2026 | 5310-PMS | 2025 | 40000 | 0 | 10000 | 50000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-507T |  | 105760 | ----- | 11.12.04 | Chandler Gilbert Arc 1 Minivan with Ramp - R | 2026 | 5310-PMS | 2025 | 74800 | 0 | 13200 | 88000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-508T |  | 105760 | ----- | 11.7A.00 | Chandler Gilbert Arc Preventative Maintenance | 2026 | 5310-PMS | 2025 | 84466 | 0 | 21117 | 105583
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-509T |  | 105760 | ----- | 11.7A.00 | United Cerebral Palsy of Central Arizona Preventative Maintenance | 2026 | 5310-PMS | 2025 | 10004 | 0 | 2501 | 12505
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-510T |  | 105760 | ----- | 30.09.01 | NAU Center for Service and Voluteerism Volunteer Driver Program | 2026 | 5310-PMS | 2025 | 106758 | 0 | 106758 | 213516
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-511T |  | 105760 | ----- | 11.7A.00 | Foothills Caring Corps Preventative Maintenance | 2026 | 5310-PMS | 2025 | 16768 | 0 | 4192 | 20960
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-512T |  | 105760 | ----- | 11.13.04 | Foothills Caring Corps 1 Cutaway with Lift - E | 2026 | 5310-PMS | 2025 | 126650 | 0 | 22350 | 149000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-513T |  | 105760 | ----- | 11.7A.00 | Civitan Foundation Preventative Maintenance | 2026 | 5310-PMS | 2025 | 60000 | 0 | 15000 | 75000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-514T |  | 105760 | ----- | 30.09.01 | Foothills Caring Corps Volunteer Driver Program | 2026 | 5310-PMS | 2025 | 98917 | 0 | 98917 | 197834
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-515T |  | 105760 | ----- | 11.7A.00 | One Step Beyond Preventative Maintenance | 2026 | 5310-PMS | 2025 | 64532 | 0 | 16133 | 80665
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-516T |  | 105760 | ----- | 11.7A.00 | Gompers Preventative Maintenance | 2026 | 5310-PMS | 2025 | 120350 | 0 | 30088 | 150438
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-517T |  | 105760 | ----- | 11.12.04 | Civitan Foundation 3 Raised Roof with Lift - R; 2 Minivan with Ramp - R | 2026 | 5310-PMS | 2025 | 476000 | 0 | 84000 | 560000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-518T |  | 105760 | ----- | 11.13.04 | One Step Beyond 2 Minivan with Ramp - E; Raised Roof with Lift - E | 2026 | 5310-PMS | 2025 | 476000 | 0 | 84000 | 560000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-519T |  | 105760 | ----- | 11.7L.00 | Gompers Mobility Management Position | 2026 | 5310-PMS | 2025 | 40000 | 0 | 10000 | 50000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-520T |  | 105760 | ----- | 11.42.20 | Gompers Equipment | 2026 | 5310-PMS | 2025 | 43379 | 0 | 10845 | 54224
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-521T |  | 105760 | ----- | 11.7A.00 | Hacienda Preventative Maintenance | 2026 | 5310-PMS | 2025 | 40000 | 0 | 10000 | 50000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-522T |  | 105760 | ----- | 30.09.01 | Duet Volunteer Driver Program | 2026 | 5310-PMS | 2025 | 112500 | 0 | 112500 | 225000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-523T |  | 105760 | ----- | 11.13.04 | Westminster Village 1 Cutaway with Lift - E | 2026 | 5310-PMS | 2025 | 126650 | 0 | 22350 | 149000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-524T |  | 105760 | ----- | 11.7A.00 | Arizona Center for the Blind and Visually Impaired Preventative Maintenance | 2026 | 5310-PMS | 2025 | 7632 | 0 | 1908 | 9540
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-525T |  | 105760 | ----- | 30.09.01 | Aster Aging Volunteer Driver Program | 2026 | 5310-PMS | 2025 | 53180 | 0 | 53180 | 106360
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-526T |  | 105760 | ----- | 11.7A.00 | Aster Aging Preventative Maintenance | 2026 | 5310-PMS | 2025 | 4944 | 0 | 1236 | 6180
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-527T |  | 105760 | ----- | 11.7A.00 | Nobody's Perfect Preventative Maintenance | 2026 | 5310-PMS | 2025 | 14656 | 0 | 3664 | 18320
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-528T |  | 105760 | ----- | 11.13.04 | Train Em Up Ministries Minivan with Ramp - E; Raised Roof with Lift - E | 2026 | 5310-PMS | 2025 | 183600 | 0 | 32400 | 216000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-530T |  | 105760 | ----- | 11.13.04 | Glencroft 1 Minivan with Ramp - E; 1 Cutaway with Lift - E; | 2026 | 5310-PMS | 2025 | 201450 | 0 | 35550 | 237000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-531T |  | 105760 | ----- | 11.12.04 | Central Arizona Council on Developmental Disabilities 1 Cutaway with Lift -R; 1 Raised Roof with Lift - R; 1 Minivan with Ramp - R | 2026 | 5310-PMS | 2025 | 310250 | 0 | 54750 | 365000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-532T |  | 105760 | ----- | 30.09.01 | Valley of the Sun YMCA Volunteer Driver Program - YOPAS | 2026 | 5310-PGA | 2025 | 51094 | 0 | 51094 | 102188
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-533T |  | 105760 | ----- | 11.7A.00 | One Step Beyond Preventative Maintenance | 2026 | 5310-PGA | 2025 | 11388 | 0 | 2847 | 14235
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-534T |  | 105760 | ----- | 11.7L.00 | One Step Beyond Mobility Management Position | 2026 | 5310-PGA | 2025 | 40000 | 0 | 10000 | 50000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-535T |  | 105760 | ----- | 11.13.04 | One Step Beyond 3 Raised Roof with Lift - E | 2026 | 5310-PGA | 2025 | 217600 | 0 | 38400 | 256000
MAG | Transit | 115 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PNP26-536T |  | 105760 | ----- | 11.12.04 | Glencroft 2 Cutaway with Lift - R; 1 Minivan with Ramp -R | 2026 | 5310-PMS | 2025 | 328100 | 0 | 57900 | 386000
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-500T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2027 | 5307-PGA | 2026 | 5107236 | 0 | 1276809 | 6384045
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-501T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2027 | 5307-PGA | 2026 | 1702412 | 0 | 425603 | 2128015
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-502T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2027 | 5307-PMS | 2026 | 59039761 | 0 | 14759940 | 73799701
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-503T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2027 | 5310-PGA | 2026 | 1038361 | 0 | 259590 | 1297951
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-504T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2027 | 5310-PMS | 2026 | 6166004 | 0 | 1541501 | 7707505
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-505T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2027 | 5337-HI PGA | 2026 | 435465 | 0 | 108866 | 544331
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-506T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2027 | 5337-HI PMS | 2026 | 9376856 | 0 | 2344214 | 11721070
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-507T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2027 | 5337-FGM PMS | 2026 | 8564428 | 0 | 2141107 | 10705535
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-508T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2027 | 5339-PGA | 2026 | 778771 | 0 | 194693 | 973464
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-509T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2027 | 5339-PMS | 2026 | 6924592 | 0 | 1731148 | 8655740
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-510T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2027 | 5307-PMS | 2026 | 19679921 | 0 | 4919980 | 24599901
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG27-511T |  | 105107 | ----- | ----- | §5307. Estimated Annual Apportionment Placeholder. | 2027 | 5307-MAR | 2026 | 1766774 | 0 | 441694 | 2208468
MAG | Transit | 31316 | MAG Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | No | No | No | No | No | No | No | MAG27-588 |  | 105087 | ----- | ----- | FY 2027 Placeholder for P479 PTF Funding | 2027 | PTF | 2027 | 0 | 180000000 | 0 | 180000000
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-500T |  | 105107 | ----- | ----- | §5307. Estimated Annual Apportionment Placeholder. | 2028 | 5307-MAR | 2027 | 1800343 | 0 | 450086 | 2250429
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-501T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2028 | 5307-PGA | 2027 | 5204273 | 0 | 1301068 | 6505341
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-502T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2028 | 5307-PGA | 2027 | 1734758 | 0 | 433690 | 2168448
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-503T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2028 | 5307-PMS | 2027 | 60161516 | 0 | 15040379 | 75201895
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-504T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2028 | 5310-PGA | 2027 | 1058090 | 0 | 264523 | 1322613
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-505T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2028 | 5310-PMS | 2027 | 6412644 | 0 | 1603161 | 8015805
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-506T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2028 | 5337-HI PGA | 2027 | 443739 | 0 | 110935 | 554674
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-507T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2028 | 5337-HI PMS | 2027 | 9555016 | 0 | 2388754 | 11943770
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-508T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2028 | 5337-FGM PMS | 2027 | 8727152 | 0 | 2181788 | 10908940
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-509T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2028 | 5339-PGA | 2027 | 793567 | 0 | 198392 | 991959
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-510T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2028 | 5339-PMS | 2027 | 7056159 | 0 | 1764040 | 8820199
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG28-511T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2028 | 5307-PMS | 2027 | 20053839 | 0 | 5013460 | 25067299
MAG | Transit | 31316 | MAG Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | No | No | No | No | No | No | No | MAG28-588 |  | 105087 | ----- | ----- | FY 2028 Placeholder for P479 PTF Funding | 2028 | PTF | 2028 | 0 | 180000000 | 0 | 180000000
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-500T |  | 105107 | ----- | ----- | §5307. Estimated Annual Apportionment Placeholder. | 2029 | 5307-MAR | 2028 | 1834550 | 0 | 458638 | 2293188
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-501T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2029 | 5307-PGA | 2028 | 5303155 | 0 | 1325789 | 6628944
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-502T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2029 | 5307-PGA | 2028 | 1767718 | 0 | 441930 | 2209648
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-503T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2029 | 5307-PMS | 2028 | 20233386 | 0 | 5058347 | 25291733
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-504T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2029 | 5310-PGA | 2028 | 1078194 | 0 | 269549 | 1347743
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-505T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2029 | 5310-PMS | 2028 | 6669150 | 0 | 1667288 | 8336438
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-506T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2029 | 5337-HI PGA | 2028 | 452170 | 0 | 113043 | 565213
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-507T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2029 | 5337-HI PMS | 2028 | 9736561 | 0 | 2434140 | 12170701
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-508T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2029 | 5337-FGM PMS | 2028 | 8892968 | 0 | 2223242 | 11116210
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-509T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2029 | 5339-PGA | 2028 | 808645 | 0 | 202161 | 1010806
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-510T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2029 | 5339-PMS | 2028 | 7190226 | 0 | 1797557 | 8987783
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG29-511T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2029 | 5307-PMS | 2028 | 20434862 | 0 | 5108716 | 25543578
MAG | Transit | 31316 | MAG Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | No | No | No | No | No | No | No | MAG29-588 |  | 105087 | ----- | ----- | FY 2029 Placeholder for P479 PTF Funding | 2029 | PTF | 2029 | 0 | 180000000 | 0 | 180000000
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-500T |  | 105107 | ----- | ----- | §5307. Estimated Annual Apportionment Placeholder. | 2030 | 5307-MAR | 2029 | 1869406 | 0 | 467352 | 2336758
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-501T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2030 | 5307-PGA | 2029 | 5403914 | 0 | 1350979 | 6754893
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-502T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2030 | 5307-PGA | 2029 | 1801305 | 0 | 450326 | 2251631
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-503T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2030 | 5307-PMS | 2029 | 21398173 | 0 | 5349543 | 26747716
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-504T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2030 | 5310-PGA | 2029 | 1098679 | 0 | 274670 | 1373349
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-505T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2030 | 5310-PMS | 2029 | 6935916 | 0 | 1733979 | 8669895
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-506T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2030 | 5337-HI PGA | 2028 | 460761 | 0 | 115190 | 575951
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-507T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2030 | 5337-HI PMS | 2029 | 9921556 | 0 | 2480389 | 12401945
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-508T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2030 | 5337-FGM PMS | 2029 | 10671561 | 0 | 2667890 | 13339451
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-509T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2030 | 5339-PGA | 2029 | 824009 | 0 | 206002 | 1030011
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-510T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2030 | 5339-PMS | 2029 | 7326840 | 0 | 1831710 | 9158550
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG30-512T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2030 | 5307-PMS | 2029 | 20823124 | 0 | 5205781 | 26028905
MAG | Transit | 31316 | MAG Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | No | No | No | No | No | No | No | MAG30-588 |  | 105087 | ----- | ----- | FY 2030 Placeholder for P479 PTF Funding | 2030 | PTF | 2030 | 0 | -540000000 | 0 | -540000000
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-500T |  | 105107 | ----- | ----- | §5307. Estimated Annual Apportionment Placeholder. | 2031 | 5307-MAR | 2030 | 1058090 | 0 | 264523 | 1322613
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-501T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2031 | 5307-PGA | 2030 | 5506589 | 0 | 1376647 | 6883236
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-502T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2031 | 5307-PGA | 2030 | 1835530 | 0 | 458883 | 2294413
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-503T |  | 105107 | ----- | ----- | §5307. Estimated Annual Partial Apportionment Placeholder. | 2031 | 5307-PMS | 2030 | 71119661 | 0 | 17779915 | 88899576
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-504T |  | 105107 | ----- | ----- | §5307. Preventive Maintenance -Estimated Annual Partial Apportionment Placeholder. | 2031 | 5307-PMS | 2030 | 23706554 | 0 | 5926639 | 29633193
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-505T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2031 | 5310-PGA | 2030 | 1119554 | 0 | 279889 | 1399443
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-506T |  | 105107 | ----- | ----- | §5310. Estimated Annual Apportionment Placeholder. | 2031 | 5310-PMS | 2030 | 7213352 | 0 | 1803338 | 9016690
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-507T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2031 | 5337-HI PGA | 2030 | 469516 | 0 | 117379 | 586895
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-508T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2031 | 5337-HI PMS | 2030 | 10110065 | 0 | 2527516 | 12637581
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-509T |  | 105107 | ----- | ----- | §5337. Estimated Annual Apportionment Placeholder. | 2031 | 5337-FGM PMS | 2030 | 10874321 | 0 | 2718580 | 13592901
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-510T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2031 | 5339-PGA | 2030 | 839666 | 0 | 209917 | 1049583
MAG | Transit | 7305 | Regionwide |  | Transit Other | N/A | Maricopa | 479-TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | Yes | No | MAG31-511T |  | 105107 | ----- | ----- | §5339. Estimated Annual Apportionment Placeholder. | 2031 | 5339-PMS | 2030 | 7466050 | 0 | 1866513 | 9332563
Maricopa (City) | Highway | 14188 | Farrell Rd: Hartman Rd to Murphy Rd | Local | Street | OCT-DEC 2027 | Pinal | Other | 1 | 0 | 2 | No | No | No | No | No | No | Yes | No | MAR23-231C |  | 104165 | ----- | ----- | Paving unpaved road (Construction) | 2026 | Private | 2026 | 0 | 0 | 1913300 | 1913300
Maricopa (City) | Highway | 46583 | Farrell Rd: Hartman Rd to Murphy Rd (North Side) | Local | Street | OCT-DEC 2027 | Pinal | Other | 1 | 2 | 3 | No | No | No | No | Yes | No | No | No | MAR24-234C |  | 104694 | ----- | ----- | Roadway widening | 2026 | Private | 2026 | 0 | 0 | 6000000 | 6000000
Maricopa (City) | Highway | 33987 | Pedestrian Bridge over the Union Pacific Railroad along the Maricopa Road alignment | Principal Arterial - Other | Bike/Ped | OCT-DEC 2026 | Pinal | Other | 0 | 0 | 0 | Yes | No | No | No | No | Yes | Yes | No | MAR24-240C |  | 103958 | MAR-0(214)T | T0458 | Construct pedestrian bridge | 2026 | CDS | 2024 | 2700000 | 0 | 2300000 | 5000000
Maricopa (City) | Highway | 21297 | Hartman Rd: Farrell Rd to Steen Rd | Major Collector | Street | OCT-DEC 2027 | Pinal | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | MAR25-234D |  | 104367 | ----- | ----- | Roadway widening (design) | 2026 | Private | 2026 | 0 | 0 | 500000 | 500000
Maricopa (City) | Highway | 27615 | Honeycutt Rd: 0.5 mile West of Santa Cruz Wash to Santa Cruz Wash (South Side) | Minor Arterial | Street | OCT-DEC 2027 | Pinal | Other | 0.5 | 2 | 3 | No | No | No | No | Yes | No | No | No | MAR25-235D |  | 104368 | ----- | ----- | Roadway widening (design) | 2026 | Private | 2026 | 0 | 0 | 500000 | 500000
Maricopa (City) | Highway | 19561 | Hartman Rd: Honeycutt Rd to Bowlin Rd | Minor Arterial | Street | APR-JUN 2029 | Pinal | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | MAR28-230C |  | 105073 | ----- | ----- | Roadway widening (Construction) | 2028 | Local | 2028 | 0 | 0 | 1950000 | 1950000
Maricopa (City) | Highway | 19561 | Hartman Rd: Honeycutt Rd to Bowlin Rd | Minor Arterial | Street | APR-JUN 2029 | Pinal | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | MAR28-230D |  | 105073 | ----- | ----- | Roadway widening (Design) | 2028 | Local | 2028 | 0 | 0 | 325000 | 325000
Maricopa (City) | Transit | 22307 | Maricopa (City) Citywide |  | Transit Bus | N/A | Pinal | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | MAR26-510T |  | 105346 | ----- | ----- | FY2024 AZ-Flex Placeholder | 2026 | TA-AZ-Flex | 2024 | 38303 | 0 | 9576 | 47879
Maricopa (City) | Transit | 22307 | Maricopa (City) Citywide |  | Transit Bus | N/A | Pinal | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | MAR26-511T |  | 105346 | ----- | ----- | Placeholder | 2026 | TA-AZ-Flex | 2025 | 41921 | 0 | 10480 | 52401
Maricopa County | Highway | 8868 | McKellips Rd: Loop 101 (Pima Fwy) to SRP-MIC/Alma School Rd | Principal Arterial - Other | Street | JUL-SEP 2025 | Maricopa | ALCP | 2 | 4 | 4 | No | No | No | No | Yes | No | No | No | MMA20-121RRB |  | 101130 | MMA-0(217)D | SS881 | Acquisition of right-of-way for Roadway Improvements | 2026 | RARF | 2026 | 0 | 1610000 | -1610000 | 0
Maricopa County | Highway | 21834 | Olive Ave: SR303 to Sarival Ave | Minor Arterial | Street | APR-JUN 2027 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | MMA20-804R |  | 101333 | ----- | ----- | Widening, capacity and safety improvement (Construction) | 2026 | Local | 2026 | 0 | 0 | 8663000 | 8663000
Maricopa County | Highway | 17477 | Olive Ave: Sarival Ave to Reems Rd | Minor Arterial | Street | APR-JUN 2027 | Maricopa | Other | 1.4 | 2 | 4 | No | No | No | No | Yes | No | No | No | MMA21-801 | TT0562 | 101346 | ----- | ----- | Widening, capacity and safety improvement (Construction) | 2026 | Local | 2026 | 0 | 0 | 8663000 | 8663000
Maricopa County | Highway | 4620 | Northern Parkway: 103rd Ave to 91st Ave | Principal Arterial - Other | Street | APR-JUN 2028 | Maricopa | ALCP | 1.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MMA24-112CZ |  | 101045 | MMA-0(281)D | T0233 | Construct Roadway Widening (Reimb) | 2026 | STBGP >200 PHX-MESA | 2026 | 40089299.42 | 0 | -40089299.42 | 0
Maricopa County | Highway | 18552 | Gilbert Road Bridge over the Salt River | Minor Arterial | Street | OCT-DEC 2024 | Maricopa | ALCP | 1.6 | 4 | 4 | No | No | No | No | Yes | No | No | No | MMA25-103CRB2 |  | 101341 | ----- | ----- | Construct Bridge and Roadway Improvements | 2026 | RARF | 2026 | 0 | 2531805.96 | -2531805.96 | 0
Maricopa County | Highway | 8868 | McKellips Rd: Loop 101 (Pima Fwy) to SRP-MIC/Alma School Rd | Principal Arterial - Other | Street | JUL-SEP 2025 | Maricopa | ALCP | 2 | 4 | 4 | No | No | No | No | Yes | No | No | No | MMA25-121CRB |  | 101130 | ----- | SS881 | Construct Roadway Improvements | 2026 | RARF | 2026 | 0 | 5936121.1 | -5936121.1 | 0
Maricopa County | Highway | 8868 | McKellips Rd: Loop 101 (Pima Fwy) to SRP-MIC/Alma School Rd | Principal Arterial - Other | Street | JUL-SEP 2025 | Maricopa | ALCP | 2 | 4 | 4 | No | No | No | No | Yes | No | No | No | MMA25-121DRB |  | 101130 | ----- | SS881 | Design Roadway Improvements | 2026 | RARF | 2026 | 0 | 242259.59 | -242259.59 | 0
Maricopa County | Highway | 36693 | Various Locations - Maricopa County |  | ITS | OCT-DEC 2027 | Maricopa | SM+O | 0 | 0 | 0 | No | No | No | No | Yes | No | Yes | No | MMA25-260C | TE083 | 103937 | ----- | ----- | L101 ICM Readiness (Procurement) | 2026 | CMAQ | 2026 | 860488 | 0 | 52012 | 912500
Maricopa County | Highway | 36693 | Various Locations - Maricopa County |  | ITS | OCT-DEC 2027 | Maricopa | SM+O | 0 | 0 | 0 | No | No | No | No | Yes | No | Yes | No | MMA25-260C1 | TE083 | 103937 | ----- | ----- | L101 ICM Readiness (Construction) | 2026 | CMAQ | 2026 | 843042 | 0 | 50958 | 894000
Maricopa County | Highway | 45336 | Northern Parkway: Agua Fria to 103rd Ave | Principal Arterial - Other | Street | APR-JUN 2027 | Maricopa | ALCP | 2.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | MMA26-124CRB |  | 101300 | MMA-0(280)D | T0188 | Roadway reconstruction (construction) | 2026 | STBGP-MAG | 2025 | 11423196.3 | 0 | 4895655.56 | 16318851.86
Maricopa County | Highway | 29289 | Wintersburg Rd: Van Buren St to Salome Hwy | Major Collector | Safety | APR-JUN 2027 | Maricopa | 5-year | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | MMA26-270C |  | 103604 | MMA-0(298)D | T0632 | Construct Passing Lane, shoulder Widening and Center and Edge line | 2026 | HSIP-AZ | 2026 | 2449461 | 0 | 147381 | 2596842
Maricopa County | Highway | 11374 | Olive Ave: Reems Rd to Litchfield Rd | Minor Collector | Street | OCT-DEC 2028 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | MMA25-230C |  | 104163 | ----- | ----- | Roadway widening | 2027 | Local | 2027 | 0 | 0 | 11000000 | 11000000
Maricopa County | Highway | 8868 | McKellips Rd: Loop 101 (Pima Fwy) to SRP-MIC/Alma School Rd | Principal Arterial - Other | Street | JUL-SEP 2025 | Maricopa | ALCP | 2 | 4 | 4 | No | No | No | No | Yes | No | No | No | MMA27-500S |  | 101130 | ----- | SS881 | Project Savings for Roadway Improvements | 2027 | RARF | 2027 | 0 | 14567434 | 0 | 14567434
Mesa | Highway | 24453 | Power Rd: East Maricopa Floodway to Santan Fwy/Loop 202 | Principal Arterial - Other | Street | JUL-SEP 2031 | Maricopa | ALCP | 3.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES20-138DRB |  | 101171 | ----- | ----- | Design Roadway Widening | 2026 | RARF | 2026 | 0 | 263077.4 | -263077.4 | 0
Mesa | Highway | 35215 | Broadway Rd: Country Club Dr to Mesa Dr | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES20-159DRB |  | 101260 | ----- | ----- | Design roadway improvements | 2026 | RARF | 2026 | 0 | 750000 | -750000 | 0
Mesa | Highway | 35215 | Broadway Rd: Country Club Dr to Mesa Dr | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES20-159DZ |  | 101260 | ----- | ----- | Design roadway improvements | 2026 | Local | 2026 | 0 | 0 | 1878524 | 1878524
Mesa | Highway | 35215 | Broadway Rd: Country Club Dr to Mesa Dr | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES20-159RRB |  | 101260 | ----- | ----- | Acquisition of right-of-way for roadway improvements | 2026 | RARF | 2026 | 0 | 350000 | -350000 | 0
Mesa | Highway | 35215 | Broadway Rd: Country Club Dr to Mesa Dr | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES20-159RWZ |  | 101260 | ----- | ----- | Acquisition of right-of-way for roadway improvements | 2026 | Local | 2026 | 0 | 0 | 738105 | 738105
Mesa | Highway | 24453 | Power Rd: East Maricopa Floodway to Santan Fwy/Loop 202 | Principal Arterial - Other | Street | JUL-SEP 2031 | Maricopa | ALCP | 3.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES21-138RRB |  | 101171 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 1534353.1 | -1534353.1 | 0
Mesa | Highway | 49255 | Stapley Dr at University Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 1.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES21-152CRB |  | 101310 | ----- | ----- | Construct intersection improvement | 2026 | RARF | 2026 | 0 | 5633160.78 | -5633160.78 | 0
Mesa | Highway | 49255 | Stapley Dr at University Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 1.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES21-152SAVZ |  | 101310 | ----- | ----- | Construct intersection improvement | 2026 | RARF | 2026 | 0 | 6584625.78 | 612655.36 | 7197281.14
Mesa | Highway | 35215 | Broadway Rd: Country Club Dr to Mesa Dr | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES21-159CRB |  | 101260 | ----- | ----- | Construct roadway improvements | 2026 | RARF | 2026 | 0 | 4539797.24 | -4539797.24 | 0
Mesa | Highway | 35215 | Broadway Rd: Country Club Dr to Mesa Dr | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES21-159CZ |  | 101260 | ----- | ----- | Construct roadway improvements | 2026 | Local | 2026 | 0 | 0 | 16310824 | 16310824
Mesa | Highway | 24453 | Power Rd: East Maricopa Floodway to Santan Fwy/Loop 202 | Principal Arterial - Other | Street | JUL-SEP 2031 | Maricopa | ALCP | 3.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES22-138CRB |  | 101171 | ----- | ----- | Construct Roadway Widening | 2026 | RARF | 2026 | 0 | 5824201.87 | -5824201.87 | 0
Mesa | Highway | 24453 | Power Rd: East Maricopa Floodway to Santan Fwy/Loop 202 | Principal Arterial - Other | Street | JUL-SEP 2031 | Maricopa | ALCP | 3.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES22-138CZ |  | 101171 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 26507883 | 26507883
Mesa | Highway | 44054 | Broadway Rd: Mesa Dr to Stapley Dr | Minor Arterial | Street | OCT-DEC 2025 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES22-160CRB |  | 101296 | ----- | ----- | Construct roadway improvements | 2026 | RARF | 2026 | 0 | 15099675.1 | -15099675.1 | 0
Mesa | Highway | 19918 | Mesa Dr: US-60 (Superstition Fwy) to Southern | Principal Arterial - Other | Street | APR-JUN 2014 | Maricopa | ALCP | 1 | 4 | 5 | No | No | No | No | Yes | No | No | No | MES23-126RRB |  | 104084 | ----- | ----- | Acquisition of Right-of-Way for Roadway Widening | 2026 | RARF | 2026 | 0 | 36384.7 | -36384.7 | 0
Mesa | Highway | 651 | Southern Ave at Stapley Dr | Principal Arterial - Other | Street | APR-JUN 2022 | Maricopa | ALCP | 1 | 4 | 6 | Yes | No | No | No | Yes | No | No | No | MES23-150RRB |  | 100491 | MES-0(224)D | SH544 | Acquisition of right-of-way for intersection improvement | 2026 | RARF | 2026 | 0 | 1296187.26 | -1296187.26 | 0
Mesa | Highway | 30976 | McKellips Rd: East of Sossaman Rd to Crismon | Principal Arterial - Other | Street | APR-JUN 2030 | Maricopa | ALCP | 3 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES23-162DZ |  | 101901 | ----- | ----- | Design roadway widening | 2026 | RARF | 2026 | 0 | 1204515 | 516220.64 | 1720735.64
Mesa | Highway | 20412 | Ellsworth Rd and Williams Field Rd Bridge | Principal Arterial - Other | Street | JAN-MAR 2024 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES23-166RRB |  | 103304 | ----- | ----- | Acquisition of right-of-way for new roadway | 2026 | RARF | 2026 | 0 | 176648.51 | -176648.51 | 0
Mesa | Highway | 3137 | Elliot Road: Eastern Maricopa Floodway (EMF) to Ellsworth Rd | Minor Arterial | Street | APR-JUN 2027 | Maricopa | ALCP | 2.7 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES23-168RRB |  | 103022 | MES-0(239)D | T0359 | Acquisition of right-of-way for roadway widening | 2026 | STBGP >200 PHX-MESA | 2025 | 1730542.8 | 0 | -1730542.8 | 0
Mesa | Highway | 10937 | SR24 Arterial Improvements | Minor Arterial | Street | APR-JUN 2022 | Maricopa | ALCP | 3 | 0 | 4 | No | No | No | No | Yes | No | No | Yes | MES23-801SAVZ |  | 102005 | ----- | ----- | Project Savings | 2026 | STBGP >200 PHX-MESA | 2026 | 810622 | 0 | 0 | 810622
Mesa | Highway | 13167 | Mesa Dr: 8th Avenue to Main Street | Principal Arterial - Other | Street | JAN-MAR 2022 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES24-130RRB |  | 101158 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 145854.57 | -145854.57 | 0
Mesa | Highway | 20065 | Ray Rd: SR24 at Ellsworth Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 0 | 6 | No | No | No | No | Yes | No | No | No | MES24-156CRB |  | 102097 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 5109490.08 | -5109490.08 | 0
Mesa | Highway | 20065 | Ray Rd: SR24 at Ellsworth Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 0 | 6 | No | No | No | No | Yes | No | No | No | MES24-156RRB |  | 102097 | ----- | ----- | Acquisition of right-of-way for new roadway | 2026 | RARF | 2026 | 0 | 511975.85 | -511975.85 | 0
Mesa | Highway | 20065 | Ray Rd: SR24 at Ellsworth Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 0 | 6 | No | No | No | No | Yes | No | No | No | MES24-156SAV |  | 102097 | ----- | ----- | Project Savings | 2026 | RARF | 2026 | 0 | 2118626.95 | -2118626.95 | 0
Mesa | Highway | 30976 | McKellips Rd: East of Sossaman Rd to Crismon | Principal Arterial - Other | Street | APR-JUN 2030 | Maricopa | ALCP | 3 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES24-162RWZ |  | 101901 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 3855194 | 1652226.17 | 5507420.17
Mesa | Highway | 47625 | Signal Butte Rd: Broadway Rd to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 4 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES24-165CZ |  | 101903 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 10504434 | 10504434
Mesa | Highway | 47625 | Signal Butte Rd: Broadway Rd to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 4 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES24-165DZ |  | 101903 | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 2412128 | 2412128
Mesa | Highway | 47625 | Signal Butte Rd: Broadway Rd to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 4 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES24-165RZ |  | 101903 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 5234275 | 5234275
Mesa | Highway | 3137 | Elliot Road: Eastern Maricopa Floodway (EMF) to Ellsworth Rd | Minor Arterial | Street | APR-JUN 2027 | Maricopa | ALCP | 2.7 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES24-168CZ |  | 103022 | MES-0(239)D | T0359 | Construct Roadway Widening (AC) | 2026 | Local | 2026 | 0 | 0 | 30685174 | 30685174
Mesa | Highway | 48743 | Dobson Rd at University Dr | Principal Arterial - Other | Street | APR-JUN 2027 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES24-169DRB |  | 103403 | ----- | ----- | Design intersection improvement | 2026 | RARF | 2026 | 0 | 456831.23 | -456831.23 | 0
Mesa | Highway | 48743 | Dobson Rd at University Dr | Principal Arterial - Other | Street | APR-JUN 2027 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES24-169DZ |  | 103403 | ----- | ----- | Design intersection improvement | 2026 | Local | 2026 | 0 | 0 | 763468 | 763468
Mesa | Highway | 37757 | Ellsworth Rd: Posada Ave to Prairie Ave | Principal Arterial - Other | Street | APR-JUN 2025 | Maricopa | ALCP | 0.25 | 4 | 5 | No | No | No | No | Yes | No | No | No | MES24-174SAV |  | 103369 | ----- | ----- | Project Savings | 2026 | RARF | 2026 | 0 | 4490455.37 | 0 | 4490455.37
Mesa | Highway | 19959 | Mountain Rd: SR 24 to Pecos Rd | Major Collector | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES24-175DZ |  | 104113 | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 653788.8 | 653788.8
Mesa | Highway | 19959 | Mountain Rd: SR 24 to Pecos Rd | Major Collector | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES24-175RWZ |  | 104113 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 12000 | 12000
Mesa | Highway | 12612 | Sossaman Rd: Velocity Way to Germann Rd | Major Collector | Street | JAN-MAR 2030 | Maricopa | ALCP | 1.4 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES24-176DRB |  | 104114 | ----- | ----- | Design roadway widening | 2026 | RARF | 2026 | 0 | 963164.58 | 412784.82 | 1375949.4
Mesa | Highway | 12612 | Sossaman Rd: Velocity Way to Germann Rd | Major Collector | Street | JAN-MAR 2030 | Maricopa | ALCP | 1.4 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES24-176RWB |  | 104114 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 54715.5 | 23449.5 | 78165
Mesa | Highway | 13167 | Mesa Dr: 8th Avenue to Main Street | Principal Arterial - Other | Street | JAN-MAR 2022 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES25-130CRB2 |  | 101158 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 381201.84 | -381201.84 | 0
Mesa | Highway | 24453 | Power Rd: East Maricopa Floodway to Santan Fwy/Loop 202 | Principal Arterial - Other | Street | JUL-SEP 2031 | Maricopa | ALCP | 3.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-138DRB |  | 101171 | ----- | ----- | Pre-Design/Design of roadway widening | 2026 | RARF | 2026 | 0 | 120339.17 | -120339.17 | 0
Mesa | Highway | 49255 | Stapley Dr at University Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 1.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES25-152DRB |  | 101310 | ----- | ----- | Design intersection improvement | 2026 | RARF | 2026 | 0 | 194558.55 | -194558.55 | 0
Mesa | Highway | 49255 | Stapley Dr at University Dr | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 1.5 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES25-152RRB |  | 101310 | ----- | ----- | Acquisition of right-of-way for intersection improvement | 2026 | RARF | 2026 | 0 | 1551871.11 | -1551871.11 | 0
Mesa | Highway | 4940 | Val Vista Dr: US-60 to Pueblo | Minor Arterial | Street | JUL-SEP 2026 | Maricopa | ALCP | 1.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-153CRB |  | 101049 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 6596918.77 | -6596918.77 | 0
Mesa | Highway | 4940 | Val Vista Dr: US-60 to Pueblo | Minor Arterial | Street | JUL-SEP 2026 | Maricopa | ALCP | 1.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-153RRB |  | 101049 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 284497.8 | -284497.8 | 0
Mesa | Highway | 17391 | Elliot Rd: Power Road to Eastern Maricopa Floodway (EMF) | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 0.4 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES25-154CRB |  | 103401 | ----- | ----- | Acquisition of right-of-way for Roadway Widening | 2026 | RARF | 2026 | 0 | 1388690.52 | 595153.08 | 1983843.6
Mesa | Highway | 20065 | Ray Rd: SR24 at Ellsworth Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 0 | 6 | No | No | No | No | Yes | No | No | No | MES25-156DRB |  | 102097 | ----- | ----- | Design new roadway | 2026 | RARF | 2026 | 0 | 268624.68 | -268624.68 | 0
Mesa | Highway | 44054 | Broadway Rd: Mesa Dr to Stapley Dr | Minor Arterial | Street | OCT-DEC 2025 | Maricopa | ALCP | 1 | 4 | 4 | No | No | No | No | Yes | No | No | No | MES25-160RRB |  | 101296 | ----- | ----- | Acquisition of right-of-way for roadway improvements | 2026 | RARF | 2026 | 0 | 247134.05 | -247134.05 | 0
Mesa | Highway | 313 | Signal Butte Rd: Williams Field Rd to Germann Rd | Principal Arterial - Other | Street | JAN-MAR 2023 | Maricopa | ALCP | 2 | 0 | 6 | No | No | No | No | Yes | No | No | No | MES25-161SAVZ |  | 103370 | ----- | ----- | Project Savings | 2026 | RARF | 2026 | 0 | 2578861.3 | -2578861.3 | 0
Mesa | Highway | 313 | Signal Butte Rd: Williams Field Rd to Germann Rd | Principal Arterial - Other | Street | JAN-MAR 2023 | Maricopa | ALCP | 2 | 0 | 6 | No | No | No | No | Yes | No | No | No | MES25-161SAVZ2 |  | 103370 | ----- | ----- | Construct new roadway (Savings) | 2026 | STBGP-MAG | 2026 | 3171006.6 | 0 | 2990259.22 | 6161265.82
Mesa | Highway | 30976 | McKellips Rd: East of Sossaman Rd to Crismon | Principal Arterial - Other | Street | APR-JUN 2030 | Maricopa | ALCP | 3 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES25-162CZ |  | 101901 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 7223599 | 2992261 | 10215860
Mesa | Highway | 45554 | McKellips Rd: Crismon Rd to Meridian Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 2 | 0 | 4 | No | No | No | No | Yes | No | No | No | MES25-164CZ |  | 103234 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 6578098 | 6578098
Mesa | Highway | 20412 | Ellsworth Rd and Williams Field Rd Bridge | Principal Arterial - Other | Street | JAN-MAR 2024 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-166CRB2 |  | 103304 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 887533.42 | 508895.97 | 1396429.39
Mesa | Highway | 20412 | Ellsworth Rd and Williams Field Rd Bridge | Principal Arterial - Other | Street | JAN-MAR 2024 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-166CRB3 |  | 103304 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 299890.51 | -299890.51 | 0
Mesa | Highway | 12820 | Sossaman Rd: Ray Rd to Warner Rd | Principal Arterial - Other | Street | APR-JUN 2025 | Maricopa | ALCP | 1 | 0 | 4 | No | No | No | No | Yes | No | No | No | MES25-167CRB |  | 102118 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 4244569.44 | -4244569.44 | 0
Mesa | Highway | 12820 | Sossaman Rd: Ray Rd to Warner Rd | Principal Arterial - Other | Street | APR-JUN 2025 | Maricopa | ALCP | 1 | 0 | 4 | No | No | No | No | Yes | No | No | No | MES25-167RRB |  | 102118 | ----- | ----- | Acquisition of right-of-way for new roadway | 2026 | RARF | 2026 | 0 | 459795.5 | -459795.5 | 0
Mesa | Highway | 3137 | Elliot Road: Eastern Maricopa Floodway (EMF) to Ellsworth Rd | Minor Arterial | Street | APR-JUN 2027 | Maricopa | ALCP | 2.7 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES25-168CRB |  | 103022 | MES-0(239)D | T0359 | Construct Roadway Widening (Reimb.) | 2026 | STBGP >200 PHX-MESA | 2026 | 20458374.41 | 0 | -20458374.41 | 0
Mesa | Highway | 3137 | Elliot Road: Eastern Maricopa Floodway (EMF) to Ellsworth Rd | Minor Arterial | Street | APR-JUN 2027 | Maricopa | ALCP | 2.7 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES25-168SAV |  | 103022 | MES-0(239)D | T0359 | Project Savings (Reimb.) | 2026 | STBGP-MAG | 2026 | 321147.04 | 0 | -321147.04 | 0
Mesa | Highway | 48743 | Dobson Rd at University Dr | Principal Arterial - Other | Street | APR-JUN 2027 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-169CRB |  | 103403 | ----- | ----- | Construct intersection improvement | 2026 | RARF | 2026 | 0 | 3023950.12 | -3023950.12 | 0
Mesa | Highway | 48743 | Dobson Rd at University Dr | Principal Arterial - Other | Street | APR-JUN 2027 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-169CZ |  | 103403 | ----- | ----- | Construct intersection improvement | 2026 | Local | 2026 | 0 | 0 | 5053705 | 5053705
Mesa | Highway | 48743 | Dobson Rd at University Dr | Principal Arterial - Other | Street | APR-JUN 2027 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-169RRB |  | 103403 | ----- | ----- | Acquisition of right-of-way for intersection improvement | 2026 | RARF | 2026 | 0 | 1439975.72 | -1439975.72 | 0
Mesa | Highway | 48743 | Dobson Rd at University Dr | Principal Arterial - Other | Street | APR-JUN 2027 | Maricopa | ALCP | 0.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-169RWZ |  | 103403 | ----- | ----- | Acquisition of right-of-way for intersection improvement | 2026 | Local | 2026 | 0 | 0 | 2406526 | 2406526
Mesa | Highway | 44292 | Ellsworth Rd: Germann to Ray | Principal Arterial - Other | Street | JUL-SEP 2026 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | Yes | MES25-172CZ |  | 102114 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 972229.05 | 540999.86 | 1513228.91
Mesa | Highway | 31669 | Williams Field Rd: SR24 to Ellsworth | Principal Arterial - Other | Street | OCT-DEC 2031 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES25-173CZ |  | 103305 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 11150526 | 11150526
Mesa | Highway | 19959 | Mountain Rd: SR 24 to Pecos Rd | Major Collector | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES25-175CZ |  | 104113 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 6364941.45 | 6364941.45
Mesa | Highway | 12612 | Sossaman Rd: Velocity Way to Germann Rd | Major Collector | Street | JAN-MAR 2030 | Maricopa | ALCP | 1.4 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES25-176CRB |  | 104114 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 10578196.44 | 4533512.76 | 15111709.2
Mesa | Highway | 4940 | Val Vista Dr: US-60 to Pueblo | Minor Arterial | Street | JUL-SEP 2026 | Maricopa | ALCP | 1.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES26-153CRB |  | 101049 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 4414989.77 | -4414989.77 | 0
Mesa | Highway | 17391 | Elliot Rd: Power Road to Eastern Maricopa Floodway (EMF) | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 0.4 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-154CRB |  | 103401 | ----- | ----- | Construct Roadway Widening | 2026 | RARF | 2026 | 0 | 3712140.56 | 1590917.38 | 5303057.94
Mesa | Highway | 30866 | Crismon Rd: Broadway to Guadalupe | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES26-168CZ |  | 103176 | ----- | ----- | Construct roadway widening | 2026 | Private | 2026 | 0 | 0 | 15137910 | 15137910
Mesa | Highway | 30866 | Crismon Rd: Broadway to Guadalupe | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES26-168DZ |  | 103176 | ----- | ----- | Design roadway widening | 2026 | Private | 2026 | 0 | 0 | 1791445 | 1791445
Mesa | Highway | 30866 | Crismon Rd: Broadway to Guadalupe | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES26-168RWZ |  | 103176 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Private | 2026 | 0 | 0 | 6035529 | 6035529
Mesa | Highway | 38619 | Hawes Rd: Elliot to Santan | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1.25 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-170CZ |  | 101231 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 1020000 | 1020000
Mesa | Highway | 38619 | Hawes Rd: Elliot to Santan | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1.25 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-170RWZ |  | 101231 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 5000000 | 5000000
Mesa | Highway | 31669 | Williams Field Rd: SR24 to Ellsworth | Principal Arterial - Other | Street | OCT-DEC 2031 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES26-173CRB |  | 103305 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 1000000 | -1000000 | 0
Mesa | Highway | 19959 | Mountain Rd: SR 24 to Pecos Rd | Major Collector | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES26-175CRB |  | 104113 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 4455459.02 | -4455459.02 | 0
Mesa | Highway | 19959 | Mountain Rd: SR 24 to Pecos Rd | Major Collector | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES26-175DRB |  | 104113 | ----- | ----- | Design roadway widening | 2026 | RARF | 2026 | 0 | 457652.16 | -457652.16 | 0
Mesa | Highway | 19959 | Mountain Rd: SR 24 to Pecos Rd | Major Collector | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES26-175RRB |  | 104113 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 8400 | -8400 | 0
Mesa | Highway | 19959 | Mountain Rd: SR 24 to Pecos Rd | Major Collector | Street | JAN-MAR 2028 | Maricopa | ALCP | 0.5 | 2 | 4 | No | No | No | No | Yes | No | No | No | MES26-175SAV |  | 104113 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 4566210.46 | -4566210.46 | 0
Mesa | Highway | 29874 | City of Mesa: Charging and Fueling Infrastructure Discretionary Grant Project |  | Other | OCT-DEC 2030 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | MES26-280 |  | 104664 | ----- | ----- | Install 48 electric vehicle charging ports and charging docks for e-bikes and e-scooters and install solar canopies. | 2026 | CFI | 2024 | 11898571 | 0 | 2974644 | 14873215
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-500DZ |  | 103386 | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 995095 | 995095
Mesa | Highway | 29678 | Country Club Dr at University Dr | Principal Arterial - Other | Street | APR-JUN 2031 | Maricopa | ALCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES26-500PDZ |  | 104075 | ----- | ----- | Predesign for intersection improvement | 2026 | RARF | 2026 | 0 | 67396.75 | -67396.75 | 0
Mesa | Highway | 4949 | Hawes Rd: Broadway to US60 | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-500RWZ |  | 103385 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 3074119.45 | 3074119.45
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-501DZ |  | 103386 | ----- | ----- | Design roadway widening | 2026 | RARF | 2026 | 0 | 696097.71 | -696097.71 | 0
Mesa | Highway | 29678 | Country Club Dr at University Dr | Principal Arterial - Other | Street | APR-JUN 2031 | Maricopa | ALCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES26-501PDZ |  | 104075 | ----- | ----- | Pre-Design intersection improvement | 2026 | Local | 2026 | 0 | 0 | 136819 | 136819
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-502RWZ |  | 103386 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 2088293.18 | -2088293.18 | 0
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-503RWZ |  | 103386 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 2983810 | 2983810
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-505CZ |  | 103386 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 4323450.9 | -4323450.9 | 0
Mesa | Highway | 12830 | Crismon Rd: Elliot Rd to Guadalupe Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 0.3 | 0 | 2 | No | No | No | No | Yes | No | No | No | MES26-520D |  | 105787 | ----- | ----- | Roadway widening (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 7000 | 0 | 3000 | 10000
Mesa | Highway | 12830 | Crismon Rd: Elliot Rd to Guadalupe Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 0.3 | 0 | 2 | No | No | No | No | Yes | No | No | No | MES26-520D1 |  | 105787 | ----- | ----- | Roadway widening (Design) | 2026 | STBGP >200 PHX-MESA | 2026 | 419160 | 0 | 179640 | 598800
Mesa | Highway | 15229 | Crismon Rd: Elliot Rd to Guadalupe Rd | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0.152 | 0 | 2 | Yes | No | Yes | No | Yes | Yes | No | No | MES27-530C |  | 105554 | ----- | ----- | Add new roadway to connect existing sections of Crismon Rd between Elliot Rd and Guadalupe Rd. One lane each direction and a center turn lane. (Construction) | 2026 | Local | 2026 | 0 | 0 | 1070699 | 1070699
Mesa | Highway | 4949 | Hawes Rd: Broadway to US60 | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES24-163DZ |  | 103385 | ----- | ----- | Design roadway widening | 2027 | Local | 2027 | 0 | 0 | 1025338.87 | 1025338.87
Mesa | Highway | 3684 | Southern Avenue and Country Club | Principal Arterial - Other | Street | OCT-DEC 2028 | Maricopa | Other | 2.25 | 6 | 6 | No | No | Yes | No | Yes | No | No | Yes | MES25-230C |  | 103577 | ----- | ----- | Construct full pavement reconstruction. Install other improvements including utilities, fiber, streetlights, and ADA ramps and driveways along project corridor. | 2027 | Local | 2027 | 0 | 0 | 14970000 | 14970000
Mesa | Highway | 25278 | 202 (Red Mountain): Val Vista Dr to Power Rd Shared Use Path |  | Bike/Ped | JUL-SEP 2029 | Maricopa | Other | 3.5 | 0 | 0 | No | No | No | No | No | Yes | No | Yes | MES25-241C |  | 101176 | ----- | ----- | Construct shared-use path | 2027 | Local | 2027 | 0 | 0 | 5832202 | 5832202
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-504RWZ |  | 103386 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 2983810 | 2983810
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES26-506CZ |  | 103386 | ----- | ----- | Construct roadway widening | 2027 | Local | 2027 | 0 | 0 | 2000000 | 2000000
Mesa | Highway | 12830 | Crismon Rd: Elliot Rd to Guadalupe Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 0.3 | 0 | 2 | No | No | No | No | Yes | No | No | No | MES26-520C |  | 105787 | ----- | ----- | Roadway widening (Construction) | 2027 | STBGP >200 PHX-MESA | 2027 | 3351390 | 0 | 1664010 | 5015400
Mesa | Highway | 12830 | Crismon Rd: Elliot Rd to Guadalupe Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 0.3 | 0 | 2 | No | No | No | No | Yes | No | No | No | MES26-520R |  | 105787 | ----- | ----- | Roadway widening (Right of Way) | 2027 | Local | 2027 | 0 | 0 | 1500 | 1500
Mesa | Highway | 12830 | Crismon Rd: Elliot Rd to Guadalupe Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 0.3 | 0 | 2 | No | No | No | No | Yes | No | No | No | MES26-520U |  | 105787 | ----- | ----- | Roadway widening (Utilities) | 2027 | STBGP >200 PHX-MESA | 2027 | 39200 | 0 | 16800 | 56000
Mesa | Highway | 38619 | Hawes Rd: Elliot to Santan | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 1.25 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES27-500CZ |  | 101231 | ----- | ----- | Construct Roadway Widening | 2027 | Local | 2027 | 0 | 0 | 2003465 | 2003465
Mesa | Highway | 4940 | Val Vista Dr: US-60 to Pueblo | Minor Arterial | Street | JUL-SEP 2026 | Maricopa | ALCP | 1.5 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES27-500PSZ |  | 101049 | ----- | ----- | Project savings | 2027 | RARF | 2027 | 0 | 3900619.2 | -3900619.2 | 0
Mesa | Highway | 29678 | Country Club Dr at University Dr | Principal Arterial - Other | Street | APR-JUN 2031 | Maricopa | ALCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES27-502DZ |  | 104075 | ----- | ----- | Design intersection improvement | 2027 | Local | 2027 | 0 | 0 | 1193265 | 1193265
Mesa | Highway | 29678 | Country Club Dr at University Dr | Principal Arterial - Other | Street | APR-JUN 2031 | Maricopa | ALCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES27-503RWZ |  | 104075 | ----- | ----- | Acquisition of right-of-way for intersection improvement | 2027 | Local | 2027 | 0 | 0 | 6781088 | 6781088
Mesa | Highway | 22606 | L202 Red Mountain Shared-Use Path: Power Rd to Brown Rd |  | Bike/Ped | OCT-DEC 2029 | Maricopa | Other | 2.6 | 0 | 0 | No | No | No | No | No | Yes | No | Yes | MES24-001 |  | 102160 | ----- | ----- | Construct shared-use path | 2028 | Local | 2028 | 0 | 0 | 3898215 | 3898215
Mesa | Highway | 29679 | Southern Ave: Sossaman Rd to Crismon | Principal Arterial - Other | Street | APR-JUN 2031 | Maricopa | ALCP | 3 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES28-500DZ |  | 104709 | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 1567846.6 | 1567846.6
Mesa | Highway | 4949 | Hawes Rd: Broadway to US60 | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES28-501CZ |  | 103385 | ----- | ----- | Construct roadway widening | 2028 | Local | 2028 | 0 | 0 | 6597082 | 6597082
Mesa | Highway | 34875 | Hawes Rd: Baseline to Elliot | Minor Arterial | Street | APR-JUN 2030 | Maricopa | ALCP | 2 | 2 | 6 | No | No | No | No | Yes | No | No | No | MES28-507CZ |  | 103386 | ----- | ----- | Construct roadway widening | 2028 | Local | 2028 | 0 | 0 | 4389155 | 4389155
Mesa | Highway | 48139 | Ellsworth Road: US 60 (Grand Avenue) to Baseline Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.6 | 4 | 6 | No | No | No | No | No | No | No | No | MES20-019D |  |  | ----- | ----- | Design roadway widening | 2029 | Local | 2029 | 0 | 0 | 724710.3 | 724710.3
Mesa | Highway | 48139 | Ellsworth Road: US 60 (Grand Avenue) to Baseline Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.6 | 4 | 6 | No | No | No | No | No | No | No | No | MES20-019DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 480265.7 | -480265.7 | 0
Mesa | Highway | 48139 | Ellsworth Road: US 60 (Grand Avenue) to Baseline Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.6 | 4 | 6 | No | No | No | No | No | No | No | No | MES20-019RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2029 | Local | 2029 | 0 | 0 | 2174130.9 | 2174130.9
Mesa | Highway | 48139 | Ellsworth Road: US 60 (Grand Avenue) to Baseline Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.6 | 4 | 6 | No | No | No | No | No | No | No | No | MES20-019RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 1440797.1 | -1440797.1 | 0
Mesa | Highway | 29204 | Warner Road: Power Road to Sossaman Road | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | MES20-031D |  |  | ----- | ----- | Design new roadway | 2029 | Local | 2029 | 0 | 0 | 3225748.3 | 3225748.3
Mesa | Highway | 29204 | Warner Road: Power Road to Sossaman Road | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | MES20-031DRB |  |  | ----- | ----- | Design new roadway (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 2137704.2 | -2137704.2 | 0
Mesa | Highway | 29204 | Warner Road: Power Road to Sossaman Road | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | MES20-031RW |  |  | ----- | ----- | Acquisition of right-of-way for new roadway | 2029 | Local | 2029 | 0 | 0 | 9677244.9 | 9677244.9
Mesa | Highway | 29204 | Warner Road: Power Road to Sossaman Road | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | MES20-031RWRB |  |  | ----- | ----- | Acquisition of right-of-way for new roadway (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 6413112.6 | -6413112.6 | 0
Mesa | Highway | 28237 | Dobson Road: Main St to Red Mountain L202 | Minor Arterial | Bike/Ped | OCT-DEC 2030 | Maricopa | Other | 3.2 | 6 | 6 | No | No | No | No | No | Yes | No | No | MES24-002 |  | 102161 | ----- | ----- | Construct complete street corridor | 2029 | Local | 2029 | 0 | 0 | 2877208 | 2877208
Mesa | Highway | 40533 | Main Street: Gilbert Rd to Sossaman Rd | Minor Arterial | Bike/Ped | OCT-DEC 2029 | Maricopa | Other | 7 | 6 | 4 | No | No | No | No | No | Yes | No | No | MES24-003 |  | 103224 | ----- | ----- | Construct new roadway to minor arterial standards. Convert 1 lane of traffic to separated bike lanes. | 2029 | Local | 2029 | 0 | 0 | 5615827 | 5615827
Mesa | Highway | 40126 | Lehi Crossing Trail Phase 2 |  | Bike/Ped | OCT-DEC 2030 | Maricopa | Other | 2.6 | 0 | 0 | No | No | No | No | No | Yes | No | No | MES25-242C |  | 103222 | ----- | ----- | Construct shared-use path | 2029 | Local | 2029 | 0 | 0 | 5392000 | 5392000
Mesa | Highway | 29678 | Country Club Dr at University Dr | Principal Arterial - Other | Street | APR-JUN 2031 | Maricopa | ALCP | 1 | 4 | 6 | No | No | No | No | Yes | No | No | No | MES29-504CZ |  | 104075 | ----- | ----- | Construct intersection improvement | 2029 | Local | 2029 | 0 | 0 | 17156932 | 17156932
Mesa | Highway | 46033 | Mesa Drive: Main Street to McKellips | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3.45 | 2 | 6 | No | No | No | No | No | No | No | No | MES20-009C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 28051012.8 | 28051012.8
Mesa | Highway | 46033 | Mesa Drive: Main Street to McKellips | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3.45 | 2 | 6 | No | No | No | No | No | No | No | No | MES20-009CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 18589413 | -18589413 | 0
Mesa | Highway | 46033 | Mesa Drive: Main Street to McKellips | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3.45 | 2 | 6 | No | No | No | No | No | No | No | No | MES20-009D |  |  | ----- | ----- | Design roadway widening | 2030 | Local | 2030 | 0 | 0 | 4675168.8 | 4675168.8
Mesa | Highway | 46033 | Mesa Drive: Main Street to McKellips | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3.45 | 2 | 6 | No | No | No | No | No | No | No | No | MES20-009DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 3098235.5 | -3098235.5 | 0
Mesa | Highway | 46033 | Mesa Drive: Main Street to McKellips | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3.45 | 2 | 6 | No | No | No | No | No | No | No | No | MES20-009RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2030 | Local | 2030 | 0 | 0 | 14025506.4 | 14025506.4
Mesa | Highway | 46033 | Mesa Drive: Main Street to McKellips | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 3.45 | 2 | 6 | No | No | No | No | No | No | No | No | MES20-009RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 9294706.5 | -9294706.5 | 0
Mesa | Highway | 48139 | Ellsworth Road: US 60 (Grand Avenue) to Baseline Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.6 | 4 | 6 | No | No | No | No | No | No | No | No | MES20-019C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 4348261.8 | 4348261.8
Mesa | Highway | 48139 | Ellsworth Road: US 60 (Grand Avenue) to Baseline Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 0.6 | 4 | 6 | No | No | No | No | No | No | No | No | MES20-019CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 2881594.2 | -2881594.2 | 0
Mesa | Highway | 29204 | Warner Road: Power Road to Sossaman Road | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | MES20-031C |  |  | ----- | ----- | Construct new roadway | 2030 | Local | 2030 | 0 | 0 | 19354489.8 | 19354489.8
Mesa | Highway | 29204 | Warner Road: Power Road to Sossaman Road | Major Collector | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | MES20-031CRB |  |  | ----- | ----- | Construct new roadway (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 12826225.2 | -12826225.2 | 0
Peoria | Highway | 28509 | El Mirage Road: Loop 303 to Jomax Road | Major Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 2.2 | 0 | 4 | No | No | No | No | No | No | No | No | PEO20-001C |  |  | ----- | ----- | Construct new roadway | 2026 | Local | 2026 | 0 | 0 | 65054617.14 | 65054617.14
Peoria | Highway | 28509 | El Mirage Road: Loop 303 to Jomax Road | Major Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 2.2 | 0 | 4 | No | No | No | No | No | No | No | No | PEO20-001CRB |  |  | ----- | ----- | Construct new roadway (Reimb.) | 2026 | 479 RARF ALCP | 2026 | 0 | 21046424 | -21046424 | 0
Peoria | Highway | 449 | Jomax Road: Dysart Road to Vistancia Boulevard | Major Collector | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 1.85 | 0 | 4 | No | No | No | No | No | No | No | No | PEO20-021RW |  |  | ----- | ----- | Acquisition of right-of-way for new roadway | 2026 | Local | 2026 | 0 | 0 | 9275503.5 | 9275503.5
Peoria | Highway | 16301 | El Mirage Rd: L303 to Jomax | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 2.2 | 0 | 4 | No | No | No | No | Yes | No | No | No | PEO24-115DRB |  | 103196 | ----- | T0428 | Design roadway widening | 2026 | STBGP >200 PHX-MESA | 2026 | 2240000 | 0 | -2240000 | 0
Peoria | Highway | 16301 | El Mirage Rd: L303 to Jomax | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 2.2 | 0 | 4 | No | No | No | No | Yes | No | No | No | PEO24-115RRB |  | 103196 | ----- | T0428 | Acquire right-of-way for roadway widening | 2026 | STBGP-MAG | 2026 | 9507548.9 | 0 | -9507548.9 | 0
Peoria | Highway | 16301 | El Mirage Rd: L303 to Jomax | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 2.2 | 0 | 4 | No | No | No | No | Yes | No | No | No | PEO24-115RWZ |  | 103196 | ----- | T0428 | Acquire right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 15600000 | 15600000
Peoria | Highway | 35711 | Northern Ave. to SR 74; 67th Ave. to 138th Ave. |  | Air Quality | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | PEO26-580 |  |  | ----- | ----- | Purchase PM-10 certified street sweepers | 2026 | CMAQ | 2026 | 366660 | 0 | 22163 | 388823
Peoria | Highway | 35820 | Lake Pleasant Pkwy: Loop 303 to SR-74/Carefree Hwy | Minor Arterial | Street | JAN-MAR 2029 | Maricopa | ALCP | 2.2 | 2 | 4 | No | No | No | No | Yes | No | No | No | PEO27-502RWZ |  | 103394 | ----- | ----- | Acquire right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 15445057 | 15445057
Peoria | Highway | 449 | Jomax Road: Dysart Road to Vistancia Boulevard | Major Collector | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 1.85 | 0 | 4 | No | No | No | No | No | No | No | No | PEO20-021C |  |  | ----- | ----- | Construct new roadway | 2027 | Local | 2027 | 0 | 0 | 18551007 | 18551007
Peoria | Highway | 9994 | Lake Pleasant Parkway: Loop 303 to SR 74 | Principal Arterial - Other | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 2.5 | 2 | 4 | No | No | No | No | No | No | No | No | PEO20-023C |  |  | ----- | ----- | Construct roadway widening | 2027 | Local | 2027 | 0 | 0 | 27326302.2 | 27326302.2
Peoria | Highway | 16301 | El Mirage Rd: L303 to Jomax | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | ALCP | 2.2 | 0 | 4 | No | No | No | No | Yes | No | No | No | PEO25-115CZ |  | 103196 | ----- | T0428 | Construct roadway widening | 2027 | Local | 2027 | 0 | 0 | 5645382.86 | 5645382.86
Peoria | Highway | 35820 | Lake Pleasant Pkwy: Loop 303 to SR-74/Carefree Hwy | Minor Arterial | Street | JAN-MAR 2029 | Maricopa | ALCP | 2.2 | 2 | 4 | No | No | No | No | Yes | No | No | No | PEO27-503CZ |  | 103394 | ----- | ----- | Construct roadway widening | 2027 | Local | 2027 | 0 | 0 | 50521330 | 50521330
Peoria | Highway | 28509 | El Mirage Road: Loop 303 to Jomax Road | Major Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 2.2 | 0 | 4 | No | No | No | No | No | No | No | No | PEO20-001CRB-1 |  |  | ----- | ----- | Construct new roadway (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 1633947.3 | -1633947.3 | 0
Peoria | Highway | 13452 | Thunderbird Road: 83rd Avenue to 67th Avenue | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2.02 | 4 | 6 | No | No | No | No | No | No | No | No | PEO20-044D |  |  | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 2465590.3 | 2465590.3
Peoria | Highway | 28509 | El Mirage Road: Loop 303 to Jomax Road | Major Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 2.2 | 0 | 4 | No | No | No | No | No | No | No | No | PEO20-001CRB-2 |  |  | ----- | ----- | Construct new roadway (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 4901841.9 | -4901841.9 | 0
Peoria | Highway | 13452 | Thunderbird Road: 83rd Avenue to 67th Avenue | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2.02 | 4 | 6 | No | No | No | No | No | No | No | No | PEO20-044RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2029 | Local | 2029 | 0 | 0 | 7396770.9 | 7396770.9
Peoria | Highway | 26608 | Vistancia Blvd: White Peak Dr to Galvin Pkwy | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | Other | 1 | 0 | 4 | No | No | No | No | Yes | No | No | No | PEO22-031 |  | 102929 | ----- | ----- | Construct new 4 lane roadway with median | 2029 | Private | 2029 | 0 | 0 | 7200000 | 7200000
Peoria | Highway | 13559 | 83rd Ave at BNSF RR Crossing | Major Collector | Street | OCT-DEC 2031 | Maricopa | Other | 0 | 4 | 4 | No | No | No | No | Yes | No | No | No | PEO10-720 |  | 101354 | ----- | ----- | Narrow intersection to remove railroad crossing | 2030 | Local | 2030 | 0 | 0 | 1800000 | 1800000
Peoria | Highway | 28509 | El Mirage Road: Loop 303 to Jomax Road | Major Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 2.2 | 0 | 4 | No | No | No | No | No | No | No | No | PEO20-001CRB-3 |  |  | ----- | ----- | Construct new roadway (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 9803683.8 | -9803683.8 | 0
Peoria | Highway | 33913 | 107th Avenue: Williams Road to Hatfield Road | Minor Arterial | Street | OCT-DEC 2032 | Maricopa | 479-ALCP | 1.23 | 2 | 4 | No | No | No | No | No | No | No | No | PEO20-043D |  |  | ----- | ----- | Design roadway widening | 2030 | Local | 2030 | 0 | 0 | 1337825.5 | 1337825.5
Peoria | Highway | 13452 | Thunderbird Road: 83rd Avenue to 67th Avenue | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2.02 | 4 | 6 | No | No | No | No | No | No | No | No | PEO20-044C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 14793541.8 | 14793541.8
Peoria | Transit | 24193 | Regionwide: Peoria |  | Transit Bus | OCT-DEC 2026 | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PEO26-210T |  | 103180 | ----- | 11.12.04 | Purchase bus: < 30 foot - 2 replace (dial-a-ride) | 2026 | 5307-PMS | 2025 | 272000 | 48000 | 0 | 320000
Peoria | Transit | 47283 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PEO26-500T |  | 105762 | ----- | 30.09.01 | City of Peoria WeRIDE | 2026 | 5310-PMS | 2025 | 166974 | 0 | 166974 | 333948
Peoria | Transit | 8913 | Regionwide: Peoria |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PEO26-510T |  |  | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PMS | 2025 | 33164 | 0 | 8291 | 41455
Phoenix | Highway | 573 | Deer Valley Rd, Tatum Blvd to Mariott Dr | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.49 | 4 | 6 | No | No | No | No | Yes | No | No | No | PHX23-201 |  | 103012 | ----- | ----- | Widen Roadway | 2026 | Private | 2026 | 0 | 0 | 1457005 | 1457005
Phoenix | Highway | 34703 | 35th Avenue: I-10 to Camelback Road | Principal Arterial - Other | Safety | APR-JUN 2026 | Maricopa | Other | 3 | 5 | 5 | Yes | No | Yes | No | Yes | No | No | Yes | PHX23-272 |  | 103288 | ----- | ----- | Safety Project includes 3 HAWKS, LED lighting, nine intersection modernization improvements, upgraded traffic signals, raised medians, pavement treatment on deteriorated sections, broadband and fiber to support intelligent and connected transportation systems. | 2026 | BUILD | 2026 | 17422515 | 0 | 7453677 | 24876192
Phoenix | Highway | 20321 | Four locations: Northern Ave & Arizona Canal, 43rd Ave & Hubbell St, Buckeye Rd & 3rd Ave, 7th Ave & Western Canal | Principal Arterial - Other | Bike/Ped | OCT-DEC 2025 | Maricopa | Other | 0 | 6 | 4 | No | No | No | No | No | Yes | No | No | PHX24-040 |  | 101920 | PHX-0(375)D | T0407 | Construct HAWKs at high-crash and high-activity areas identified by our T2050 Mobility Studies. | 2026 | TA-MAG | 2026 | 1341422 | 0 | 81083 | 1422505
Phoenix | Highway | 23830 | Phoenix: ReVISIONing Indian School Road |  | Safety | OCT-DEC 2028 | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | PHX24-273C | ST89320180 | 104464 | ----- | ----- | Implement intersection and pedestrian infrastructure changes and safety treatments along Indian School Road between 91st and 39th Avenues, including installation of sidewalks, pedestrian beacons, crossing improvements, and lighting improvements. Of the proposed project area’s adjacent Census tracts, 95% are categorized as disadvantaged communities. | 2026 | SS4A | 2023 | 24962745 | 0 | 6240687 | 31203432
Phoenix | Highway | 23830 | Phoenix: ReVISIONing Indian School Road |  | Safety | OCT-DEC 2028 | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | PHX24-273D | ST89320180 | 104464 | ----- | ----- | Design intersection and pedestrian infrastructure changes and safety treatments along Indian School Road between 91st and 39th Avenues, including installation of sidewalks, pedestrian beacons, crossing improvements, and lighting improvements. Of the proposed project area’s adjacent Census tracts, 95% are categorized as disadvantaged communities. | 2026 | Local | 2026 | 0 | 0 | 2598728 | 2598728
Phoenix | Highway | 24374 | Happy Valley Rd: 35th Ave to 67th Ave | Minor Arterial | Street | JUL-SEP 2025 | Maricopa | ALCP | 4 | 5 | 6 | No | No | No | No | Yes | No | No | No | PHX25-107RRB |  | 102205 | ----- | T0239 | Acquisition of right of way for roadway widening | 2026 | RARF | 2026 | 0 | 155649.06 | -155649.06 | 0
Phoenix | Highway | 37157 | 3rd Street Pedestrian Bridge over the Rio Salado |  | Bike/Ped | OCT-DEC 2026 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | Yes | No | No | PHX26-240C |  | 104174 | ----- | ----- | Pedestrian bridge over Rio Salado. Improvements to south bank pathway including concrete retrofit and lighting (Construction) | 2026 | RAISE | 2025 | 25000000 | 0 | 4887554 | 29887554
Phoenix | Highway | 19935 | Thunderbird Rd at 43rd Ave |  | Safety | N/A | Maricopa | 5-year | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | PHX26-271C |  | 103600 | PHX-0(378)D | T0506 | Construction Traffic Signal Visibility | 2026 | HSIP-AZ | 2026 | 1030472 | 0 | 0 | 1030472
Phoenix | Highway | 25574 | 27th Ave: Lower Buckeye Rd to Buckeye Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | PHX26-520D | ST85100341 | 105785 | ----- | ----- | Roadway widening (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 7000 | 0 | 3000 | 10000
Phoenix | Highway | 45997 | 35th Ave: I-10 to Camelback Rd | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 3.2 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | PHX26-521C | ST89340634 | 105775 | ----- | ----- | Roadway rehabilitation (Construction) | 2026 | STBGP >200 PHX-MESA | 2026 | 10024591.4 | 0 | 4296253.46 | 14320844.86
Phoenix | Highway | 45997 | 35th Ave: I-10 to Camelback Rd | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 3.2 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | PHX26-521D | ST89340634 | 105775 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 7000 | 0 | 3000 | 10000
Phoenix | Highway | 44367 | Lower Buckeye Rd: 27th Ave to 19th Ave | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 1 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | PHX26-522D | ST85100411 | 105782 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 7000 | 0 | 3000 | 10000
Phoenix | Highway | 35925 | 7th Ave: Southern Ave to Broadway Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | PHX26-523D | ST85100459 | 105776 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 7000 | 0 | 3000 | 10000
Phoenix | Highway | 27589 | Various alleys in Phoenix |  | Air Quality | OCT-DEC 2026 | Maricopa | Other | 34.8 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | PHX26-530C |  | 105115 | ----- | T0693 | Paving Unpaved Alleys (Construction) | 2026 | CMAQ | 2026 | 2875552 | 0 | 1613851 | 4489403
Phoenix | Highway | 27589 | Various alleys in Phoenix |  | Air Quality | OCT-DEC 2026 | Maricopa | Other | 34.8 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | PHX26-530D1 |  | 105115 | PHX-0(384)D | T0693 | ADOT Review Fee | 2026 | Local | 2026 | 0 | 0 | 10000 | 10000
Phoenix | Highway | 27485 | 3 Intersections: Jesse Owens Pkwy and Baseline Rd, 7th St and McDowell Rd, and Cave Creek Rd and Greenway Pkwy | Local | Safety | OCT-DEC 2027 | Maricopa | 5-year | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | PHX26-570C |  | 103598 | ----- | T0509 | Construct Traffic Signal | 2026 | HSIP-AZ | 2026 | 2879032 | 0 | 0 | 2879032
Phoenix | Highway | 40616 | Phoenix: Planning Study |  | Safety | N/A | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | PHX26-571 |  | 105806 | ----- | ----- | Planning Study_Creating Safer and Equitable Streets | 2026 | SS4A | 2022 | 460000 | 0 | 115000 | 575000
Phoenix | Highway | 41886 | Estrella Dr. to Camelback Rd.; 107th Ave. to Central Ave. |  | Air Quality | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | PHX26-580 |  |  | ----- | ----- | Purchase PM-10 certified street sweepers | 2026 | CMAQ | 2026 | 441783 | 0 | 26704 | 468487
Phoenix | Highway | 28349 | Lower Buckeye Rd: 19th Ave to 27th Ave (ST85100411) | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 1 | 2 | 5 | No | No | No | No | Yes | No | No | No | MMA22-802 | ST85100411 | 102201 | ----- | ----- | Construction | 2027 | Local | 2027 | 0 | 0 | 9298000 | 9298000
Phoenix | Highway | 40117 | Sonoran Desert Drive: I-17 Freeway to North Valley Parkway | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 1.5 | 0 | 6 | No | No | No | No | Yes | No | No | No | PHX15-435 | ST85110090 | 105765 | ----- | ----- | Construct Roadway | 2027 | Private | 2027 | 0 | 0 | 6200000 | 6200000
Phoenix | Highway | 44514 | Indian School Road: 59th Avenue to 27th Avenue | Minor Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 4.01 | 5 | 5 | No | No | No | No | No | No | No | No | PHX20-064D |  |  | ----- | ----- | Design roadway reconstruction | 2027 | Local | 2027 | 0 | 0 | 1793395.3 | 1793395.3
Phoenix | Highway | 31264 | Southern Avenue: 51st Avenue to 37th Avenue | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1.8 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-129CD |  |  | ----- | ----- | Design roadway widening | 2027 | Local | 2027 | 0 | 0 | 1835276.1 | 1835276.1
Phoenix | Highway | 31264 | Southern Avenue: 51st Avenue to 37th Avenue | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1.8 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-129CDRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 1216237.9 | -1216237.9 | 0
Phoenix | Highway | 31264 | Southern Avenue: 51st Avenue to 37th Avenue | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1.8 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-129CRW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 5505828.3 | 5505828.3
Phoenix | Highway | 31264 | Southern Avenue: 51st Avenue to 37th Avenue | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1.8 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-129CRWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 3648713.7 | -3648713.7 | 0
Phoenix | Highway | 45844 | 43rd Av & Missouri Av | Local | Safety | OCT-DEC 2027 | Maricopa | 5-year | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | PHX26-270C | ST89320170 | 103599 | PHX-0(377)D | T0505 | Construction Install New Traffic Signal | 2027 | HSIP-AZ | 2026 | 959737 | 0 | 0 | 959737
Phoenix | Highway | 44367 | Lower Buckeye Rd: 27th Ave to 19th Ave | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | Other | 1 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | PHX26-522C | ST85100411 | 105782 | ----- | ----- | Roadway rehabilitation (Construction) | 2027 | STBGP >200 PHX-MESA | 2027 | 8482419.78 | 0 | 3635322.76 | 12117742.54
Phoenix | Highway | 35925 | 7th Ave: Southern Ave to Broadway Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | PHX26-523D1 | ST85100459 | 105776 | ----- | ----- | Roadway rehabilitation (Design) | 2027 | STBGP >200 PHX-MESA | 2027 | 445200 | 0 | 190800 | 636000
Phoenix | Highway | 32814 | Various alleys in Phoenix |  | Air Quality | OCT-DEC 2027 | Maricopa | Other | 39.3 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | PHX27-530C |  | 105116 | ----- | ----- | Paving Unpaved Alleys (Construction) | 2027 | CMAQ | 2027 | 4247817 | 0 | 933667 | 5181484
Phoenix | Highway | 32814 | Various alleys in Phoenix |  | Air Quality | OCT-DEC 2027 | Maricopa | Other | 39.3 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | PHX27-530D1 |  | 105116 | ----- | ----- | ADOT Review Fee | 2027 | Local | 2027 | 0 | 0 | 10000 | 10000
Phoenix | Highway | 44514 | Indian School Road: 59th Avenue to 27th Avenue | Minor Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 4.01 | 5 | 5 | No | No | No | No | No | No | No | No | PHX20-064RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway reconstruction | 2028 | Local | 2028 | 0 | 0 | 5380185.9 | 5380185.9
Phoenix | Highway | 49688 | Dobbins Road: Loop 202 South Mountain to 27th Avenue | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 4.16 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-109D |  |  | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 5780614.5 | 5780614.5
Phoenix | Highway | 49688 | Dobbins Road: Loop 202 South Mountain to 27th Avenue | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 4.16 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-109DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 2109862.74 | -2109862.74 | 0
Phoenix | Highway | 31264 | Southern Avenue: 51st Avenue to 37th Avenue | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1.8 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-129CC |  |  | ----- | ----- | Construct roadway widening | 2028 | Local | 2028 | 0 | 0 | 11011656.6 | 11011656.6
Phoenix | Highway | 31264 | Southern Avenue: 51st Avenue to 37th Avenue | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1.8 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-129CCRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 7297427.4 | -7297427.4 | 0
Phoenix | Highway | 25574 | 27th Ave: Lower Buckeye Rd to Buckeye Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | PHX26-520C | ST85100341 | 105785 | ----- | ----- | Roadway widening (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 3100813.7 | 0 | 10518251.9 | 13619065.6
Phoenix | Highway | 35925 | 7th Ave: Southern Ave to Broadway Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | PHX26-523R | ST85100459 | 105776 | ----- | ----- | Roadway rehabilitation (Right of Way) | 2028 | STBGP >200 PHX-MESA | 2028 | 287000 | 0 | 123000 | 410000
Phoenix | Highway | 35925 | 7th Ave: Southern Ave to Broadway Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | PHX26-523U | ST85100459 | 105776 | ----- | ----- | Roadway rehabilitation (Utilities) | 2028 | STBGP >200 PHX-MESA | 2028 | 350000 | 0 | 150000 | 500000
Phoenix | Highway | 33165 | Various alleys in Phoenix |  | Air Quality | OCT-DEC 2028 | Maricopa | Other | 37.4 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | PHX28-530C |  | 105117 | ----- | ----- | Paving Unpaved Alleys (Construction) | 2028 | CMAQ | 2028 | 4361116 | 0 | 2913527 | 7274643
Phoenix | Highway | 33165 | Various alleys in Phoenix |  | Air Quality | OCT-DEC 2028 | Maricopa | Other | 37.4 | 0 | 0 | No | No | Yes | No | No | No | Yes | No | PHX28-530D1 |  | 105117 | ----- | ----- | ADOT Review Fee | 2028 | Local | 2028 | 0 | 0 | 10000 | 10000
Phoenix | Highway | 44514 | Indian School Road: 59th Avenue to 27th Avenue | Minor Collector | Street | OCT-DEC 2029 | Maricopa | 479-ALCP | 4.01 | 5 | 5 | No | No | No | No | No | No | No | No | PHX20-064C |  |  | ----- | ----- | Construction roadway reconstruction | 2029 | Local | 2029 | 0 | 0 | 10760371.8 | 10760371.8
Phoenix | Highway | 35925 | 7th Ave: Southern Ave to Broadway Rd | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | PHX26-523C | ST85100459 | 105776 | ----- | ----- | Roadway rehabilitation (Construction) | 2029 | STBGP >200 PHX-MESA | 2029 | 2909367.19 | 0 | 8578429.21 | 11487796.4
Phoenix | Highway | 49688 | Dobbins Road: Loop 202 South Mountain to 27th Avenue | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 4.16 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-109C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 34683687 | 34683687
Phoenix | Highway | 49688 | Dobbins Road: Loop 202 South Mountain to 27th Avenue | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 4.16 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-109CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 12659176.01 | -12659176.01 | 0
Phoenix | Highway | 49688 | Dobbins Road: Loop 202 South Mountain to 27th Avenue | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 4.16 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-109RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2030 | Local | 2030 | 0 | 0 | 17341843.5 | 17341843.5
Phoenix | Highway | 49688 | Dobbins Road: Loop 202 South Mountain to 27th Avenue | Minor Arterial | Street | OCT-DEC 2031 | Maricopa | 479-ALCP | 4.16 | 2 | 4 | No | No | No | No | No | No | No | No | PHX20-109RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 6329588.22 | -6329588.22 | 0
Phoenix | Highway | 28364 | Buckeye Rd: 67 Ave to 59 Ave (T2050) (ST85100409) | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | Other | 1 | 2 | 4 | No | No | No | No | Yes | No | No | No | PHX21-003 | ST85100409 | 102199 | ----- | ----- | Construction: Add thru lanes, median, curb, gutter and sidewalks | 2030 | Local | 2030 | 0 | 0 | 10281335 | 10281335
Phoenix | Highway | 39179 | Happy Valley: 7th Ave to 7th St | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | Other | 1 | 2 | 6 | No | No | No | No | Yes | No | No | No | PHX25-204 |  | 103219 | ----- | ----- | Widen Roadway | 2030 | Private | 2030 | 0 | 0 | 17659684 | 17659684
Phoenix | Transit | 40430 | 19th Ave & Pinnacle Peak Road |  | Transit Bus | OCT-DEC 2028 | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-010T |  | 104440 | ----- | 11.41.03 | Design - New North Phoenix Bus Facility | 2026 | Local | 2026 | 0 | 0 | 9000000 | 9000000
Phoenix | Transit | 32671 | Regionwide |  | Transit Bus | OCT-DEC 2026 | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-211T |  | 101244 | ----- | 11.79.00 | Program Administration | 2026 | 5307-PMS | 2025 | 1154113 | 0 | 288528 | 1442641
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-212T |  | 103143 | ----- | 11.12.04 | Purchase bus: < 30 foot - 18 replace (dial-a-ride) | 2026 | 5307-PMS | 2025 | 2697788 | 476081 | 0 | 3173869
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-213T |  | 103143 | ----- | 11.12.01 | Purchase bus: standard - 11 replace | 2026 | 5307-PMS | 2025 | 13265406 | 2340954 | 0 | 15606360
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-213T2 |  | 103143 | ----- | 11.12.01 | Purchase bus: standard - 11 replace | 2026 | 5307-PMS | 2024 | 13601503 | 2400265 | 0 | 16001768
Phoenix | Transit | 15316 | Regionwide: Phoenix |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-214T |  | 104363 | ----- | 11.12.01 | Purchase bus: 40 foot - 5 replace (CapEx Repayment) | 2026 | CMAQ-Flex | 2025 | 6514398 | 0 | 1149600 | 7663998
Phoenix | Transit | 15316 | Regionwide: Phoenix |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-215T |  | 104363 | ----- | 11.7A.00 | Preventive Maintenance (CapEx Repayment) | 2026 | 5307-PMS | 2025 | 7000000 | 0 | 1235294 | 8235294
Phoenix | Transit | 23840 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PHX26-500T |  | 103172 | ----- | 11.80.00 | Program Administration | 2026 | 5310-PMS | 2023 | 128365 | 0 | 0 | 128365
Phoenix | Transit | 23840 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PHX26-501T |  | 103172 | ----- | 30.09.01 | City of Phoenix RideChoice | 2026 | 5310-PMS | 2025 | 250000 | 0 | 250000 | 500000
Phoenix | Transit | 23840 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PHX26-502T |  | 103172 | ----- | 11.80.00 | Phoenix Program Administration | 2026 | 5310-PMS | 2025 | 445569 | 0 | 0 | 445569
Phoenix | Transit | 23840 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | PHX26-503T |  | 103172 | ----- | 11.80.00 | Phoenix Program Administration | 2026 | 5310-PGA | 2025 | 43741 | 0 | 0 | 43741
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-510T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | STBGP-AZ-Flex | 2024 | 2875186 | 0 | 718797 | 3593983
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-511T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | TA-AZ-Flex | 2025 | 2843441 | 0 | 710860 | 3554301
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-512T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307 | 2023 | 137861 | 0 | 34465 | 172326
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-513T |  | 103143 | ----- | 11.12.01 | Purchase bus: BEB 40 foot - 12 replace, CNG portion | 2026 | 5307 | 2023 | 6018000 | 1062000 | 0 | 7080000
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-514T |  | 103143 | ----- | 11.12.01 | Purchase bus: BEB 40 foot - 9 replace | 2026 | 5307 | 2023 | 10853514 | 1915326 | 0 | 12768840
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-515T |  | 103143 | ----- | 11.12.04 | Purchase bus: < 30 foot - 7 replace (dial-a-ride) | 2026 | 5307 | 2023 | 1049140 | 185142 | 0 | 1234282
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-516T |  | 103143 | ----- | 11.12.04 | Purchase bus: < 30 foot - 20 replace (dial-a-ride) | 2026 | 5307 | 2023 | 2775505 | 489795 | 0 | 3265300
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-517T |  | 103143 | ----- | 11.12.04 | Purchase bus: < 30 foot - 5 replace (circulator) | 2026 | 5307 | 2023 | 1073945 | 189520 | 0 | 1263465
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-518T |  | 103143 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 3 replace | 2026 | 5307-PGA | 2024 | 3349851 | 591150 | 0 | 3941001
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-519T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PGA | 2024 | 1945507 | 0 | 486377 | 2431884
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-520T |  | 103143 | ----- | 11.12.01 | Purchase Bus: 40 foot RAPID - 3 replace | 2026 | 5337-HI | 2023 | 3349853 | 591151 | 0 | 3941004
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-521T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI | 2023 | 897743 | 0 | 224436 | 1122179
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-522T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI PGA | 2024 | 91145 | 0 | 22786 | 113931
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-523T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI PMS | 2024 | 4425368 | 0 | 1106342 | 5531710
Phoenix | Transit | 15316 | Regionwide: Phoenix |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-524T |  | 104363 | ----- | 11.12.04 | Purchase bus: < 30 foot - 11 replace (dial-a-ride) (CapEx Repayment) | 2026 | CMAQ-Flex | 2025 | 485602 | 85694 | 0 | 571296
Phoenix | Transit | 4101 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-525T |  | 103143 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 3 replace | 2026 | 5307-PGA | 2025 | 3617838 | 0 | 638442 | 4256280
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-526T |  | 104626 | ----- | 11.79.00 | Program Administration | 2026 | 5307-PGA | 2025 | 105675 | 0 | 26419 | 132094
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-527T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PGA | 2025 | 1471779 | 0 | 367945 | 1839724
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-528T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PMS | 2025 | 4831724 | 0 | 1207931 | 6039655
Phoenix | Transit | 47276 | Regionwide: Phoenix |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX26-529T |  | 104626 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI PGA | 2025 | 150000 | 0 | 37500 | 187500
Phoenix | Transit | 9720 | Phoenix-Citywide |  | Transit Other | OCT-DEC 2026 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | Yes | No | No | PHX26-580T |  | 105063 | ----- | ----- | Operation of three microtransit zones in Phoenix | 2026 | CoRP | 2024 | 7383600 | 0 | 1845900 | 9229500
Phoenix | Transit | 9720 | Phoenix-Citywide |  | Transit Other | OCT-DEC 2026 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | Yes | No | No | PHX26-581T |  | 105063 | ----- | ----- | Operation of commuter bus enhancement in Phoenix | 2026 | CoRP | 2024 | 5140800 | 0 | 1285200 | 6426000
Phoenix | Transit | 9720 | Phoenix-Citywide |  | Transit Other | OCT-DEC 2026 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | Yes | No | No | PHX26-582T |  | 105063 | ----- | ----- | Microtransit App integration | 2026 | CoRP | 2024 | 420000 | 0 | 105000 | 525000
Phoenix | Transit | 15316 | Regionwide: Phoenix |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX27-210T |  | 104363 | ----- | ----- | Bus Purchases TBD (CapEx Repayment) | 2026 | CMAQ-Flex | 2026 | 6857225 | 0 | 1210098 | 8067323
Phoenix | Transit | 15316 | Regionwide: Phoenix |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX27-211T |  | 104363 | ----- | 11.7A.00 | Preventive Maintenance (CapEx Repayment) | 2026 | 5307-PMS | 2026 | 6857225 | 0 | 1210098 | 8067323
Phoenix | Transit | 40430 | 19th Ave & Pinnacle Peak Road |  | Transit Bus | OCT-DEC 2028 | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | PHX28-010T |  | 104440 | ----- | 11.43.03 | Construction - New North Phoenix Bus Facility | 2028 | Local | 2028 | 0 | 0 | 80000000 | 80000000
Pinal County | Highway | 8258 | El Camino Viejo: North San Mateo Castro Rd-Sand Tanks Wash Bridge | Minor Collector | Bridge | OCT-DEC 2029 | Pinal | 5-year | 0.1 | 2 | 2 | No | No | No | Yes | No | No | No | No | PNL28-220C |  | 104511 | PPN-0(233)T | T0603 | Bridge Replacement (Construction) | 2028 | STBGP-OSB | 2028 | 1706000 | 0 | 0 | 1706000
Queen Creek | Highway | 9134 | Hawes Road: Rittenhouse Road to Chandler Heights | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.25 | 2 | 4 | No | No | No | No | No | No | No | No | QNC20-053D |  |  | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 4543880.7 | 4543880.7
Queen Creek | Highway | 9134 | Hawes Road: Rittenhouse Road to Chandler Heights | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.25 | 2 | 4 | No | No | No | No | No | No | No | No | QNC20-053DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2026 | 479 RARF ALCP | 2026 | 0 | 3011230.8 | -3011230.8 | 0
Queen Creek | Highway | 18668 | Crismon Rd: Queen Creek Rd to Ryan Rd | Local | Street | OCT-DEC 2026 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | QNC23-202 |  | 103161 | ----- | ----- | Widen Roadway | 2026 | Private | 2026 | 0 | 0 | 2500000 | 2500000
Queen Creek | Highway | 28209 | Various Locations - Queen Creek | Principal Arterial - Other | ITS | OCT-DEC 2028 | Maricopa | SM+O | 0 | 0 | 0 | No | No | No | No | Yes | No | Yes | No | QNC25-260D-1 |  | 103941 | ----- | ----- | Fiber optic cabling and communication infrastructure (Design) | 2026 | Local | 2026 | 0 | 0 | 100000 | 100000
Queen Creek | Highway | 28209 | Various Locations - Queen Creek | Principal Arterial - Other | ITS | OCT-DEC 2028 | Maricopa | SM+O | 0 | 0 | 0 | No | No | No | No | Yes | No | Yes | No | QNC25-260D1-2 |  | 103941 | ----- | ----- | ADOT Design Review Fee | 2026 | Local | 2026 | 0 | 0 | 30000 | 30000
Queen Creek | Highway | 5628 | Germann Road: Rittenhouse Road to 194th Way (Sossaman/UPRR) | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.61 | 0 | 6 | No | No | No | No | No | No | No | No | QNC20-035D |  |  | ----- | ----- | Design roadway reconstruction | 2027 | Local | 2027 | 0 | 0 | 1771076.3 | 1771076.3
Queen Creek | Highway | 5628 | Germann Road: Rittenhouse Road to 194th Way (Sossaman/UPRR) | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.61 | 0 | 6 | No | No | No | No | No | No | No | No | QNC20-035DRB |  |  | ----- | ----- | Design roadway reconstruction (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 1173692.7 | -1173692.7 | 0
Queen Creek | Highway | 5628 | Germann Road: Rittenhouse Road to 194th Way (Sossaman/UPRR) | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.61 | 0 | 6 | No | No | No | No | No | No | No | No | QNC20-035RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway reconstruction | 2027 | Local | 2027 | 0 | 0 | 5313228.9 | 5313228.9
Queen Creek | Highway | 5628 | Germann Road: Rittenhouse Road to 194th Way (Sossaman/UPRR) | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.61 | 0 | 6 | No | No | No | No | No | No | No | No | QNC20-035RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway reconstruction (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 121078.1 | -121078.1 | 0
Queen Creek | Highway | 9134 | Hawes Road: Rittenhouse Road to Chandler Heights | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.25 | 2 | 4 | No | No | No | No | No | No | No | No | QNC20-053CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 3400000 | -3400000 | 0
Queen Creek | Highway | 9134 | Hawes Road: Rittenhouse Road to Chandler Heights | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.25 | 2 | 4 | No | No | No | No | No | No | No | No | QNC20-053RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 13631642.1 | 13631642.1
Queen Creek | Highway | 9134 | Hawes Road: Rittenhouse Road to Chandler Heights | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.25 | 2 | 4 | No | No | No | No | No | No | No | No | QNC20-053RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 9033692.4 | -9033692.4 | 0
Queen Creek | Highway | 28209 | Various Locations - Queen Creek | Principal Arterial - Other | ITS | OCT-DEC 2028 | Maricopa | SM+O | 0 | 0 | 0 | No | No | No | No | Yes | No | Yes | No | QNC25-260C |  | 103941 | ----- | ----- | Fiber optic cabling and communication infrastructure (Procurement) | 2027 | CMAQ | 2027 | 713097 | 0 | 285143 | 998240
Queen Creek | Highway | 5628 | Germann Road: Rittenhouse Road to 194th Way (Sossaman/UPRR) | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.61 | 0 | 6 | No | No | No | No | No | No | No | No | QNC20-035C |  |  | ----- | ----- | Construction roadway reconstruction | 2028 | Local | 2028 | 0 | 0 | 10626457.8 | 10626457.8
Queen Creek | Highway | 5628 | Germann Road: Rittenhouse Road to 194th Way (Sossaman/UPRR) | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.61 | 0 | 6 | No | No | No | No | No | No | No | No | QNC20-035CRB |  |  | ----- | ----- | Construct roadway reconstruction (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 7042156.2 | -7042156.2 | 0
Queen Creek | Highway | 9134 | Hawes Road: Rittenhouse Road to Chandler Heights | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.25 | 2 | 4 | No | No | No | No | No | No | No | No | QNC20-053C |  |  | ----- | ----- | Construct roadway widening | 2028 | Local | 2028 | 0 | 0 | 27263284.2 | 27263284.2
Queen Creek | Highway | 5628 | Germann Road: Rittenhouse Road to 194th Way (Sossaman/UPRR) | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.61 | 0 | 6 | No | No | No | No | No | No | No | No | QNC28-035RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway reconstruction (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 3400000 | -3400000 | 0
Queen Creek | Highway | 9134 | Hawes Road: Rittenhouse Road to Chandler Heights | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.25 | 2 | 4 | No | No | No | No | No | No | No | No | QNC28-053CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 14667384.8 | -14667384.8 | 0
Salt River Pima-Maricopa Indian Community | Highway | 23910 | Via de Ventura: Pima Rd to Loop 101 (Pima Freeway) | Minor Arterial | Street | OCT-DEC 2027 | Maricopa | Other | 0.6 | 4 | 4 | Yes | No | Yes | No | No | Yes | No | No | SRP26-520C |  | 105784 | ----- | ----- | Roadway rehabilitation (Construction) | 2026 | STBGP >200 PHX-MESA | 2026 | 5079118.75 | 0 | 2176765.18 | 7255883.93
Salt River Pima-Maricopa Indian Community | Highway | 23303 | Salt River Pima-Maricopa Indian Community: Comprehensive Safety Action Plan and Demonstration Plan |  | Safety | N/A | Maricopa | Other | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | SRP26-570 |  | 105802 | ----- | ----- | Planning and Demonstration | 2026 | SS4A | 2024 | 200000 | 0 | 50000 | 250000
Salt River Pima-Maricopa Indian Community | Highway | 5210 | Dobson Road Bridge at the Salt River | Minor Arterial | Street | OCT-DEC 2032 | Maricopa | 479-ALCP | 1.5 | 0 | 4 | No | No | No | No | No | No | No | No | SRP20-001D |  |  | ----- | ----- | Design new bridge | 2029 | Local | 2029 | 0 | 0 | 7274672.9 | 7274672.9
Scottsdale | Highway | 4095 | Pima Rd: Via Linda to Via De Ventura | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 7.2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT16-113CRB |  | 101040 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 19776842.06 | -19776842.06 | 0
Scottsdale | Highway | 29143 | Legacy Boulevard: 94th Street to 98th Street | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-004D |  |  | ----- | ----- | Design new bridge | 2026 | Local | 2026 | 0 | 0 | 483140.2 | 483140.2
Scottsdale | Highway | 29143 | Legacy Boulevard: 94th Street to 98th Street | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-004DRB |  |  | ----- | ----- | Design new bridge (Reimb.) | 2026 | 479 RARF ALCP | 2026 | 0 | 320177.1 | -320177.1 | 0
Scottsdale | Highway | 4095 | Pima Rd: Via Linda to Via De Ventura | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 7.2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT20-113DRB |  | 101040 | ----- | ----- | Design roadway widening | 2026 | RARF | 2026 | 0 | 2235568.83 | -2235568.83 | 0
Scottsdale | Highway | 49272 | Alma School Pkwy: Jomax Rd to Pinnacle Vista Rd | Major Collector | Street | OCT-DEC 2026 | Maricopa | Other | 0.55 | 2 | 4 | No | No | No | No | Yes | No | No | No | SCT20-707 |  | 101311 | ----- | ----- | Widen roadway from two to four lanes | 2026 | Local | 2026 | 0 | 0 | 4325000 | 4325000
Scottsdale | Highway | 24722 | Shea Blvd Intersection Improvements | Principal Arterial - Other | Street | OCT-DEC 2025 | Maricopa | ALCP | 6 | 6 | 6 | No | No | Yes | No | Yes | No | No | Yes | SCT21-140RRB |  | 102209 | ----- | ----- | Acquisition of right-of-way for roadway improvements | 2026 | RARF | 2026 | 0 | 487929.41 | -487929.41 | 0
Scottsdale | Highway | 25440 | Pima Rd: Happy Valley Rd to Jomax Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT22-131CZ |  | 101765 | SCT-0(243)D | T0499 | Construct roadway widening | 2026 | STBGP-MAG | 2026 | 5072321.15 | 0 | 2173851.92 | 7246173.07
Scottsdale | Highway | 25440 | Pima Rd: Happy Valley Rd to Jomax Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT22-131RRB |  | 101765 | SCT-0(243)D | T0499 | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 350000 | -350000 | 0
Scottsdale | Highway | 24722 | Shea Blvd Intersection Improvements | Principal Arterial - Other | Street | OCT-DEC 2025 | Maricopa | ALCP | 6 | 6 | 6 | No | No | Yes | No | Yes | No | No | Yes | SCT22-140SAVZ |  | 102209 | ----- | ----- | Project savings for roadway improvements | 2026 | RARF | 2026 | 0 | 458886 | 0 | 458886
Scottsdale | Highway | 22239 | Pima Rd: Dynamite Blvd to Las Piedras | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 1.3 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT23-128RRB |  | 102220 | ----- | ----- | Acquisition of right-of-way for Roadway Widening | 2026 | RARF | 2026 | 0 | 210000 | -210000 | 0
Scottsdale | Highway | 19791 | Carefree Hwy: Cave Creek Rd to Scottsdale Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | ALCP | 2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT23-130RRB |  | 102216 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 756842.95 | -756842.95 | 0
Scottsdale | Highway | 30558 | Scottsdale Rd: Dixileta Dr to Carefree Highway | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 3 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT23-139DRB |  | 102222 | ----- | ----- | Design roadway improvements | 2026 | STBGP >200 PHX-MESA | 2026 | 1400000 | 0 | -1400000 | 0
Scottsdale | Highway | 30558 | Scottsdale Rd: Dixileta Dr to Carefree Highway | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 3 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT23-139DZ |  | 102222 | ----- | ----- | Design roadway improvements | 2026 | Local | 2026 | 0 | 0 | 2000000 | 2000000
Scottsdale | Highway | 21900 | Hualapai Dr: 83rd St to Pima Rd | Minor Arterial | Street | OCT-DEC 2024 | Maricopa | ALCP | 0.5 | 0 | 4 | No | No | No | No | Yes | No | No | No | SCT23-148DRB |  | 102217 | ----- | ----- | Design New Roadway (Reimb) | 2026 | RARF | 2026 | 0 | 350000 | -350000 | 0
Scottsdale | Highway | 21900 | Hualapai Dr: 83rd St to Pima Rd | Minor Arterial | Street | OCT-DEC 2024 | Maricopa | ALCP | 0.5 | 0 | 4 | No | No | No | No | Yes | No | No | No | SCT23-148RRB |  | 102217 | ----- | ----- | Acquisition of right of way for New Roadway (Reimb) | 2026 | RARF | 2026 | 0 | 365427.33 | -365427.33 | 0
Scottsdale | Highway | 7209 | Raintree Drive: Hayden Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT24-118CRB |  | 101053 | ----- | ----- | Design roadway improvements | 2026 | RARF | 2026 | 0 | 223456.68 | -223456.68 | 0
Scottsdale | Highway | 25440 | Pima Rd: Happy Valley Rd to Jomax Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT24-131CZ |  | 101765 | SCT-0(243)D | T0499 | Construct roadway widening | 2026 | STBGP >200 PHX-MESA | 2026 | 5072321.15 | 0 | 2173851.92 | 7246173.07
Scottsdale | Highway | 18658 | Scottsdale Rd: Pinnacle Peak to Jomax Rd | Principal Arterial - Other | Street | OCT-DEC 2028 | Maricopa | ALCP | 2 | 4 | 6 | No | No | Yes | No | Yes | No | No | No | SCT24-137DRB |  | 102229 | ----- | ----- | Design Roadway Widening | 2026 | RARF | 2026 | 0 | 210000 | -210000 | 0
Scottsdale | Highway | 18658 | Scottsdale Rd: Pinnacle Peak to Jomax Rd | Principal Arterial - Other | Street | OCT-DEC 2028 | Maricopa | ALCP | 2 | 4 | 6 | No | No | Yes | No | Yes | No | No | No | SCT24-137DZ2 |  | 102229 | ----- | ----- | Pre-Design Roadway Widening | 2026 | Local | 2026 | 0 | 0 | 300000 | 300000
Scottsdale | Highway | 30558 | Scottsdale Rd: Dixileta Dr to Carefree Highway | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 3 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT24-139RRB |  | 102222 | ----- | ----- | Acquisition of right-of-way for roadway improvements | 2026 | STBGP >200 PHX-MESA | 2026 | 350000 | 0 | -350000 | 0
Scottsdale | Highway | 30558 | Scottsdale Rd: Dixileta Dr to Carefree Highway | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 3 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT24-139RWZ |  | 102222 | ----- | ----- | Acquisition of right-of-way for roadway improvements | 2026 | Local | 2026 | 0 | 0 | 500000 | 500000
Scottsdale | Highway | 24722 | Shea Blvd Intersection Improvements | Principal Arterial - Other | Street | OCT-DEC 2025 | Maricopa | ALCP | 6 | 6 | 6 | No | No | Yes | No | Yes | No | No | Yes | SCT24-140DRB |  | 102209 | ----- | ----- | Design roadway improvements | 2026 | RARF | 2026 | 0 | 191338.46 | -191338.46 | 0
Scottsdale | Highway | 30524 | 14 intersections along Scottsdale Rd and Frank Lloyd Wright | Principal Arterial - Other | ITS | OCT-DEC 2028 | Maricopa | SM+O | 17.5 | 6 | 6 | No | No | No | No | Yes | No | Yes | No | SCT24-260D |  | 103095 | ----- | ----- | ADOT Design Review Fee | 2026 | Local | 2026 | 0 | 0 | 30000 | 30000
Scottsdale | Highway | 7209 | Raintree Drive: Hayden Road to Loop 101 | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-118RRB |  | 101053 | ----- | ----- | Acquisition of right-of-way for roadway improvements | 2026 | RARF | 2026 | 0 | 81231.83 | -81231.83 | 0
Scottsdale | Highway | 29852 | Raintree Drive: Scottsdale Rd to Hayden Rd | Minor Arterial | Street | APR-JUN 2024 | Maricopa | ALCP | 1.2 | 0 | 2 | No | No | No | No | Yes | No | No | No | SCT25-122CRB |  | 101229 | ----- | ----- | Construct new roadway | 2026 | RARF | 2026 | 0 | 826066.63 | -826066.63 | 0
Scottsdale | Highway | 29852 | Raintree Drive: Scottsdale Rd to Hayden Rd | Minor Arterial | Street | APR-JUN 2024 | Maricopa | ALCP | 1.2 | 0 | 2 | No | No | No | No | Yes | No | No | No | SCT25-122RRB |  | 101229 | ----- | ----- | Acquisition of right of way for roadway widening | 2026 | RARF | 2026 | 0 | 117086.7 | -117086.7 | 0
Scottsdale | Highway | 36968 | Pima Rd: Pinnacle Peak Rd to Happy Valley Rd | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 1 | 4 | 6 | No | No | Yes | No | Yes | No | No | No | SCT25-125CRB |  | 101267 | ----- | ----- | Construct roadway widening | 2026 | RARF | 2026 | 0 | 239871.1 | -239871.1 | 0
Scottsdale | Highway | 22239 | Pima Rd: Dynamite Blvd to Las Piedras | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 1.3 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-128CZ |  | 102220 | ----- | ----- | Construct Roadway Widening | 2026 | Local | 2026 | 0 | 0 | 24365900 | 24365900
Scottsdale | Highway | 22239 | Pima Rd: Dynamite Blvd to Las Piedras | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 1.3 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-128DRB |  | 102220 | ----- | ----- | Design Roadway Widening | 2026 | RARF | 2026 | 0 | 622961.16 | -622961.16 | 0
Scottsdale | Highway | 34361 | Pima Rd: Las Piedras to Stagecoach Rd | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 3.7 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-129CZ |  | 102227 | ----- | ----- | Construct Roadway Widening | 2026 | Local | 2026 | 0 | 0 | 29648796.69 | 29648796.69
Scottsdale | Highway | 34361 | Pima Rd: Las Piedras to Stagecoach Rd | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 3.7 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-129DRB |  | 102227 | ----- | ----- | Design Roadway Widening | 2026 | RARF | 2026 | 0 | 2450000 | -2450000 | 0
Scottsdale | Highway | 34361 | Pima Rd: Las Piedras to Stagecoach Rd | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 3.7 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-129DZ |  | 102227 | ----- | ----- | Design Roadway Widening | 2026 | Local | 2026 | 0 | 0 | 3500000 | 3500000
Scottsdale | Highway | 34361 | Pima Rd: Las Piedras to Stagecoach Rd | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 3.7 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-129RRB |  | 102227 | ----- | ----- | Acquisition of right-of-way for Roadway Widening | 2026 | RARF | 2026 | 0 | 350000 | -350000 | 0
Scottsdale | Highway | 34361 | Pima Rd: Las Piedras to Stagecoach Rd | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 3.7 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-129RWZ |  | 102227 | ----- | ----- | Acquisition of right-of-way for Roadway Widening | 2026 | Local | 2026 | 0 | 0 | 500000 | 500000
Scottsdale | Highway | 19791 | Carefree Hwy: Cave Creek Rd to Scottsdale Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | ALCP | 2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-130CZ3 |  | 102216 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 25020017 | 25020017
Scottsdale | Highway | 25440 | Pima Rd: Happy Valley Rd to Jomax Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-131DRB |  | 101765 | ----- | T0499 | Design roadway widening | 2026 | RARF | 2026 | 0 | 228447.22 | -228447.22 | 0
Scottsdale | Highway | 25440 | Pima Rd: Happy Valley Rd to Jomax Rd | Principal Arterial - Other | Street | APR-JUN 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-131SAVZ |  | 101765 | SCT-0(243)D | T0499 | Project savings for roadway widening | 2026 | STBGP-MAG | 2026 | 1137754.4 | 0 | 0 | 1137754.4
Scottsdale | Highway | 39752 | Scottsdale Rd: Jomax Rd to Dixileta Dr | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 2 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-138RRB |  | 101764 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 509959.21 | -509959.21 | 0
Scottsdale | Highway | 30558 | Scottsdale Rd: Dixileta Dr to Carefree Highway | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 3 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-139CRB |  | 102222 | ----- | ----- | Construct Roadway improvements | 2026 | STBGP-MAG | 2026 | 24758922.12 | 0 | -24758922.12 | 0
Scottsdale | Highway | 25253 | Happy Valley Rd: Pima Rd to Alma School Rd | Principal Arterial - Other | Street | JAN-MAR 2025 | Maricopa | ALCP | 2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-139CRB2 |  | 101174 | ----- | ----- | Construct Roadway Widening | 2026 | RARF | 2026 | 0 | 548946.92 | -548946.92 | 0
Scottsdale | Highway | 30558 | Scottsdale Rd: Dixileta Dr to Carefree Highway | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 3 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-139CZ |  | 102222 | ----- | ----- | Construct Roadway improvements | 2026 | Local | 2026 | 0 | 0 | 37638071 | 37638071
Scottsdale | Highway | 25253 | Happy Valley Rd: Pima Rd to Alma School Rd | Principal Arterial - Other | Street | JAN-MAR 2025 | Maricopa | ALCP | 2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-139RRB2 |  | 101174 | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | RARF | 2026 | 0 | 133833.62 | -133833.62 | 0
Scottsdale | Highway | 24722 | Shea Blvd Intersection Improvements | Principal Arterial - Other | Street | OCT-DEC 2025 | Maricopa | ALCP | 6 | 6 | 6 | No | No | Yes | No | Yes | No | No | Yes | SCT25-140CRB |  | 102209 | ----- | ----- | Construct roadway improvements | 2026 | RARF | 2026 | 0 | 2438324.53 | -2438324.53 | 0
Scottsdale | Highway | 28982 | Hayden/Miller: Pinnacle Peak to Happy Valley | Principal Arterial - Other | Street | OCT-DEC 2024 | Maricopa | ALCP | 1 | 0 | 4 | No | No | No | No | Yes | No | No | No | SCT25-143CRB2 |  | 102941 | ----- | ----- | Construct new roadway | 2026 | RARF | 2026 | 0 | 819216.2 | -819216.2 | 0
Scottsdale | Highway | 35912 | Pima Rd: Jomax Rd to Dynamite Blvd | Principal Arterial - Other | Street | OCT-DEC 2026 | Maricopa | ALCP | 1 | 4 | 4 | No | No | Yes | No | Yes | No | No | No | SCT25-147PDZ |  | 102228 | ----- | ----- | Preliminary design for roadway widening | 2026 | STBGP >200 PHX-MESA | 2026 | 210000 | 0 | 90000 | 300000
Scottsdale | Highway | 22239 | Pima Rd: Dynamite Blvd to Las Piedras | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 1.3 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT26-128CRB |  | 102220 | ----- | ----- | Construct Roadway Widening | 2026 | RARF | 2026 | 0 | 17056130 | -17056130 | 0
Scottsdale | Highway | 34361 | Pima Rd: Las Piedras to Stagecoach Rd | Principal Arterial - Other | Street | OCT-DEC 2029 | Maricopa | ALCP | 3.7 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT26-129CRB |  | 102227 | ----- | ----- | Construct Roadway Widening | 2026 | RARF | 2026 | 0 | 20754157.68 | -20754157.68 | 0
Scottsdale | Highway | 19791 | Carefree Hwy: Cave Creek Rd to Scottsdale Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | ALCP | 2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT26-130CZ |  | 102216 | ----- | ----- | Construct roadway widening | 2026 | STBGP-MAG | 2026 | 17514011.9 | 0 | -17514011.9 | 0
Scottsdale | Highway | 19791 | Carefree Hwy: Cave Creek Rd to Scottsdale Rd | Minor Arterial | Street | OCT-DEC 2028 | Maricopa | ALCP | 2 | 2 | 4 | No | No | Yes | No | Yes | No | No | No | SCT26-130SAV |  | 102216 | ----- | ----- | Construct roadway widening | 2026 | STBGP-MAG | 2026 | 3395787.11 | 0 | -3395787.11 | 0
Scottsdale | Highway | 30514 | Scottsdale Rd: Thompson Peak Pkwy to Pinnacle Peak Pkwy (Phase II) | Principal Arterial - Other | Street | JAN-MAR 2026 | Maricopa | ALCP | 2 | 4 | 6 | No | No | Yes | No | Yes | No | No | No | SCT26-136CZ |  | 102224 | ----- | ----- | Construct roadway widening | 2026 | Local | 2026 | 0 | 0 | 5897143 | 5897143
Scottsdale | Highway | 18254 | Thomas Rd: 56th St to 74th St | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.3 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | SCT26-520D |  | 105783 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 21000 | 0 | 9000 | 30000
Scottsdale | Highway | 18254 | Thomas Rd: 56th St to 74th St | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.3 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | SCT26-520R |  | 105783 | ----- | ----- | Roadway rehabilitation (Right of Way) | 2026 | STBGP >200 PHX-MESA | 2026 | 245000 | 0 | 125000 | 370000
Scottsdale | Highway | 30514 | Scottsdale Rd: Thompson Peak Pkwy to Pinnacle Peak Pkwy (Phase II) | Principal Arterial - Other | Street | JAN-MAR 2026 | Maricopa | ALCP | 2 | 4 | 6 | No | No | Yes | No | Yes | No | No | No | SCT27-136CZ |  | 102224 | ----- | ----- | Construct Roadway Widening | 2026 | Local | 2026 | 0 | 0 | 20000000 | 20000000
Scottsdale | Highway | 29143 | Legacy Boulevard: 94th Street to 98th Street | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-004RW |  |  | ----- | ----- | Acquisition of right-of-way for new bridge | 2027 | Local | 2027 | 0 | 0 | 1449420.6 | 1449420.6
Scottsdale | Highway | 29143 | Legacy Boulevard: 94th Street to 98th Street | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-004RWRB |  |  | ----- | ----- | Acquisition of right-of-way for new bridge (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 960531.3 | -960531.3 | 0
Scottsdale | Highway | 39312 | Goldwater Boulevard on the west side of Scottsdale Road: Rancho Vista and Chaparral Road | Principal Arterial - Other | Bike/Ped | JAN-MAR 2029 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | Yes | Yes | No | SCT23-040 |  | 101862 | SCT-0(244)D | T0571 | New non-motorized underpass with sidewalks to tie into Scottsdale Rd and Chaparral Dr and Scottsdale Rd and Rancho Vista Dr traffic signals (Construction) | 2027 | CMAQ | 2027 | 2352421 | 0 | 142193 | 2494614
Scottsdale | Highway | 30524 | 14 intersections along Scottsdale Rd and Frank Lloyd Wright | Principal Arterial - Other | ITS | OCT-DEC 2028 | Maricopa | SM+O | 17.5 | 6 | 6 | No | No | No | No | Yes | No | Yes | No | SCT24-260C |  | 103095 | ----- | ----- | Flashing Yellow Arrow heads and accessories (Procurement / Construction) | 2027 | CMAQ | 2027 | 768545 | 0 | 46455 | 815000
Scottsdale | Highway | 47972 | Central Arizona Canal: Scottsdale Road to Northsight Boulevard. | Principal Arterial - Other | Bike/Ped | JAN-MAR 2029 | Maricopa | Other | 1.7 | 6 | 6 | No | No | No | No | No | Yes | Yes | No | SCT25-250C |  | 103071 | SCT-0(245)T | T0573 | Construct Shared-use path (10' min.) | 2027 | CMAQ | 2027 | 2372024.94 | 0 | 207378 | 2579402.94
Scottsdale | Highway | 29143 | Legacy Boulevard: 94th Street to 98th Street | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-004C |  |  | ----- | ----- | Construct new bridge | 2028 | Local | 2028 | 0 | 0 | 2898841.2 | 2898841.2
Scottsdale | Highway | 29143 | Legacy Boulevard: 94th Street to 98th Street | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-004CRB |  |  | ----- | ----- | Construct new bridge (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 1921062.6 | -1921062.6 | 0
Scottsdale | Highway | 49038 | Dynamite Boulevard: 56th Street to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 4 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-016D |  |  | ----- | ----- | Design roadway widening | 2028 | Local | 2028 | 0 | 0 | 6836170.8 | 6836170.8
Scottsdale | Highway | 49038 | Dynamite Boulevard: 56th Street to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 4 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-016DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2028 | 479 RARF ALCP | 2028 | 0 | 4530332 | -4530332 | 0
Scottsdale | Highway | 18254 | Thomas Rd: 56th St to 74th St | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 2.3 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | SCT26-520C |  | 105783 | ----- | ----- | Roadway rehabilitation (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 17113098.98 | 0 | 7334185.28 | 24447284.26
Scottsdale | Highway | 49038 | Dynamite Boulevard: 56th Street to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 4 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-016RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2029 | Local | 2029 | 0 | 0 | 20508512.4 | 20508512.4
Scottsdale | Highway | 49038 | Dynamite Boulevard: 56th Street to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 4 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-016RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2029 | 479 RARF ALCP | 2029 | 0 | 13590996 | -13590996 | 0
Scottsdale | Highway | 13985 | Pinnacle Peak Road: Scottsdale Road to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-006C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 15297687.6 | 15297687.6
Scottsdale | Highway | 13985 | Pinnacle Peak Road: Scottsdale Road to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-006CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 10137781.8 | -10137781.8 | 0
Scottsdale | Highway | 13985 | Pinnacle Peak Road: Scottsdale Road to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-006D |  |  | ----- | ----- | Design roadway widening | 2030 | Local | 2030 | 0 | 0 | 2549614.6 | 2549614.6
Scottsdale | Highway | 13985 | Pinnacle Peak Road: Scottsdale Road to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-006DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 1689630.3 | -1689630.3 | 0
Scottsdale | Highway | 13985 | Pinnacle Peak Road: Scottsdale Road to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-006RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2030 | Local | 2030 | 0 | 0 | 7648843.8 | 7648843.8
Scottsdale | Highway | 13985 | Pinnacle Peak Road: Scottsdale Road to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-006RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 5068890.9 | -5068890.9 | 0
Scottsdale | Highway | 49038 | Dynamite Boulevard: 56th Street to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 4 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-016C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 41017024.8 | 41017024.8
Scottsdale | Highway | 49038 | Dynamite Boulevard: 56th Street to Pima Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 4 | 2 | 4 | No | No | No | No | No | No | No | No | SCT20-016CRB |  |  | ----- | ----- | Construct roadway widening (Reimb.) | 2030 | 479 RARF ALCP | 2030 | 0 | 27181992 | -27181992 | 0
Scottsdale | Transit | 40751 | Regionwide: Scottsdale |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | SCT26-510T |  |  | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PMS | 2025 | 195288 | 0 | 48822 | 244110
Surprise | Highway | 39274 | 163rd Avenue: US 60 (Grand Avenue) to Jomax Road | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.7 | 4 | 6 | No | No | No | No | No | No | No | No | SUR20-026D |  |  | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 2825319.6 | 2825319.6
Surprise | Highway | 40880 | Waddell Road: 175th Avenue to Cotton Lane | Major Collector | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SUR20-126D |  |  | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 783789.9 | 783789.9
Surprise | Highway | 40880 | Waddell Road: 175th Avenue to Cotton Lane | Major Collector | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SUR20-126RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2026 | Local | 2026 | 0 | 0 | 2351369.7 | 2351369.7
Surprise | Highway | 16867 | Cotton Ln: Cactus Rd to Waddell Rd | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 1 | 2 | 6 | No | No | No | No | Yes | No | No | No | SUR23-001 |  | 102234 | ----- | ----- | Construct 2 lanes in each direction with bike lane and sidewalk | 2026 | Private | 2026 | 0 | 0 | 12000000 | 12000000
Surprise | Highway | 35684 | 163rd Ave and Jomax Rd - Phase 2 | Minor Arterial | Street | OCT-DEC 2026 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | Yes | Yes | No | No | SUR25-205 |  | 103745 | ----- | ----- | Intersection widening, including box culvert | 2026 | Local | 2026 | 0 | 0 | 6837500 | 6837500
Surprise | Highway | 22786 | Waddell Road: Litchfield Road to Bullard Avenue | Minor Arterial | ITS | OCT-DEC 2027 | Maricopa | SM+O | 1 | 6 | 6 | No | No | No | No | Yes | No | Yes | No | SUR25-260C |  | 103943 | SUR-0(237)T | T0588 | Conduit, pull boxes, and fiber optic infrastructure (Construction) | 2026 | CMAQ | 2026 | 511923 | 0 | 30943 | 542866
Surprise | Highway | 22786 | Waddell Road: Litchfield Road to Bullard Avenue | Minor Arterial | ITS | OCT-DEC 2027 | Maricopa | SM+O | 1 | 6 | 6 | No | No | No | No | Yes | No | Yes | No | SUR25-260D |  | 103943 | SUR-0(237)T | T0588 | Conduit, pull boxes, and fiber optic infrastructure (Design) | 2026 | Local | 2026 | 0 | 0 | 89000 | 89000
Surprise | Highway | 22786 | Waddell Road: Litchfield Road to Bullard Avenue | Minor Arterial | ITS | OCT-DEC 2027 | Maricopa | SM+O | 1 | 6 | 6 | No | No | No | No | Yes | No | Yes | No | SUR25-260D1 |  | 103943 | SUR-0(237)T | T0588 | ADOT Design Review Fee | 2026 | Local | 2026 | 0 | 0 | 30000 | 30000
Surprise | Highway | 43124 | 155th Avenue: Pinnacle Peak Road to Happy Valley Road | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-001D |  |  | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 1298300 | 1298300
Surprise | Highway | 43124 | 155th Avenue: Pinnacle Peak Road to Happy Valley Road | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-001DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2026 | 479 RARF ALCP | 2026 | 0 | 908810 | -908810 | 0
Surprise | Highway | 14943 | Pinnacle Peak Road: 163rd Avenue to 155th Avenue | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-002D |  |  | ----- | ----- | Design roadway widening | 2026 | Local | 2026 | 0 | 0 | 1072200 | 1072200
Surprise | Highway | 14943 | Pinnacle Peak Road: 163rd Avenue to 155th Avenue | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-002DRB |  |  | ----- | ----- | Design roadway widening (Reimb.) | 2026 | 479 RARF ALCP | 2026 | 0 | 519417.7 | -519417.7 | 0
Surprise | Highway | 39274 | 163rd Avenue: US 60 (Grand Avenue) to Jomax Road | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.7 | 4 | 6 | No | No | No | No | No | No | No | No | SUR20-026RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 8475958.8 | 8475958.8
Surprise | Highway | 40880 | Waddell Road: 175th Avenue to Cotton Lane | Major Collector | Street | OCT-DEC 2027 | Maricopa | 479-ALCP | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SUR20-126C |  |  | ----- | ----- | Construct roadway widening | 2027 | Local | 2027 | 0 | 0 | 4702739.4 | 4702739.4
Surprise | Highway | 12113 | Happy Valley Rd: 163rd Ave to El Granada Blvd | Principal Arterial - Other | Street | OCT-DEC 2028 | Maricopa | Other | 3.5 | 2 | 6 | No | No | No | No | Yes | No | No | No | SUR25-503 |  | 105753 | ----- | ----- | Roadway Widening - Construct 2 lanes in each direction with curb, gutter, and sidewalks | 2027 | Local | 2027 | 0 | 0 | 40000000 | 40000000
Surprise | Highway | 43124 | 155th Avenue: Pinnacle Peak Road to Happy Valley Road | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-001RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 6113150 | 6113150
Surprise | Highway | 43124 | 155th Avenue: Pinnacle Peak Road to Happy Valley Road | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-001RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 4279205 | -4279205 | 0
Surprise | Highway | 14943 | Pinnacle Peak Road: 163rd Avenue to 155th Avenue | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-002RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2027 | Local | 2027 | 0 | 0 | 6393590 | 6393590
Surprise | Highway | 14943 | Pinnacle Peak Road: 163rd Avenue to 155th Avenue | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 1 | 2 | 4 | No | No | No | No | No | No | No | No | SUR26-002RWRB |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening (Reimb.) | 2027 | 479 RARF ALCP | 2027 | 0 | 1558253.1 | -1558253.1 | 0
Surprise | Highway | 39274 | 163rd Avenue: US 60 (Grand Avenue) to Jomax Road | Major Collector | Street | OCT-DEC 2028 | Maricopa | 479-ALCP | 2.7 | 4 | 6 | No | No | No | No | No | No | No | No | SUR20-026C |  |  | ----- | ----- | Construct roadway widening | 2028 | Local | 2028 | 0 | 0 | 16951917.6 | 16951917.6
Surprise | Highway | 42479 | Tierra Buena Ln: Bullard Ave to Statler Blvd | Minor Collector | Street | APR-JUN 2030 | Maricopa | Other | 0.7 | 2 | 4 | No | No | No | No | Yes | Yes | No | No | SUR20-801 |  | 101292 | ----- | ----- | Construct 2 lanes in the eastern direction with curb, gutter, raised median, sidewalks and bike lane. | 2029 | Private | 2029 | 0 | 0 | 5000000 | 5000000
Surprise | Highway | 2860 | Civic Center Parkway : Bell Rd to Paradise Ln | Minor Arterial | Street | JUL-SEP 2030 | Maricopa | Other | 0.5 | 2 | 4 | No | No | No | No | No | No | No | No | SUR25-203 |  | 105055 | ----- | ----- | Construct 1 outside lane in each direction with curb, gutter, and sidewalks | 2030 | Private | 2030 | 0 | 0 | 3840000 | 3840000
Tempe | Highway | 18102 | Broadway Rd: 55th St to Mill Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1.5 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | TMP26-520D |  | 105777 | ----- | ----- | Roadway rehabilitation (ADOT Fee) | 2026 | STBGP >200 PHX-MESA | 2026 | 7000 | 0 | 3000 | 10000
Tempe | Highway | 15199 | Ray Rd. to Continental Dr.; Evergreen to Interstate-10 |  | Air Quality | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | TMP26-580 |  |  | ----- | ----- | Purchase PM-10 certified street sweepers | 2026 | CMAQ | 2026 | 378946 | 0 | 22905 | 401851
Tempe | Highway | 18102 | Broadway Rd: 55th St to Mill Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1.5 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | TMP26-520D1 |  | 105777 | ----- | ----- | Roadway rehabilitation (Design) | 2027 | STBGP >200 PHX-MESA | 2027 | 343000 | 0 | 147000 | 490000
Tempe | Highway | 18102 | Broadway Rd: 55th St to Mill Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1.5 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | TMP26-520C |  | 105777 | ----- | ----- | Roadway rehabilitation (Construction) | 2028 | STBGP >200 PHX-MESA | 2028 | 3511043.9 | 0 | 1504733.1 | 5015777
Tempe | Highway | 18102 | Broadway Rd: 55th St to Mill Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1.5 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | TMP26-520R |  | 105777 | ----- | ----- | Roadway rehabilitation (Right of Way) | 2028 | STBGP >200 PHX-MESA | 2028 | 31500 | 0 | 13500 | 45000
Tempe | Highway | 18102 | Broadway Rd: 55th St to Mill Ave | Minor Arterial | Street | OCT-DEC 2029 | Maricopa | Other | 1.5 | 5 | 5 | Yes | No | Yes | No | No | Yes | No | No | TMP26-520U |  | 105777 | ----- | ----- | Roadway rehabilitation (Utilities) | 2028 | STBGP >200 PHX-MESA | 2028 | 266000 | 0 | 114000 | 380000
Tempe | Highway | 22988 | Pedestrian Bridge across Rio Salado North Bank and Shared-use Path: North Bank to -Indian Bend Wash/McClintock Drive | Local | Bike/Ped | OCT-DEC 2030 | Maricopa | Other | 1.1 | 0 | 0 | No | No | No | No | No | Yes | No | No | TMP30-540C |  | 105801 | ----- | ----- | Construct Bicycle and Pedestrian Bridge across the Rio Salado River, construct 0.25 mile shared-use path along the North Bank from the bridge to the regional Indian Bend Wash Path and McClintock Drive. Rehabilitation of the existing Tempe Indian Bend Wash Path, lighting, ADA improvements, landscaping, and pedestrian amenities. | 2030 | RAISE | 2025 | 25000000 | 0 | 22676257 | 47676257
Tolleson | Highway | 15630 | 99th Avenue: Van Buren Street to Lower Buckeye Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 6 | No | No | No | No | No | No | No | No | TOL20-002D |  |  | ----- | ----- | Design roadway widening | 2027 | Local | 2027 | 0 | 0 | 1970634.3 | 1970634.3
Tolleson | Highway | 15630 | 99th Avenue: Van Buren Street to Lower Buckeye Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 6 | No | No | No | No | No | No | No | No | TOL20-002RW |  |  | ----- | ----- | Acquisition of right-of-way for roadway widening | 2028 | Local | 2028 | 0 | 0 | 5911902.9 | 5911902.9
Tolleson | Highway | 15630 | 99th Avenue: Van Buren Street to Lower Buckeye Road | Minor Arterial | Street | OCT-DEC 2030 | Maricopa | 479-ALCP | 2 | 2 | 6 | No | No | No | No | No | No | No | No | TOL20-002C |  |  | ----- | ----- | Construct roadway widening | 2030 | Local | 2030 | 0 | 0 | 11823805.8 | 11823805.8
Tolleson | Highway | 15547 | McDowell Road: 99th Avenue to 91st Avenue | Minor Arterial | Street | OCT-DEC 2032 | Maricopa | 479-ALCP | 1 | 3 | 6 | No | No | No | No | No | No | No | No | TOL20-008D |  |  | ----- | ----- | Design roadway widening | 2030 | Local | 2030 | 0 | 0 | 915077.9 | 915077.9
Valley Metro Rail | Transit | 46277 | Regionwide: Valley Metro Rail |  | Transit Rail | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMR23-275T |  | 103236 | ----- | 11.44.03 | Systemwide refurbishments | 2026 | 5337-FGM PMS | 2025 | 7090896 | 1772724 | 0 | 8863620
Valley Metro Rail | Transit | 31491 | Regionwide: Valley Metro Rail |  | Transit Rail | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMR26-570T |  |  | ----- | 12.12.20 | Purchase Vehicle: Light Rail 1 replace | 2026 | CMAQ-Flex | 2025 | 6536870 | 0 | 1634218 | 8171088
Valley Metro Rail | Transit | 31491 | Regionwide: Valley Metro Rail |  | Transit Rail | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMR26-571T |  |  | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PMS | 2025 | 3100262 | 0 | 775066 | 3875328
Valley Metro Rail | Transit | 31491 | Regionwide: Valley Metro Rail |  | Transit Rail | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMR26-572T |  |  | ----- | ----- | Light Rail Safety Enhancement Placeholder (PTASP) | 2026 | 5307-PMS | 2025 | 579473 | 0 | 144868 | 724341
Valley Metro Rail | Transit | 45013 | University Dr at Rural Rd |  | Transit Rail | OCT-DEC 2030 | Maricopa | 479-TLCP | 0 | 0 | 0 | No | No | No | No | No | Yes | Yes | No | VMR29-570T |  | 105103 | ----- | ----- | Transit: Rail Crossing (grade separation) | 2029 | 5307-PMS | 2028 | 41071199 | 0 | 17601942 | 58673141
Valley Metro Rail | Transit | 5248 | Scottsdale Rd/Rural Rd |  | Transit Bus | OCT-DEC 2030 | Maricopa | 479-TLCP | 0 | 0 | 0 | No | No | No | No | No | Yes | Yes | No | VMR30-530T |  | 105057 | ----- | ----- | Scottsdale Rd/Rural Rd Bus Rapid Transit (BRT) | 2030 | PTF | 2030 | 0 | 790023301 | 338581415 | 1128604716
Valley Metro Rail | Transit | 45013 | University Dr at Rural Rd |  | Transit Rail | OCT-DEC 2030 | Maricopa | 479-TLCP | 0 | 0 | 0 | No | No | No | No | No | Yes | Yes | No | VMR30-570T |  | 105103 | ----- | ----- | Transit: Rail Crossing (grade separation) | 2030 | 5307-PMS | 2029 | 41071199 | 0 | 17601943 | 58673142
Valley Metro/RPTA | Transit | 47757 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | VMT25-218T |  | 103172 | AZ-2025-013-00 | 30.09.01 | East Valley RideChoice | 2026 | 5310-PMS | 2023 | 101696 | 0 | 101696 | 203392
Valley Metro/RPTA | Transit | 12972 | Regionwide: Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-211T |  | 103149 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI PGA | 2025 | 100000 | 0 | 25000 | 125000
Valley Metro/RPTA | Transit | 6560 | Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-212T |  | 103146 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 9 replace (Express Bus) | 2026 | 5337-HI PMS | 2025 | 8150984 | 1438409 | 0 | 9589393
Valley Metro/RPTA | Transit | 6560 | Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-213T |  | 103146 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 5 replace (Express bus) | 2026 | 5339-PMS | 2025 | 4419600 | 824330 | 0 | 5243930
Valley Metro/RPTA | Transit | 47757 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | VMT26-500T |  | 103172 | ----- | 30.09.01 | West Valley RideChoice | 2026 | 5310-PMS | 2023 | 130900 | 0 | 130900 | 261800
Valley Metro/RPTA | Transit | 47757 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | VMT26-501T |  | 103172 | ----- | 30.09.01 | East Valley RideChoice | 2026 | 5310-PMS | 2023 | 507426 | 0 | 507426 | 1014852
Valley Metro/RPTA | Transit | 47757 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | VMT26-502T |  | 103172 | ----- | 30.09.01 | East Valley RideChoice | 2026 | 5310-PMS | 2025 | 86574 | 0 | 86574 | 173148
Valley Metro/RPTA | Transit | 47757 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | VMT26-503T |  | 103172 | ----- | 11.7L.00 | Valley Metro Travel Training | 2026 | 5310-PMS | 2025 | 176000 | 0 | 44000 | 220000
Valley Metro/RPTA | Transit | 47757 | Regionwide |  | Transit Other | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | Yes | No | No | No | VMT26-504T |  | 103172 | ----- | 30.09.01 | Valley Metro West Valley RideChoice | 2026 | 5310-PGA | 2025 | 73587 | 0 | 73587 | 147174
Valley Metro/RPTA | Transit | 10865 | Regionwide:Valley Metro/RPTA |  | Transit Bus | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-510T |  | 103741 | AZ-2021-049 | 30.09.00 | Operating Assistance | 2026 | 5307-AVN UZA | 2020 | 82880 | 0 | 82880 | 165760
Valley Metro/RPTA | Transit | 25589 | Regionwide: Valley Metro/RPTA |  | Transit Bus | OCT-DEC 2027 | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-511T |  | 103184 | AZ-2024-019 | 30.09.00 | Operating Assistance | 2026 | 5307-AVN UZA | 2023 | 43581 | 0 | 43581 | 87162
Valley Metro/RPTA | Transit | 6560 | Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-512T |  | 103146 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 3 replace (Express bus) | 2026 | 5337-HI | 2023 | 2674404 | 471954 | 0 | 3146358
Valley Metro/RPTA | Transit | 12972 | Regionwide: Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-513T |  | 103149 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI | 2023 | 550230 | 0 | 137558 | 687788
Valley Metro/RPTA | Transit | 6560 | Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-514T |  | 103146 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 1 replace (Express bus) | 2026 | 5337-HI PGA | 2024 | 891468 | 157318 | 0 | 1048786
Valley Metro/RPTA | Transit | 12972 | Regionwide: Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-515T |  | 103149 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI PGA | 2024 | 18668 | 0 | 4667 | 23335
Valley Metro/RPTA | Transit | 6560 | Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-516T |  | 103146 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 1 replace (Express bus) | 2026 | 5337-HI PMS | 2024 | 891468 | 157318 | 0 | 1048786
Valley Metro/RPTA | Transit | 12972 | Regionwide: Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-517T |  | 103149 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5337-HI PMS | 2024 | 2712322 | 0 | 678081 | 3390403
Valley Metro/RPTA | Transit | 6560 | Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-518T |  | 103146 | ----- | 11.12.01 | Purchase bus: standard 40 foot - 2 replace (Express bus) | 2026 | 5339-PMS | 2024 | 1862452 | 328668 | 0 | 2191120
Valley Metro/RPTA | Transit | 12972 | Regionwide: Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-519T |  | 103149 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PMS | 2025 | 6051923 | 0 | 1512981 | 7564904
Valley Metro/RPTA | Transit | 6560 | Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | TLCP | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-520T |  | 103146 | ----- | 11.71.12 | Capital Cost of Contracting - Vanpool Program | 2026 | 5307-PMS | 2025 | 3000000 | 0 | 750000 | 3750000
Valley Metro/RPTA | Transit | 12972 | Regionwide: Valley Metro/RPTA |  | Transit Bus | N/A | Maricopa | Other | 0 | 0 | 0 | No | Yes | No | No | No | Yes | No | No | VMT26-521T |  | 103149 | ----- | 11.7A.00 | Preventive Maintenance | 2026 | 5307-PGA | 2025 | 295109 | 0 | 73777 | 368886

## Dictionary
Contact Information of Person Requesting the Change | Name |  |  | The name of the person requesting the change
| Phone |  |  | A phone number to call for additional information
| E-mail |  |  | An e-mail address to contact for additional information
| Date Submitted |  |  | The date the request was submitted
Project Information | Agency |  |  | The name of the agency sponsoring the project. A drop down list of agencies is associated with the cell
| Section |  |  | The Section of the TIP the project information is or will be located. This is limited to "Highway" and "Transit"
| MAG ID |  |  | The project identification number used by MAG in the TIP. Leave blank for a new project.
| Location |  |  | The location of the project. Where applicable, please use a 'On Road.. From Limit To Limit' format.
| Federal Functional Classification |  |  | The current federal function classification of the roadway. If the project is on an unclassified roadway, enter 'Local' in the input cell. If the classification is not applicable, please leave the input cell blank.
| MAG Mode |  |  | The MAG mode of the project. A drop down list of MAG modes is associated with the input cell.
| Estimate Date for Completion/Open to Traffic: MM/YY |  |  | The month and year the project is anticipated to be in service
| AQ Area |  |  | The County the project is located in for air quality purposes. Enter an 'M' for Maricopa or a 'P' for Pinal.
| In Program |  |  | The funding program for the project. A drop down list is associated with the cell.
| Miles |  |  | The length in miles of the project. If not applicable, please enter '0'
| Through Lanes | Before |  | The number of through lanes on the roadway before the project is completed. Do not include turn lanes. If not applicable, enter a '0'.
|  | After |  | The number of through lanes on the roadway after the project is completed. Do not include turn lanes. If not applicable, enter a '0'.
| Performance Categories | PM1 | Safety | Please enter 'Yes' if the project may influence SAFETY Performance as follows: • Number of fatalities • Number of serious injuries • Rate of fatalities • Rate of serious injuries • Number of non-motorized fatalities and non-motorized serious injuries
|  | PM2T | Transit Asset Condition | Please enter 'Yes' if the project may influence TRANSIT ASSET CONDITION Performance as follows: • Transit Vehicles (Bus/Rail): ROLLING STOCK - EXPAND FLEET • Transit Vehicles (Bus/Rail): ROLLING STOCK - REPLACE EXISTING FLEET • Systems Improvements: EXTEND LINE • Systems Improvements: IMPROVE LINE • Guideway/Facility Improvements: REHABILITATE REPLACE
|  | PM2N | Pavement Condition | Please enter if the project could influence PAVEMENT CONDITION Performance as follows: • Percentage of Interstate pavements in Good condition • Percentage of Interstate pavements in Poor condition • Percentage of non-Interstate NHS pavements in Good condition • Percentage of non-Interstate NHS pavements in Poor condition
|  | PM2B | Bridge Condition | Please enter 'Yes' if the project could influence BRIDGE CONDITION Performance as follows: • Percentage of NHS bridges in Good condition • Percentage of NHS bridges in Poor condition
|  | PM3F | Travel Reliability | Please enter "Yes" if the project may influence TRAVEL • Freight Movement Measure • Truck Travel Time Reliability (TITR) index • Travel Time Reliability -Non-Interstate ·- • Peak Hour Excessive Delay Per Capita
|  | PM3S | Non SOV Travel | Please enter 'Yes if the project could influence NON-SOV TRAVEL performance as follows: • Percent of person-miles traveled on the interstate and non-interstate that are reliable • Percent of Non-Single Occupancy Vehicle Travel
|  | PM3E | CMAQ Emissions | Please enter 'Yes' if the project could influence EMMISSIONS REDUCTION performance as follows: • CMAQ Emissions Measure • PM-10 and PM-2.5 • CMAQ Traffic Congestion Measures Percent of Non-Single Occupancy Vehicle (SOV) travel in each urbanized area
Work Phase Information | TIP ID |  |  | The TIP ID for the work phase. If this is a new work phase leave the cell blank.
| Federal ID / Grant ID |  |  | For Highway Section projects, the Federal Identification number for the project; for Transit Section projects, the Transit Grant Identification number.
| TRACS / ALI |  |  | For Highway Section projects, the ADOT identification code for the project; for Transit Section projects the transit work breakdown code.
| Work |  |  | A short description of the work to be performed. The work description should begin with a verb and provide enough information to know what work is being performed.
| Work Year |  |  | The year the work is programmed in the TIP. A drop down box with applicable years is associated with the cell.
| Funding Type |  |  | The primary source of funding for the work. If the work is federally funded, the source will be federal source. A drop down list is associated with the cell.
| Apportionment Year |  |  | The appropriation year for funding. If requesting changes to a transit project, enter the appropriate value, otherwise enter the 'Work Year' as identified above.
| Federal |  |  | The federal amount programmed for the work phase. Enter '0' if no federal funds are programmed.
| Regional |  |  | The RARF or PTF amount programmed for the work phase. Enter '0' if no RARF or PTF funds are programmed.
| Local |  |  | The State, local or private amount programmed for the work phase. Enter '0' if none are programmed.
| Total |  |  | The total funding programmed. This is the sum of the 'Federal', 'Regional' and 'Local' cells.
Note/Justification |  |  |  | A brief note describing what action is requested.
Items in light blue are needed for modeling purposes if project is regionally significant prior to inclusion in the TIP.

## Constants (hidden)
AgenciesLU | SectionLU | ModeLU | AqAreaLU | LifeCycleProgramLU | YearLU | FundingLU | YesNoLU | FedFuncLU
ADOT | Highway | Air Quality | M | Other | 2018 | 5307 | Yes | Local
Apache Junction | Transit | Bicycle | P | ALCP | 2019 | 5311 | No | Major Collector
Avondale |  | Bike/Ped |  | TLCP | 2020 | 5339 |  | Minor Arterial
Buckeye |  | Bridge |  | RFHP | 2021 | 5307-AVN UZA |  | Minor Collector
Carefree |  | Freeway |  | 5-year | 2022 | 5309-New Starts |  | Principal Arterial - Interstate
Cave Creek |  | Freeway Interchange |  | UPWP |  | 5310-AZ |  | Principal Arterial - Other
Chandler |  | ITS |  |  |  | 5310-MAG |  | Principal Arterial - Other Freeway or Expressway
El Mirage |  | Maintenance |  |  |  | 5337-FGM
Florence |  | Other |  |  |  | 5337-HI
Fort McDowell Yavapai Nation |  | Pedestrian |  |  |  | CMAQ
Fountain Hills |  | Safety |  |  |  | CMAQ-2.5
Gila Bend |  | Street |  |  |  | CMAQ-Flex
Gila River Indian Community |  | Street Intersection |  |  |  | FLAP
Gilbert |  | Telecomms |  |  |  | HSIP
Glendale |  | Transit Bus |  |  |  | HSIP-AZ
Goodyear |  | Transit Other |  |  |  | HSIP-MAG
Guadalupe |  | Transit Rail |  |  |  | STBGP-AZ-Flex
Litchfield Park | [5 empty] | STBGP-MAG
Maricopa (City) | [5 empty] | STBGP-MAG-Flex
Maricopa County | [5 empty] | STBGP-MAG-SPF
Mesa | [5 empty] | STP-AZ-Flex
Paradise Valley | [5 empty] | STP-Flex
Peoria | [5 empty] | STP-MAG
Phoenix | [5 empty] | TA-MAG
Pinal County | [5 empty] | TAP-MAG
Queen Creek | [5 empty] | TIGER
Salt River Pima-Maricopa Indian Community | [5 empty] | TTP-BIA
Scottsdale | [5 empty] | PTF
Surprise | [5 empty] | RARF
Tempe | [5 empty] | Local
Tolleson | [5 empty] | NHPP
Valley Metro Rail | [5 empty] | Private
Valley Metro/RPTA | [5 empty] | State
Wickenburg
Youngtown